## DPC
Project Details |  | Data Provision Checklist Details (insert below) | Version 1.0 - Feb 2020 Sponsor: DEPU
Project Number:
Project Name:
Project Location (Region):
New Construction/Extension Or Upgrade Existing
EIPP Endorsed by PD / PM
Planned Start
Planned Finish
PD/PM / PMCA
Contractor Representative
PSS Representative
Zone EMP Representative
Project Phase |  | Data Provision Actions and Deliverables | Responsible Person | Planned Completion Date | Completed Y/N | Completion Date | Comments
Design
1 | Design | PMCA requests data extracts from GEMS and copy of spaces plan to be provided to the Designer (required for existing facilities, extending current infrastructure and/or upgrading existing) | (request) PMCA (supply) GEMS Master Data Team (MDT) (supply) EMOS - Spaces Plan
2 | Design | Designer to identify (new or existing) assets and provide the data requirements. | Designer
3 | Design | EMOS PSS provides feedback on Data Requirements | EMOS PSS
4 | Design | The Project submits request for Asset Shell record GDLs for Buildings, Levels, Spaces, Infrastructure, Equipment Systems & Equipment (where known) etc. and provides a new or updated spaces plan. | PD / PM / PMCA
5 | Design | All required GEMS Asset Shells have been created in GEMS at the 90% design - Building, Level, Space, Infrastructure, Equipment Systems & Equipment (where known) etc. | PD / PM / PMCA and MDT
6 | Design | Design Drawings Completed - End of design phase. | Designer
Construction
7 | Pre-mobilisation | Data Extracts from GEMS provided to Contractor Representative (required for existing facilities, extending current infrastructure and/or upgrading existing) | (request) Contractor Rep (supply) MDT
8 | Pre-mobilisation | Complete and agree Estate Information Provision Plan (EIPP) and Data Provision Checklist (DPC) requirements and schedule for construction and DLP phases. | Contractor Representative
9 | Pre-mobilisation | Asset Labelling preparation | Contractor Representative (Review\Support) - EMOS PSS
10 | Construction | Submission of GDLs throughout construction phase (GDL submissions can be grouped to logical work elements depending on nature of project. Add lines below to indicate schedule for additional GDL delivery times) | Contractor Representative
11 | Construction | Additional GDL submissions, as required & determined by project | Contractor Representative
11 | Construction | Additional GDL submissions, as required & determined by project | Contractor Representative
28 Day notice of Completion (CFI project) or 90% construction for all other projects.
12 | Construction | Final submission to EMOS PSS of all GDLs - all data fields completed. | Contractor Representative
13 | Construction | Submission of draft O&MM for validation. | Contractor Representative
14 | Construction | Submission of draft As Constructed drawings for validation. | Contractor Representative
15 | Construction | Spaces Plan prepared and submitted IAW SDMP | Contractor Representative
16 | Construction | RFI Notice to request Mater Site Plan (MSP) for Update purposes issued to EMOS PSS | PMCA
17 | Construction | MSP sent to EMOS for validating and uploading to NSIMS | Contractor Representative
18 | Construction | EMOS PSS feedback on draft O&MM | EMOS PSS
19 | Construction | EMOS PSS feedback on draft As Constructed (ASCON) drawings | EMOS PSS
Hand Over Take Over (HOTO)
21 | HOTO | Submission of GDLs for outstanding items identified prior to HOTO | Contractor Representative
22 | HOTO | Specified/Identified GDLs accurately completed and provided to the MDT for uploading to GEMS | EMOS PSS
23 | HOTO | Warranty information recorded in GEMS via a GDL (copy of certificates placed in O&MM) | Contractor Representative
24 | HOTO | All ASCON drawings are delivered in accordance with the contract requirements and agreed changes implemented. | Contractor Representative
25 | HOTO | All O&MM are delivered in accordance with the contract requirements and agreed changes are implemented. | Contractor Representative
26 | HOTO | EMOS PSS have reviewed and accepted Key Datasets (MSP, Spaces Plan) | EMOS PSS
27 | HOTO | EMOS PSS confirm all ASCON drawings and O&MM received and agreed changes are complete. | EMOS PSS
Defect Liability Period (DLP)
28 | DLP | GDLs submitted as a result of defect rectifications | Contractor Representative
29 | DLP | O&MM and ASCONs updated as a result of defect rectifications | Contractor Representative
30 | DLP | EMOS PSS confirm all defect rectification updates received and uploaded to NSIMS / Objective or forwarded to the MDT for upload to GEMS. | EMOS PSS
Note on D14: Nicholls, Gavin MR: Entity responsible to fulfil the action / deliverables
Note on E14: Nicholls, Gavin MR: To be completed by the Contractor Rep in consultation & agreement with PMCA / PM, PSS & EMP Rep
Note on F14: Nicholls, Gavin MR: To be completed by the PD / PMCA / PM
Note on G14: Nicholls, Gavin MR: To be completed by the PD / PMCA / PM
Note on A16: Gavin: Click on number to link to corresponding instructions

## DPC Instructions
DATA PROVISION CHECKLIST INSTRUCTIONS
|  | Data Provision Checklist Development | The Data Provision Checklist (DPC) - template and instructions, are to complement the contractor's Estate Information Provision Plan (EIPP). The DPC aims to provide contractor representatives with sufficient information to plan and document a schedule for the submission of project information and data throughout the project lifecycle and for the PD / PMCA / PM and EMOS to validate receipt and completion in accordance with the contract conditions and HOTO requirements. Estate data includes but is not limited to: GEMS data, design & as-constructed drawings and Operating & Maintenance Manuals (O&MM). When developing the EIPP and DPC, contractor representatives must liaise with the EMOS PSS to agree a schedule for data submission, checking and turn-around validation / processing times that enable related HOTO criteria to be achieved.
Design Phase
1 | Design | Data Extracts from GEMS provided to Designer (required for existing facilities, extending current infrastructure and/or upgrading existing assets) | Data extracts are to be taken to inform the design process and also identify what information will require updating as a result of the project. (Extracts should be used "for information only" purposes as GEMS data can be incomplete and/or inaccurate. Requests for these extracts are to be prepared using the Request Estate Data Form, to define the scale and extent of data to be included. The form can be obtained from the DEQMS Estate Information Page. If unsure of the extent of the current estate data, liaise with EMOS to ensure correct footprint is requested If after inspection of the GEMS data extracts it is found that data is missing or incorrect, and it inhibits the contractor representative from creating project related asset shell and data records via GDLs (e.g. where a functional parent is required but extracted data is missing or incorrect) the contractor representative is to create new shell and data records via GDL submission to address the problem. Where missing or incorrect data does not inhibit the project data creation requirements, PMCAs / PMs are to report the data anomalies to EMOS to initiate remedial action. Spaces Plan. Where a spaces plan is available for an existing facility, EMOS is to provide a copy for the project to reference and/or update as applicable. For a new facility the project is to create and provide a spaces plan for the facility. | Form Request Estate Data Form: http://www.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Default.asp Information \ Support GEMS IH01 (Estate Hierarchy) Report for Property
2 | Design | Designer to identify (new or existing) assets and provide the following data requirements: a. high level asset classes relevant to the project; b. estimate the number of assets to be delivered and provide their EC classification; c. requests for EBIs for building level and spaces and compliant with the SDMP; d. physical asset hierarchy relationship map; and e. functional asset grouping relationship map. | The Data Requirements supporting documents are intended to identify the hierarchy and proposed structure of the data at an early stage to ensure understanding of the Estate Register Information Model (ERIM), interdependent policies, environmental data considerations and the data capture requirements as it applies to the project being undertaken. a. Proposed EBI Floor Plan (including level and space) is a simplified conceptual floor plan for any newly constructed buildings. This plan is to be marked up by the designer with the proposed EBI marked on it IAW the space numbering conventions outlined within the SDMP. b. The physical hierarchy map is to be developed to give a graphical representation on how the project supplied estate data is to be structured to ensure appropriate classifications and physical parents have been identified and appropriately mapped. This is to take into consideration the ERIM hierarchy, how this applies to the project in terms of new assets, the floor plans and the quantity of new assets. This is to ensure that prior to requesting shell records, appropriate identifiers and parent IDs can be clarified and how many of each asset type are required. c. The functional asset grouping relationship map is similar to the physical hierarchy map in content and appearance but represents the functional parent relationship between networked systems. This applies to all infrastructure and equipment systems only. d. Correcting Existing Data. Where existing spaces data is missing or inaccurate, and the project is changing or refurbishing 50% or more of a facility; the project is to up-date and/or provide new spaces data for that facility. Where the project is changing or refurbishing less than 50% of the facility, the data deficiency should be reported to the local EMOS PSS. | Policy Spatial Data Management Plan Section 4, Spaces Plan Datasets http://www.defence.gov.au/estatemanagement/governance/Policy/SDMP/Default.asp Estate Register Information Model version 10.2.1 http://www.defence.gov.au/estatemanagement/lifecycle/EstateUpkeepInformation/DEPUQuicklinks.asp Information \ Support Example Hierarchy Diagrams http://www.defence.gov.au/estatemanagement/lifecycle/EstateUpkeepInformation/ERIMHeirachy.asp Physical Hierarchy and Functional Relationship Map support guide
3 | Design | EMOS PSS provides feedback on Data Requirements | PSS are to review and endorse data requirements against relevant policies and convention prior to asset shell creation. This is done to ensure data errors are not replicated into dependant processes or requests.
4 | Design | Project submits request for asset shell record GDLs for Buildings, Levels, Spaces, Infrastructure systems, Equipment systems and Equipment. | Asset shell records are the minimum data attributes required to create an initial record in the GEMS database that can be added to later and are created using the GDL. GDLs are to be completed to request asset shell creation for all new assets using the endorsed Data Requirements documentation (Estate Class Mapping Diagrams for all Estate Classes, EBI Numbering Plan for Levels and Spaces). This is done early in the project lifecycle to ensure all dependant activities are founded on accurate shell records to reduce latter complications. Completed GDL Asset Shell Requests are submitted to the EMOS for validating before they are sent to the GEMS Master Data Team (MDT) for processing. It may be beneficial for projects to request the shell records for building assets earlier in the design phase once it is known how many new buildings may be required to ease the integration of EBIs into drawing Title block information. Note: creating new Asset Shells relates to shell records for Building, Level, Space, Infrastructure, Equipment and Equipment Systems where these are known in the design phase. Please refer to DEQMS (Bottom link in cell E) for the updated guidance and workflow on projects preparing Estate and Equipment GDLs. | Form Estate GDL Tool Template, Overview Tab, Create Asset Shell button http://www.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Docs/TemplatesForms/EstateGDLTemplate.xlsm Support \ Information Estate Data Management Handbook, step 12.2 http://www.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Default.asp https://www.video.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Docs/EstateInformationManagementHandbook/GDLProcessInstructionsSuppInfo.pdf
5 | Design | All required GEMS Asset Shells have been identified by the 90% design and where confirmed, created in GEMS - Building, Level, Space, Infrastructure, Equipment, Equipment Systems etc. Some equipment shell records may not be created until the delivery phase. | Confirmation from Defence that all asset shells have been identified, created and generated within the GEMS and assigned EBIs returned to the project for integration into project documentation. Where equipment shell records have been identified but not created, a plan for creating the shell records during the delivery phase is to be developed and agreed.
6 | Design | Design Drawings Completed - End of design phase. | Throughout the project design phase there will be several meetings and various activities conducted to ensure the required stakeholders are engaged, project scope and deliverables (including approved changes) are understood & agreed; risks and constraints are identified; and plans, designs and drawings are developed to the required standards. It is the designer’s responsibility to ensure that all design plans and drawings are complete (includes approved project scope and user requirements) and compliant with the SDMP. Compliance includes incorporating allocated room and space numbers, provision of geo-referenced information and a format suitable for ultimately loading on the Defence Estate Information System (NSIMS) if/when required. Design Drawings are finalised and circulated for comment\endorsement. By this stage, it is expected that: - Title blocks of drawings are to accurately reflect issued EBIs for Building\Infrastructure. - Floor\Layout plans are to accurately reflect the issued space Identifiers and comply with the SDMP.
Construction Phase
| Pre-mobilisation | Changes to design, changes to existing shell records or new shells | If at this stage there have been any changes made to the design, check with the EMOS PSS or GEMS MDT if you have submitted the shell GDL to ensure all shell records are consistent with the design change. If they are no longer accurate, create new shells records in a new GDL and advise EMOS PSS & GEMS MDT of the changes/updates/deletions to be made.
7 | Pre-mobilisation | Data Extracts from GEMS provided to Contractor Representative (required for existing facilities, extending current infrastructure and/or upgrading existing) | Data extracts are to be taken to inform the ongoing development, update and submission of GDLs throughout the construction phase. Requests for extracts is via use of the Request Estate Data Form obtained from the DEQMS Estate Information Page. If unsure of the extent of the current estate data, liaise with EMOS to ensure correct footprint is requested. If the GEMS data extracts are missing data or the data provided is incorrect, after inspection, take measures to have these records corrected/updated/created. Contact the EMOS, who will be able to guide the data supplier in the right direction to have this missing data created or incorrect data updated. | https://www.video.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Default.asp
8 | Pre-mobilisation | Complete and agree the EIPP and DPC requirements and schedule for construction and DLP phases | Contractor Representatives are to meet with the EMOS PSS to determine and agree EIPP requirements and schedule for delivery and validation of data. EMOS PSS and Contractor Representatives are to: a. confirm that required shell records are created in GEMS and identify any additional shell records to be created; b. determine the applicable GDL breakdown & packaging and schedule for supply of GDLs; and c. determine the schedule for supply and validation of O&MM and As Constructed (ASCON) drawings ("drafts" and "final" documents), and Master Site Plan (MSP).
9 | Pre-mobilisation | Asset Labelling preparation | Asset Labelling is an important step in matching an asset on the ground to a record in GEMS. While physically attaching a label to the item is done during the construction phase, preparatory activities are required prior to construction to ensure the labelling standard is implemented correctly and do not create issues further in the construction process. In conjunction with the EMOS, the project is to: a. confirm what is required to be labelled as per the Defence Signage and Labelling Standard; b. the layout of the Signage\Label required; c. text\content of the label; and d. address any perceived placement issues. | Policy Signage and Labelling Standards http://www.defence.gov.au/estatemanagement/lifecycle/EstateUpkeep/PDEU12LabellingofEstateElements.asp
10 | Construction | Submission of GDLs throughout construction phase. GDL submissions broken into logical batches depending on nature of project. Add lines below to indicate schedule for additional GDL delivery times. | Large projects by nature are required to submit considerable amounts of data. The larger the project, the larger amount of information will be created. To avoid processing issues, reviewing and approving an entire project set of data can create unnecessary delays or other issues. Data submissions are to be broken down into logical batches where appropriate. For large and/or complex projects, incremental or a rolling provision of data could be expected from early in the construction phase to 90% construction or 28 day notice of completion. These GDLs would take into account any updates (either New Asset or Disposal\Demolition) that have occurred over the period. These data submissions should also include any submissions or updates to hazards or asbestos data and any necessary environmental data either via GDL or Environmental Factor Record Interactive PDF form. A GDL submission schedule is to be developed, agreed and circulated to representatives at the commencement of the Construction Phase and forms part of the EIPP. Where the provision and/or upload of GDLs is incomplete, the PD/PM, EMOS, the Zone EMP representative and contractor representative are to revise the EIPP and agree to a new data supply schedule as required. | Form Estate GDL Tool Template, Overview Tab, Assign\Commissioning and Disposal Buttons http://www.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Default.asp Equipment GDL Tool Template, Overview Tab, Modify, Assign, Disposal Buttons http://www.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Default.asp GEMS EFM Interactive Form or other GDL Template, as advised by Defence SME or EMOS Support \ Information Estate Data Management Handbook, step 13.4 .1 thru 13.5.3 http://www.defence.gov.au/estatemanagement/lifecycle/EstateDataInformation/Default.asp Defence Safety Manual Vol 3, Part 3A http://drnet.defence.gov.au/People/WHS/SafetyMan/Pages/SafetyMan.aspx
11 | Construction | Additional GDL submissions, as required & determined by project | Additional rows are added to the checklist to record the different batches and timing of GDL submissions to EMOS. For large projects there may be many batches that align to project construction phase, as different facilities and/or assets are completed etc.
| Construction | 28 Day notice of Completion (CFI project) or 90% construction for all other projects.
12 | Construction | Final submission to PSS of all GDLs - all data fields completed. | By this stage, all GDLs should have been completed including necessary asset attributes and submitted to the PSS for review, validation and upload.
13 | Construction | Submission of draft O&MMs for validation. | Draft O&MM are provided to the PD / PM to confirm requirements specified in the contract and agreed EIPP delivery schedule have been met. Once these requirements are confirmed and the submission checked, the PD / PM is to forward the draft O&MM to the EMOS PSS for validation of completeness and meeting Defence O&MM Instructions. O&MM are crucial in recording key facility information required for the ongoing sustainment of the Defence estate. All O&MM by this stage need to be prepared and submitted to review (either as draft digital media or notified draft completion for Online Document management system). O&MM are to be checked and quality assured by the Contractor Representative prior to submission to ensure all relevant content has been provided and completeness of all project relevant sections as required IAW the Defence O&MM Instructions. | Policy Operations and Maintenance Manual Policy & Instructions https://defence.gov.au/estatemanagement/lifecycle/PlanHandoverTakeover/OMM.asp
14 | Construction | Submission of draft ASCON drawings for validation. | Draft as-constructed drawings (ASCONs) are provided to the PD / PM to confirm requirements specified in the contract and agreed EIPP delivery schedule have been met. Once these requirements are confirmed and the submission meets Defence requirements, the PD / PM is to forward the draft ASCONs to the EMOS PSS for validation of completeness and SDMP requirements. All ASCONs by this stage need to be prepared and submitted to review taking into considerations of the SDMP. ASCONs are to meet the following requirements: a. Drawing Format: presented in AutoCAD DWG version specified in the SDMP. b. Drawing Structure: all drawing content to be in model space, title blocks only on paper space). External references are bound to parent drawing. c. Metadata: provided with (or provision allowed for) compliant metadata taking into consideration freeform text guidance IAW NSIMS SOP6. d. Revision: have been revised to final as-constructed status, remove unnecessary construction notations and labelled the title block accordingly. | Policy Spatial Data Management Plan http://www.defence.gov.au/estatemanagement/governance/Policy/SDMP/Default.asp Support \ Information NSIMS Standard Operating Procedure 6 Freeform Metadata Standards Objective DocID: xxxxx
15 | Construction | Spaces Plan prepared and submitted IAW SDMP | Spaces Plans differ from ASCON architectural plans and are a requirement under the SDMP. The space plans are used to create the GEMS-Geo geometries and underpin many other key datasets i.e. Fire Evacuation Plans. Space plans have defined accuracy, content and presentation requirements. An updated plan (for refurbishment projects) or provision of new plan, complying with the SDMP space plan specifications, is submitted for each building level. | Policy Spatial Data Management Plan Section 6 - Engineering Detail Survey Appendix H: Space Plan Standards http://www.defence.gov.au/estatemanagement/governance/Policy/SDMP/Default.asp
16 | Construction | RFI Notice to request Master Site Plan (MSP) (or applicable portion) for Update purposes issued to EMOS PSS. | Master Site Plans (MSP) are controlled access documents and can only be issued to one party at a time for update and will only be issued for a minimum length of time to conduct the update. Projects are required to update this plan IAW the SDMP. Projects are to: a. familiarise themselves with the content\accuracy and submission requirements of the SDMP; b. submit a request to obtain a MSP (or applicable portion) once all major external works are completed; and c. collect by means of survey to satisfy accuracy provisions, all changes to the estate from the building line out. Updates to the MSP generally can occur once all major construction and landscaping works external to the building line are complete. Timing of the request is important so monitoring of project progress will assist in determining when this criteria is met and it may allow additional flexibility in the provision timeline in event the document is unavailable. | Policy Spatial Data Management Plan Section 3: Master Site Plan Datasets Section 6: Engineering Detail Survey Appendix G: Master Site Plan Dataset Standards http://www.defence.gov.au/estatemanagement/governance/Policy/SDMP/Default.asp Support \ Information Contact relevant NSIMS Data Custodian
17 | Construction | MSP sent to EMOS for validating and uploading to NSIMS | It is the Contractor Representative’s responsibility to ensure the MSP is amended and finalised to reflect all changes delivered via the project works. The MSP is to be provided to the EMOS for validation of accuracy and completeness before uploading to NSIMS and subsequent Defence custodian approval.
18 | Construction | EMOS PSS feedback on draft O&MM | EMOS PSS is to conduct its primary validation of completeness and meeting O&MM Instructions, and provide feedback on the required corrective actions for the Contractor Representative to address in the final issue O&MMs.
19 | Construction | EMOS PSS feedback on draft ASCON drawings | EMOS PSS is to conduct its primary validation of completeness and meeting SDMP requirements, and provide feedback on the required corrective actions for the Contractor Representative to address in the final issue ASCONs.
Hand Over Take Over (HOTO)
21 | HOTO | Submission of GDLs for outstanding items identified in HOTO | It is expected that by 28 Day Notice of Completion or 90% construction (depending on project type), all estate GEMS data would have been provided to EMOS for validation and by HOTO, EMOS has submitted valid GDLs to the MDT for loading into GEMS. However, there will be circumstances where assets and/or defects will be identified during HOTO that requires additional work or rectification. In these circumstances, the provision of remaining and/or corrected information to an agreed plan must occur. The contractor representative and PD / PM are to ensure and confirm to EMOS that all remaining and/or corrected estate data has been identified and will be provided to EMOS IAW with the agreed EIPP and provisions are in place to manage any further changes resulting during the Defects Liability Period (DLP).
22 | HOTO | Specified/Identified GDLs accurately completed and provided to the GDT for uploading to GEMS. | EMOS is to confirm that all GEMS data (excluding new items discovered / rectified during HOTO) have been received, validated and GDLs submitted to the MDT for uploading to GEMS. For any outstanding GDLs or Environmental Factor Record data submissions, EMOS is to confirm that an acceptable provisions and arrangements are in place and documented in the agreed EIPP.
23 | HOTO | Warranty information provided on GDL Warranty section of GEMS (copy of certificates placed in O&MM) | The normal DLP is 12 months, however, it is also mandated that the contractor representative provide details of warranties on works, material and labour. In addition, the contractor representative must provide all manufacturer and supplier warranties associated with the procurement of equipment and goods. It is the contractor representative and PD/PM responsibility to ensure these warranties are recorded in GEMS and the O&MM.
24 | HOTO | All final ASCON drawings are delivered in accordance with the contract requirements and agreed changes are implemented. | PD / PM are to confirm completion of final ASCON drawings IAW the contract requirements and that changes identified and agreed from review of the "draft" drawings have been fully implemented. Once these requirements are confirmed and the submission not rejected, the PD / PM is to forward the final ASCONs to the EMOS PSS for final validation of agreed changes and uploading to NSIMS. Any submissions not meeting the required standards are to be returned to the Contractor Representative for corrective action.
25 | HOTO | All final O&MM are delivered in accordance with the contract requirements and agreed changes are implemented. | PD / PM are to confirm completion of final O&MM IAW the contract requirements and that changes identified and agreed from review of the "draft" O&MM have been fully implemented. Once these requirements are confirmed and the submission not rejected, the PD / PM is to forward the final O&MM to the EMOS PSS for validation of agreed changes and uploading to NSIMS. Any submissions not meeting the required standards are to be returned to the Contractor Representative for corrective action. | https://defence.gov.au/estatemanagement/lifecycle/PlanHandoverTakeover/OMM.asp
26 | HOTO | EMOS PSS have reviewed and accepted Key Datasets (MSP and Spaces Plan) | EMOS PSS are to undertake conformance checks of all returned MSP and Spaces Plans before returned to NSIMS for Custodian approval. Any submissions not meeting the standards are to be returned to the project for corrective action.
27 | HOTO | EMOS PSS confirm all As-constructed drawings and O&MM received and agreed changes are complete. | EMOS PSS are to review and validate that O&M Manuals and ASCONs have agreed changes implemented and non-rejected documents have been received for uploading to NSIMS. Any submissions not meeting the required standards are to be returned to the Contractor Representative for corrective action IAW contract T&Cs..
Defect Liability Period (DLP)
28 | DLP | GDLs submitted as a result of defect rectifications | Any GDLs that have been returned due to error are to be addressed and resubmitted. Any replacement assets or defects rectified during DLP are to be updated and the required GDL submitted IAW with the process detailed in the agreed EIPP.
29 | DLP | O&MM and ASCONs updated as a result of defect rectifications | Any outstanding documents\drawings that were unavailable for submission at HOTO or have been otherwise updated as a result of a rectification are to be submitted to EMOS PSS for validation.
30 | DLP | EMOS PSS confirm all defect rectification updates received and is uploaded to NSIMS / Objective or sent to the MDT for uploading to GEMS. | EMOS PSS have confirmed that all updated estate GEMS data has been validated and sent to the GEMS MDT for uploading to GEMS and updated drawings & manuals validated and saved on NSIMS.