PROJECT NUMBER: [INSERT PROJECT NUMBER]

PROJECT NAME: [INSERT PROJECT NAME and Description of Works and Services, as applicable]

DESIGN SERVICES SUBCONTRACT

(FOR USE WITH DEFENCE DESIGN SERVICES CONTRACT)

[LAST AMENDED: 22 JANUARY 2026 - PLEASE REMOVE PRIOR TO publication OF TENDER DOCUMENTS

IMPORTANT NOTE: THIS TEMPLATE HAS BEEN PREPARED BY THE COMMONWEALTH AS A STARTING POINT FOR USE AS A SUBCONTRACT UNDER THE DEFENCE DESIGN SERVICES CONTRACT. THE COMMONWEALTH ACCEPTS NO RESPONSIBILITY FOR ANY USE OF, OR RELIANCE UPON, THIS TEMPLATE. ANY person PROPOSING TO USE this template MUST UNDERTAKE THEIR OWN DUE DILIGENCE AND REVIEW TO ENSURE APPROPRIATE ALIGNMENT WITH THE DEFENCE DESIGN SERVICES CONTRACT, THAT it IS OTHERWISE APPROPRIATE FOR USE IN THE CONTEXT OF THE SPECIFIC PROJECT and services FOR WHICH IT IS BEING USED and that any necessary amendments are made to address these matters]

Table of Contents

FORMAL AGREEMENT	5

CONDITIONS OF SUBCONTRACT	7

1.	Glossary of terms, interpretation AND MISCELLANEOUS	7

1.1	Glossary of Terms	7

1.2	Interpretation	33

1.3	Miscellaneous	35

2.	ROLE OF THE SUBCONSULTANT	37

2.1	Engagement	37

2.2	Standard of Care	37

2.3	Authority to Act	37

2.4	Knowledge of the Consultant's Requirements	37

2.5	Notice of Matters Impacting on the Subcontract Services or the Works	37

2.6	Co-operation with Other Contractors	38

2.7	Access to Subconsultant's Premises	38

2.8	Conflict of Interest	38

2.9	Subcontracting	38

2.10	Statutory Requirements	38

2.11	Change in Statutory Requirements or Variance with Subcontract	39

2.12	Subconsultant Deed of Covenant and Novation	39

2.13	The Environment	39

2.14	Pandemic Adjustment Event	40

2.15	Method of Work Plan for Airfield Activities and Operating Airfield	41

3.	Role of the CONSULTANT	42

3.1	Information and Subcontract Services	42

3.2	Additional Information	42

3.3	Access to the Site	42

4.	Personnel	43

4.1	Consultant's Representative	43

4.2	Replacement of Consultant's Representative	43

4.3	Parties' Conduct	43

4.4	Key People for the Subcontract Services	43

4.5	Removal of Persons	43

4.6	Monthly Meeting	43

4.7	Subconsultant’s Monthly Report	44

5.	Insurance	47

5.1	Subconsultant Insurance Obligations	47

5.2	Consultant Insurance Obligations	49

5.3	Failure to Insure	49

5.4	Period of Insurance	49

5.5	Notice of Potential Claim	50

5.6	Cross Liability	50

5.7	Insurances Secondary	50

5.8	Exclusion of Consequential Loss and Limitation on Liability	51

6.	DESIGN AND Documentation	52

6.1	Subconsultant's Documentation Program	52

6.2	Subconsultant's Design	52

6.3	Consultant's Representative May Review Design Documentation	52

6.4	No Obligation to Review	52

6.5	Copies of Design Documentation	52

6.6	Licence over Project Documents	53

6.7	Intellectual Property Warranties	53

6.8	Intellectual Property Rights	53

6.9	Consultant Material	54

6.10	Resolution of Ambiguities	54

6.11	Access to Premises and Project Documents	54

6.12	Measurements and Dimensions	55

6.13	Design Certification	55

6.14	Samples	55

6.15	Work Health and Safety	56

7.	Quality	60

7.1	Quality Assurance	60

7.2	Non-Complying Subcontract Services	60

7.3	Reperformance of the Non-complying Subcontract Services	60

7.4	Project Plans	61

7.5	Drawings	62

8.	Time	63

8.1	Progress	63

8.2	Programming	63

8.3	Subconsultant Not Relieved	63

8.4	Suspension	64

8.5	Delays Entitling Claim in Extension of Time	64

8.6	Claim for Extension of Time	64

8.7	Conditions Precedent to Extension	65

8.8	Extension of Time	65

8.9	Unilateral Extension of Time	65

8.10	Acceleration	65

8.11	Prolongation	66

9.	PLANNING PHASE AND DELIVERY PHASE	68

9.1	Planning Phase and Delivery Phase	68

9.2	Updated Delivery Phase Fee Proposal	68

9.3	Approval (or otherwise) of Updated Delivery Phase Fee Proposal	70

9.4	Notice to Proceed (or not Proceed) with Delivery Phase Subcontract Services	71

10.	VariationS	73

10.1	Variation Price Request	73

10.2	Variation Order	73

10.3	Valuation of Variation	73

10.4	Table of Variation Rates and Prices	73

10.5	Omissions	73

11.	Payment	74

11.1	Payment Obligation	74

11.2	Payment Claims	74

11.3	Certification to Accompany Submission of Payment Claim	74

11.4	Payment Statement	75

11.5	Payment	75

11.6	Payment on Account	76

11.7	Completion Payment Claim and Notice	76

11.8	Release after Completion Payment Claim and Notice	76

11.9	Interest	76

11.10	Correction of Payment Statements	77

11.11	Right of Set-Off	77

11.12	Payment of Workers	77

11.13	GST	77

11.14	Security of Payment Legislation	78

11.15	Accounting Records	79

11.16	Cost Allocation Advice	79

11.17	Facilities and Infrastructure Accounting	79

11.18	Fee Payment Schedule	79

12.	Termination	80

12.1	Preservation of Rights	80

12.2	Subconsultant Default	80

12.3	Contents of Notice of Default	80

12.4	Termination for Insolvency or Breach	80

12.5	Consultant's Entitlements after Termination by Consultant	80

12.6	Subconsultant's Entitlements after Termination by Subconsultant	81

12.7	Termination for Convenience	81

12.8	Subconsultant’s Entitlements after Termination for Convenience by Consultant	81

12.9	Termination of Design Services Contract	82

12.10	Consequences Following Design Services Contract Termination	82

13.	DisputeS	83

13.1	Notice of Dispute	83

13.2	Expert Determination	83

13.3	The Expert	83

13.4	Not Arbitration	83

13.5	Procedure for Determination	83

13.6	Disclosure of Interest	84

13.7	Costs	84

13.8	Conclusion of Expert Determination	84

13.9	Expert Determination Agreement	84

13.10	Determination of Expert	84

13.11	Executive Negotiation	85

13.12	Arbitration Agreement	85

13.13	Arbitration	85

13.14	DSC Dispute Procedures	86

13.15	DSC Disputes	86

13.16	Procedure for DSC Disputes	87

13.17	Further Procedures	87

13.18	Proportionate Liability	88

13.19	Continuation of Subcontract Services	88

14.	Notices	89

14.1	Notice of Variation	89

14.2	Notices of Other Claims	89

14.3	Prescribed Notices	89

14.4	Continuing Events	90

14.5	Time Bar	90

14.6	Other Provisions Unaffected	90

14.7	Address for Service	90

14.8	Receipt of Notices	90

15.	Whole of Life	92

15.1	General	92

15.2	Consultation	92

15.3	WOL Proposals	92

15.4	HOTO Process	92

15.5	Post Occupancy Evaluation	93

15.6	Rights and Obligations Not Affected	93

16.	General	95

16.1	Workplace Gender Equality	95

16.2	Indigenous Procurement Policy	95

16.3	Defence's Security Alert System	95

16.4	IT Equipment	96

16.5	Privacy	96

16.6	Moral Rights	97

16.7	Freedom of Information	98

16.8	Long Service Leave	98

16.9	Assignment	98

16.10	Publicity	98

16.11	Building Works Manual and National Construction Code Certification	99

16.12	Applicable Standards	99

16.13	Shadow Economy Procurement Connected Policy	99

16.14	Commonwealth Publication and Reporting Requirements	100

16.15	Modern Slavery	101

16.16	Compliance with the Commonwealth Supplier Code of Conduct	101

17.	COMMERCIAL-IN-CONFIDENCE INFORMATION	103

18.	INFORMATION SECURITY	104

18.1	DISP Membership	104

18.2	Confidential Information and Information Security	104

18.3	Security or Confidentiality Incidents	105

18.4	Return and Retention of Confidential Information	105

18.5	Release and Indemnity	106

19.	STRATEGIC NOTICE EVENT	107

19.1	Subconsultant's Warranty on Award Date	107

19.2	Subconsultant to Give Notice	107

19.3	Consultant Rights Upon Occurrence of Strategic Notice Event	107

19.4	Strategic Notice Event Remediation Plan	108

19.5	Additional Obligations in respect of Known or Suspected Fraud or Corruption	108

19.6	Release	109

19.7	Subconsultant's Compliance	109

20.	FINANCIAL VIABILITY	110

21.	ESTATE INFORMATION	111

21.1	Subconsultant Estate Information Obligations	111

21.2	No Obligation to Review	111

SUBCONTRACT PARTICULARS	112

Attachment 1 to the SUBContract Particulars - Delivery Phase Fee Proposal	122

Annexure 1 - Brief	123

Annexure 2 - SPECIAL CONDITIONS	124

Annexure 3 - FEE PAYMENT SCHEDULE	133

Annexure 4 - TABLE OF VARIATION RATES AND PRICES	135

- FORMAL AGREEMENT

The Subcontract is made on                   day of

Parties	The consultant specified in the Subcontract Particulars (Consultant)

The subconsultant specified in the Subcontract Particulars (Subconsultant)

A.	The Commonwealth of Australia (Commonwealth) and the Consultant entered into the Design Services Contract for the design of the Works.

B.	The Consultant wishes to subcontract certain obligations under the Design Services Contract to the Subconsultant under the Subcontract.

C.	The Consultant and the Subconsultant promise to carry out and complete their respective obligations in accordance with the:

(a)	attached Conditions of Subcontract; and

(b)	other documents referred to in the definition of "Subcontract" in clause 1.1 of the Conditions of Subcontract.

This Formal Agreement may be executed in any number of counterparts and all such counterparts taken together will be deemed to constitute one and the same instrument.

SIGNED as an agreement

[S 127 OF CORPORATIONS ACT]

| Executed by the Consultant in accordance with section 127 of the Corporations Act 2001 (Cth): |  |  |  |
| --- | --- | --- | --- |
| Signature of director |  |  | Signature of company secretary/director [delete position as appropriate] |
| Full name of director who states that they are a director of the Consultant |  |  | Full name of company secretary/director [delete position as appropriate] who states that they are a company secretary/director [delete position as appropriate] of the Consultant |

[OR - AUTHORISED SIGNATORY OF COMPANY]

| Signed for and on behalf of the Consultant by its authorised signatory in the presence of: |  |  |  |
| --- | --- | --- | --- |
| Signature of witness |  |  | Signature of authorised signatory |
| Full name of witness |  |  | Full name of authorised signatory |

[THESE ARE EXAMPLE EXECUTION CLAUSES ONLY. INSERT APPROPRIATE EXECUTION CLAUSE FOR CONSULTANT]

[S 127 OF CORPORATIONS ACT]

| Executed by the Subconsultant in accordance with section 127 of the Corporations Act 2001 (Cth): |  |  |  |
| --- | --- | --- | --- |
| Signature of director |  |  | Signature of company secretary/director [delete position as appropriate] |
| Full name of director who states that they are a director of the Subconsultant |  |  | Full name of company secretary/director [delete position as appropriate] who states that they are a company secretary/director [delete position as appropriate] of the Subconsultant |

[OR - AUTHORISED SIGNATORY OF COMPANY]

| Signed for and on behalf of the Subconsultant by its authorised signatory in the presence of: |  |  |  |
| --- | --- | --- | --- |
| Signature of witness |  |  | Signature of authorised signatory |
| Full name of witness |  |  | Full name of authorised signatory |

[THESE ARE EXAMPLE EXECUTION CLAUSES ONLY. INSERT APPROPRIATE EXECUTION CLAUSE FOR SUBCONSULTANT]

- CONDITIONS OF SUBCONTRACT

Glossary of terms, interpretation AND MISCELLANEOUS

Glossary of Terms

Unless the context otherwise indicates, whenever used in the Subcontract, each word or phrase in the headings in clause 1.1 has the meaning given to it under the relevant heading.

Accredited Building Surveyor

A person who meets all requirements of a "building surveyor" in accordance with and as defined in the Building Works Manual.

ACM

Has the meaning given in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth).

Act of Prevention

Any one of:

a breach of the Subcontract by the Consultant;

any other act or omission of the Commonwealth, the Consultant, the DSC Contract Administrator, the Consultant's Representative or an Other Contractor engaged by the Commonwealth or the Consultant; or

a Variation the subject of a direction by the Consultant's Representative,

but excluding any act or omission of any person specified in paragraph (b) in accordance with or otherwise permitted by the Subcontract.

Approval

Any licence, permit, consent, approval, determination, certificate, notice or other requirement of any Commonwealth, State, Territory or local authority, body or other organisation having any jurisdiction in connection with the Site, the Subcontract Services or the Works or under any applicable Statutory Requirement, which must be obtained or satisfied to:

carry out the Subcontract Services or the Works; or

occupy, use, maintain or operate the completed Works, to the extent that the Subcontract Services are relevant to such obtaining or satisfaction.

Asbestos

Has the meaning given in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth).

Asbestos Management Plan

The Security and Estate Group Asbestos Management Plan (including Annex A – Asbestos in Soils and Surface Contamination) dated 1 September 2025, available at https://www.defence.gov.au/business-industry/industry-governance/industry-regulations/security-and-estate-asbestos-management-plan, as amended or replaced from time to time.

Australian Privacy Principle

Has the meaning given in the Privacy Act.

Award Date

The date on which the Formal Agreement, to which these Conditions of Subcontract are attached, has been completed and signed by the Consultant and the Subconsultant.

Brief

The brief in Annexure 1.

Building Works Manual

The Building Works Manual - Edition 1 dated 24 August 2020 available on the Defence Website, as amended or replaced from time to time.

Change of Control

In relation to the Subconsultant, where a person who did not (directly or indirectly) effectively Control the Subconsultant at the Award Date, either alone or together with others, acquires Control of the Subconsultant.

Claim

Includes any claim for an increase in the Fee, for payment of money (including damages) or for an extension of time:

under, arising out of or in connection with the Subcontract, including any direction of the Consultant's Representative;

arising out of or in connection with the Subcontract Services, the Works or either party’s conduct before the Subcontract; or

otherwise at law or in equity including:

by statute;

in tort for negligence or otherwise, including negligent misrepresentation; or

for restitution.

Commonwealth

Commonwealth of Australia.

Commonwealth Procurement Rules

The Commonwealth Procurement Rules issued under section 105B(1) of the Public Governance, Performance and Accountability Act 2013 (Cth).

Completion

The point in time when, in respect of a Milestone:

the Design Documentation has been completed in accordance with the Subcontract;

the Subcontract Services have been completed in accordance with the Subcontract;

the Subconsultant has satisfied all Subconsultant HOTO Obligations and other obligations (including applicable Subconsultant Estate Information Obligations) (if any) which must be satisfied in respect of that Milestone in accordance with the HOTO Requirements;

all documents and other information (if any) required in respect of that Milestone have been submitted to the Consultant’s Representative in accordance with the Subcontract; and

without limiting the foregoing, the Subconsultant has done everything which the Subcontract requires it to do as a condition precedent to Completion, including those things specified in the Subcontract Particulars.

Confidential Information

  - Means, subject to paragraph (b):

the Subcontract;

the Project Documents;

any document, drawing, information or communication (whether in written, oral or electronic form) given to the Subconsultant by the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative or anyone on the Commonwealth’s or the Consultant’s behalf, whether or not owned by the Commonwealth or the Consultant, which is in any way connected with the Subcontract Services or the Works, which:

by its nature is confidential; or

the Subconsultant knows or ought to know is confidential; and

everything recording, containing, setting out or making reference to the document, drawing, information or communication (whether in written, oral or electronic form) described in subparagraph (iii) including documents, notes, records, memoranda, materials, software, disks and all other media, articles or things.

Excludes any document, drawing, information or communication (whether in written, oral or electronic form) given to the Subconsultant by the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative or anyone on the Commonwealth’s or the Consultant’s behalf, whether or not owned by the Commonwealth or the Consultant, which:

is in the possession of the Subconsultant without restriction in relation to its disclosure or use before the date of its receipt from the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative or anyone on the Commonwealth’s or the Consultant’s behalf;

is in the public domain otherwise than due to a breach of clause 18; or

has been independently developed or acquired by the Subconsultant.

Consolidated Group

A Consolidated Group or MEC (Multiple Entry Consolidated) group as those terms are defined in section 995-1 of the Income Tax Assessment Act 1997 (Cth).

Construction Contract

A building or construction contract which the Commonwealth has entered into or will enter into with a contractor to construct or design and construct any part of the Works.

Consultant

The person specified in the Subcontract Particulars.

Consultant Material

All material provided to the Subconsultant by the Consultant, including documents provided in accordance with clause 6 and any other documents, equipment, machinery and data (stored by any means).

Consultant's Design Management Plan

The design management plan specified in the Subcontract Particulars, as updated in accordance with the Design Services Contract.

Consultant's Environmental Management and Sustainability Plan

The environmental management and sustainability plan specified in the Subcontract Particulars, as updated in accordance with the Design Services Contract.

Consultant's Program

The program prepared by the Consultant for the Subcontract Services and the Works, as updated in accordance with the Design Services Contract.

Consultant's Project Lifecycle and HOTO Plan

The commissioning, handover and takeover plan specified in the Subcontract Particulars, as updated in accordance with the Design Services Contract.

Consultant's Project Plans

The:

Consultant's Design Management Plan;

Consultant's Project Lifecycle and HOTO Plan;

Consultant's Environmental Management and Sustainability Plan;

Consultant's Quality Plan;

Consultant's Site Management Plan;

Consultant's Work Health and Safety Plan; and

additional plans specified in the Subcontract Particulars.

Consultant's Quality Plan

The quality plan specified in the Subcontract Particulars, as updated in accordance with the Design Services Contract.

Consultant's Representative

The person specified in the Subcontract Particulars or any other person nominated by the Consultant from time to time under clause 4.2 to replace that person.

Consultant's Site Management Plan

The site management plan specified in the Subcontract Particulars, as updated in accordance with the Design Services Contract.

Consultant's Work Health and Safety Plan

The work health and safety plan specified in the Subcontract Particulars, as updated in accordance with the Design Services Contract.

Contamination

The presence in, on or under land, air or water of a substance (whether a solid, liquid, gas, odour, heat, sound, vibration or radiation) at a concentration above the concentration at which the substance is normally present in, on or under land, air or water in the same locality, that presents a risk of Environmental Harm, including harm to human health or any other aspect of the Environment, or could otherwise give rise to a risk of non-compliance with any Statutory Requirement for the protection of the Environment.

Contractor

Any contractor engaged or to be engaged by the Commonwealth to construct or design and construct the Works including any subcontractor of such contractor.

Control

Includes:

the ability to exercise or control the exercise of the right to vote in respect of more than 50% of the voting shares or other form of voting equity in a corporation;

the ability to dispose or exercise control over the disposal of more than 50% of the shares or other form of equity in a corporation;

the ability to appoint or remove all or a majority of the directors of a corporation;

the ability to exercise or control the exercise of the casting of a majority of the votes cast at the meetings of the board of directors of a corporation; and

any other means, direct or indirect, of dominating the decision making and financial and operating policies of a corporation.

Corruption

- Any conduct (whether criminal or non-criminal in nature) that does or could compromise the integrity, accountability or probity of public administration, including:

any conduct of any person (whether or not a staff member of a Commonwealth agency) that adversely affects, or that could adversely affect, either directly or indirectly:

the honest or impartial exercise of any staff member's powers as a staff member of a Commonwealth agency; or

the honest or impartial performance of any public official's functions or duties as a public official;

any conduct of a staff member of a Commonwealth agency that constitutes or involves a breach of public trust;

any conduct of a staff member of a Commonwealth agency that constitutes, involves or is engaged in for the purpose of abuse of the person's office; and

any conduct of a staff member of a Commonwealth agency, or former staff member of a Commonwealth agency, that constitutes or involves the misuse of information or documents acquired in the person's capacity as a staff member of a Commonwealth agency.

Data Provision Checklist

The worksheets contained within the excel workbook titled "Data Provision Checklist" available at https://www.defence.gov.au/business-industry/industry-governance/industry-regulations/estate-project-handover-takeover-policy, as amended or replaced from time to time.

Data Supplier

Any person identified as a "Data Supplier" or "Estate Data Supplier" in the Defence Estate Information Management Requirements, including a contract administrator, designer, contractor, subcontractor or any person engaged by the Consultant to design, construct or otherwise provide services in relation to the Subcontract Services, the Works or a Stage (as defined in the Construction Contract).

Date for Completion

The date or period of time (if any) specified in the Subcontract Particulars for Completion of a Milestone, as adjusted under the Subcontract.

Date for Delivery Phase Agreement

The date (if any) specified in the Subcontract Particulars, as may be adjusted under clause 9.

Defence

Department of Defence.

Defence Asbestos Register

The document or documents specified in the Subcontract Particulars, as amended or replaced from time to time.

Defence Environmental Management System

The environmental management system applicable to the Site (if any).

Defence Environmental Plan

The environmental plan applicable to the Site (if any).

Defence Environmental Requirements

The Defence Environmental Management System and Defence Environmental Plan applicable to the Site, the Subcontract Services or the Works, including any procedures, instructions, requirements and standing orders which have been developed or issued under the Defence Environmental Management System or Defence Environmental Plan.

Defence Estate

The properties owned, leased or otherwise occupied by the Commonwealth from time to time.

Defence Estate Information Management Requirements

The requirements published on the Defence Website in respect of the assessment, creation, recording, updating and management of Estate Information (and whether referred to as "Estate Information", "Estate Data", "GEMS" or otherwise), including:

the documents set out at https://www.defence.gov.au/business-industry/industry-governance/industry-regulations/estate-project-handover-takeover-policy;

any requirements contained in:

GEMS; and

the Spatial Data Management Plan; and

any other requirement published on the Defence Website relating to the assessment, creation, recording, updating and management of Estate Information,

each as amended or replaced from time to time.

Defence Requirements

Includes all policies, plans, manuals, guidelines, instructions (including departmental procurement policy instructions) and other Commonwealth or Defence requirements which are, or may become, applicable to the Site, the Subcontract Services or the Works.

Defence Strategic Interest Issue

Any issue arising out of or in relation to the Subcontract, the Subcontract Services or the Subconsultant (or any Related Body Corporate of the Subconsultant) that involves an actual, potential or perceived risk of an adverse effect on the national security interests of the Commonwealth, including arising from any breach by the Subconsultant of its obligations in respect of compliance with all Statutory Requirements.

Defence Website

The website available at www.defence.gov.au/ or such alternative location as notified by the Consultant's Representative.

Delivery Phase

The period (if any) commencing on the date specified in the notice issued under clause 9.4(a) (or, if no date is specified, the date of such notice) until the earlier of the:

  - date the Delivery Phase Subcontract Services have been completed in accordance with the Subcontract; and

date of termination of the Subcontract.

- Delivery Phase Agreement Minutes

- Has the meaning in clause 9.3(a)(i).

Delivery Phase Fee

The Indicative Delivery Phase Fee adjusted under clause 9.2(b)(i) (if at all) and set out in the Delivery Phase Agreement Minutes issued under clause 9.3(a)(ii), as adjusted in accordance with the Subcontract.

Delivery Phase Fee Proposal

The Delivery Phase Fee Proposal (if any) specified in the Subcontract Particulars.

Delivery Phase Subcontract Services

The services described in, or reasonably to be inferred from, the Subcontract as Delivery Phase Subcontract Services, including those Subcontract Services described in the Brief.

Design Documentation

All design documentation required to be brought into existence by the Subconsultant as part of, or for the purpose of, carrying out the Subcontract Services, including documents, drawings, specifications, reports, models, samples and calculations, equipment, technical information, plans, charts, tables, schedules, data (stored by any means), photographs and finishes boards, in computer readable and written form.

Design Management Plan

- The plan prepared by the Subconsultant and finalised under clause 7.4, which must set out in adequate detail the procedures and processes the Subconsultant will undertake in order to plan and manage the design of the Works. The Design Management Plan must not be inconsistent with the Consultant’s Design Management Plan and must address, at a minimum, the matters set out in the Brief.

Design Services Contract

The design services contract between the Commonwealth and the Consultant specified in the Subcontract Particulars for the design of the Works.

direction

Any agreement, approval, authorisation, certificate, consent, decision, demand, determination, direction, explanation, failure to consent, instruction, notice, notification, order, permission, rejection, request or requirement.

DISP

The Defence Industry Security Program more particularly described at http://www.defence.gov.au/dsvs/industry.

DSC Contract Administrator

Means:

the person specified in the Subcontract Particulars or any other person nominated by the Commonwealth from time to time under the Design Services Contract to administer the Design Services Contract; and

any representative of that person appointed under the Design Services Contract,

- as notified by the Consultant's Representative to the Subconsultant.

DSC Dispute Procedures

The dispute resolution procedures under the Design Services Contract referred to in clause 13.14(a).

DSPF

The Defence Security Principles Framework dated 19 July 2024 available at https://www.defence.gov.au/business-industry/industry-governance/defence-security-principles-framework, as amended or replaced from time to time.

Employers' Liability Insurance

A policy of insurance covering the liability of the Subconsultant to its employees at common law, for death or injuries arising out of or in connection with their employment, whether as an extension to Workers Compensation Insurance or otherwise.

Environment

Includes:

ecosystems and their constituent parts, including people and communities;

natural and physical resources;

the qualities and characteristics of locations, places and areas; and

the social, economic, aesthetic and cultural aspects of a thing mentioned in paragraphs (a), (b) or (c).

Environmental Clearance Certificate

The Environmental Clearance Certificate issued by the Commonwealth relating to the Subcontract Services or the Works and any conditions incorporated in that certificate.

Environmental Harm

Any actual or threatened adverse impact on, or damage to, the Environment.

Environmental Incident

Any Environmental Harm or Contamination arising out of or in connection with the Subcontract Services or the Works.

Environmental Management and Sustainability Plan

The plan prepared by the Subconsultant and finalised under clause 7.4, which must set out in adequate detail the procedures the Subconsultant will implement to manage the Subcontract Services from an environmental perspective to:

ensure compliance with the Environmental Requirements and Statutory Requirements; and

maximise the achievement of the Environmental Objectives.

- The Environmental Management and Sustainability Plan must not be inconsistent with the Consultant’s Environmental Management and Sustainability Plan and must address, at a minimum:

all Environmental Requirements;

without limiting paragraph (c), all Statutory Requirements;

all Environmental Objectives;

the roles and responsibilities of all Subconsultant personnel (including the Subconsultant’s key people under clause 4.4(a)(i)) regarding the Environment;

the procedure for consultation, co-operation and co-ordination of activities with the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative and Other Contractors regarding the Environment during the Subcontract Services and the Works;

the training and awareness programmes provided to Subconsultant personnel regarding the Environment;

the procedure for preparing (including tailoring) and finalising the Environmental Management and Sustainability Plan under clause 7.4;

the procedure for regularly identifying, controlling and monitoring possible and actual impacts on the Environment associated with the Subcontract Services and the Works, including the procedures for recording, reporting, responding to and finalising:

matters arising out of or in connection with such identification, control and monitoring; and

complaints, incidents (including Environmental Incidents), near misses and other situations or accidents regarding the Environment during the Subcontract Services and the Works;

the procedure for regularly reviewing, updating and amending the Environmental Management and Sustainability Plan under clause 7.4 (including as a result of any complaint, incident (including Environmental Incidents), near misses and other situations or accidents on Commonwealth property or the Site during the Subcontract Services and the Works);

the procedure for regular auditing or other monitoring of Subconsultant compliance with the Environmental Management and Sustainability Plan, including the procedures for recording, reporting, responding to and finalising:

matters arising out of or in connection with such audits or other monitoring; and

complaints, incidents (including Environmental Incidents), near misses and other situations or accidents regarding the Environment during the Subcontract Services;

all matters in the Smart Infrastructure Handbook and the Sustainable Procurement Guide;

the additional matters specified in the Subcontract Particulars; and

any other matters required by the:

Subcontract; or

Consultant’s Representative.

Environmental Objectives

The following objectives:

to encourage best practice environmental management through the planning, development, implementation and continuous improvement of environmental management procedures during the Subcontract Services;

to prevent and minimise adverse impacts on the Environment;

to recognise and protect any special environmental characteristics of the Site (including cultural heritage significance); and

the additional objectives specified in the Subcontract Particulars.

Environmental Requirements

Includes the:

Environmental Clearance Certificate;

Defence Environmental Requirements; and

additional requirements specified in the Subcontract Particulars.

Estate Information

Information and data created in connection with and relating to the design and construction of the Works or a Stage (as defined in the Construction Contract) or otherwise relating to each element of the Works or a Stage (as defined in the Construction Contract) and that part of the Defence Estate upon which they are constructed.

Estate Information Provision Plan

The plan prepared by the Subconsultant and finalised under clause 7.4 in accordance with and for the purposes of the Defence Estate Information Management Requirements (and whether referred to as the "Data Provision Plan", "Estate Information Provision Plan" or otherwise), which must:

set out in adequate detail all procedures the Subconsultant will implement to manage the assessment, provision, creation, recording and updating of Estate Information in accordance with this Subcontract;

be prepared in accordance with the Data Provision Checklist;

meet all applicable Defence Estate Information Management Requirements;

meet all applicable HOTO Requirements;

include a program for the provision of all Estate Information in accordance with the Subcontract, including to provide for the deliverables and timeframes as required by the Defence Estate Information Management Requirements and clause 21.1; and

include any other materials required by the:

Subcontract;

Consultant's Representative; or

Regional Base Services Contractor.

Executive Negotiators

The representatives of the parties specified in the Subcontract Particulars or any person nominated by the relevant party to replace that person from time to time by notice in writing to the other party.

Expert Determination Agreement

An expert determination agreement on the terms set out in the Schedule of Collateral Documents.

Fee

If:

clause 9 does not apply, the amount set out in the Subcontract Particulars as adjusted in accordance with the Subcontract; or

clause 9 applies, the sum of the Planning Phase Fee and the Delivery Phase Fee (if any).

Fee Payment Schedule

The fee payment schedule (if any) set out in Annexure 3, as adjusted from time to time in accordance with clause 11.18, setting out:

  - the instalments in which the Fee (or any part of the Fee) will be payable; and

if applicable, the milestones which must be achieved for each instalment to become payable (failing which the Subconsultant's entitlement to be paid the relevant instalment of the Fee will not arise until such time as the applicable milestone is achieved).

Financial Representative

Means the Subconsultant’s chief financial officer, financial controller or other officer or employee with primary responsibility for managing the financial affairs of the Subconsultant.

Fraud

- Dishonestly obtaining (including attempting to obtain) a gain or benefit, or causing a loss or risk of loss, by deception or other means.

GEMS

The Garrison and Estate Management System established and managed by the Commonwealth to record and manage Estate Information including to define the classifications, attributes and formats for recording data for each element on the Defence Estate.

GST

The tax payable on taxable supplies under the GST Legislation.

GST Group

A GST group formed in accordance with Division 48 of the GST Legislation.

GST Legislation

A New Tax System (Goods and Services Tax) Act 1999 (Cth) and any related Act imposing such tax or legislation that is enacted to validate, recapture or recoup such tax.

Hazardous Substances

Has the meaning in the Special Conditions (if any).

HOTO Plan and Checklist

#### The worksheets contained within the excel workbook titled "HOTO Plan & Checklist" available at https://www.defence.gov.au/business-industry/industry-governance/industry-regulations/estate-project-handover-takeover-policy, as amended or replaced from time to time.

HOTO Process

#### The process for handover and takeover of the Works or a Stage (as defined in the Construction Contract) to enable the occupation, use, operation and maintenance of the Works or the Stage (as defined in the Construction Contract) by the Commonwealth and Other Contractors including the:

commissioning of the Works or the Stage (as defined in the Construction Contract) (including the inspection and testing process);

handover of the Works or the Stage (as defined in the Construction Contract) to the Commonwealth; and

occupation, use, operation and maintenance of the Works or the Stage (as defined in the Construction Contract) by the Commonwealth and Other Contractors,

#### in accordance with the HOTO Requirements.

HOTO Requirements

#### The requirements published on the Defence Website in respect of commissioning, handover and takeover of projects on the Defence Estate, including:

  - the documents set out at https://www.defence.gov.au/business-industry/industry-governance/industry-regulations/estate-project-handover-takeover-policy, and all applicable requirements referred to therein; and

any other requirement published on the Defence Website expressed as applying to the commissioning, handover and takeover of projects on the Defence Estate,

#### each as amended or replaced from time to time.

Indicative Delivery Phase Fee

The amount (if any) specified in the Subcontract Particulars.

Indigenous Enterprise

Has the meaning given to it in the Indigenous Procurement Policy.

Indigenous Procurement Policy

The Commonwealth's Indigenous Procurement Policy, as amended from time to time, available at https://www.niaa.gov.au/indigenous-affairs/economic-development/indigenous-procurement-policy-ipp.

Information Security Requirements

Means the:

Australian Government's Protective Security Policy Framework available at https://www.protectivesecurity.gov.au/;

Australian Government's Information Security Manual available at https://www.cyber.gov.au/ism; and

DSPF,

each as amended or replaced from time to time.

Insolvency Event

Any one of the following:

the Subconsultant becomes, is declared to be, is taken under any applicable law (including the Corporations Act 2001 (Cth)) to be, admits to or informs the Consultant in writing or its creditors generally that the Subconsultant is insolvent, an insolvent under administration, bankrupt, unable to pay its debts or is unable to proceed with the Subcontract for financial reasons;

execution is levied against the Subconsultant by a creditor;

a garnishee order, mareva injunction or similar order, attachment, distress or other process is made, levied or issued against or in relation to any asset of the Subconsultant;

where the Subconsultant is an individual person or a partnership including an individual person, the Subconsultant:

commits an act of bankruptcy;

has a bankruptcy petition presented against him or her or presents his or her own petition;

is made bankrupt; or

applies for, agrees to, enters into, calls a meeting for the consideration of, executes or is the subject of an order or declaration in respect of:

a moratorium of any debts; or

a personal insolvency agreement or any other assignment, composition or arrangement (formal or informal) with creditors,

- by which his or her assets are subjected conditionally or unconditionally to the control of a creditor or trustee;

where the Subconsultant is a corporation, any one of the following:

notice is given of a meeting of creditors with a view to the corporation entering into a deed of company arrangement;

a liquidator or provisional liquidator is appointed in respect of a corporation;

the corporation entering a deed of company arrangement with creditors;

a controller, restructuring practitioner, administrator, receiver, receiver and manager, provisional liquidator or liquidator (each as defined in section 9 of the Corporations Act 2001 (Cth)) is appointed to the corporation;

an application is made to a court for the winding up of the corporation and not stayed within 14 days;

any application (not withdrawn or dismissed within 7 days) is made to a court for an order, an order is made, a meeting is convened or a resolution is passed, for the purpose of proposing or implementing a scheme of arrangement other than with the prior approval of the Commonwealth under a solvent scheme of arrangement pursuant to Part 5.1 of the Corporations Act 2001 (Cth);

a winding up order or deregistration order is made in respect of the corporation;

the corporation resolves by special resolution that it be wound up voluntarily (other than for a members’ voluntary winding-up);

as a result of the operation of section 459F(1) of the Corporations Act 2001 (Cth), the corporation is taken to have failed to comply with a statutory demand (as defined in the Corporations Act 2001 (Cth)); or

a mortgagee of any property of the corporation takes possession of that property;

the Commissioner of Taxation issues a notice to any creditor of a person under the Taxation Administration Act 1953 (Cth) requiring that creditor to pay any money owing to that person to the Commissioner in respect of any tax or other amount required to be paid by that person to the Commissioner (whether or not due and payable) or the Commissioner advises that creditor that it intends to issue such a notice; or

anything analogous to anything referred to in paragraphs (a) to (f) or which has a substantially similar effect, occurs with respect to a person or corporation under any law of any jurisdiction.

Intellectual Property Rights

All statutory and other proprietary rights in respect of inventions, innovations, patents, utility models, designs, circuit layouts, mask rights, copyrights (including future copyrights), confidential information, trade secrets, know-how, trade marks and all other rights in respect of intellectual property as defined in Article 2 of the Convention establishing the World Intellectual Property Organisation of July 1967.

IT Equipment

Any software, hardware or telecommunications equipment:

produced; or

provided, or required to be provided, to the Consultant or the Consultant's Representative,

under, for the purpose of, arising out of or in connection with the Subcontract, the Subcontract Services or the Works by, for or on behalf of the Subconsultant.

Long Service Leave Legislation

Means:

Long Service Leave (Portable Schemes) Act 2009 (ACT);

Building and Construction Industry Long Service Payments Act 1986 (NSW);

Construction Industry Long Service Leave and Benefits Act 2005 (NT);

Building and Construction Industry (Portable Long Service Leave) Act 1991 (Qld);

Construction Industry Long Service Leave Act 1987 (SA);

Construction Industry (Long Service) Act 1997 (Tas);

Construction Industry Long Service Leave Act 1997 (Vic);

Construction Industry Portable Paid Long Service Leave Act 1985 (WA);

the long service leave obligations in the National Employment Standards in the Fair Work Act 2009 (Cth); and

any legislation in any State or Territory of Australia addressing long service leave in the building and construction industry.

Material Adverse Effect

In respect of a Prolongation Event, means a material increase in the resources required for, and the costs of, performing the Subcontract Services, which a prudent, competent and experienced consultant would not have anticipated as at:

  - if clause 9 does not apply, the Award Date; or

if clause 9 does apply, the date on which a notice is issued under clause 9.4(a).

Material Change

Any actual, potential or perceived material change to the circumstances of the Subconsultant, including any change:

arising out of or in connection with:

a Change of Control;

an Insolvency Event; or

the Subconsultant’s financial viability, availability, capacity or ability to perform the Subcontract Services and otherwise meet its obligations under the Subcontract; or

which affects the truth, completeness or accuracy of:

if the Subconsultant lodged a registration of interest, the Subconsultant’s registration of interest;

if the Subconsultant lodged a tender, the Subconsultant’s tender; or

any other information, documents, evidence or clarifications provided by the Subconsultant to the Consultant arising out of or in connection with its registration of interest, the registration of interest process, its tender, the tender process, the Subcontract or the Subcontract Services.

Method of Work Plan for Airfield Activities

The plan (if any) prepared by the Subconsultant and finalised under clause 7.4, which must incorporate Site specific management and control procedures and must set out in adequate detail all procedures the Subconsultant will implement to manage the Subcontract Services on and near the Site to ensure that the Subcontract Services do not impact aircraft operations, including procedures as they relate to:

the establishment of the Site;

access to the Site;

security passes for the Site;

personnel and vehicle identification and control on the Site;

control of personnel including a point of contact from the Subconsultant;

liaison with the Commonwealth, Consultant and Other Contractors;

Approvals prior to carrying out Subcontract Services;

rubbish, dust and debris control;

Foreign Object Damage (FOD) control;

noise management;

fencing;

security;

hours of work;

traffic management;

safety procedures;

fuel and hazardous material storage;

issues associated with military exercises and military expeditions;

issues associated with aircraft movements;

other information and details as may be required by Statutory Requirements;

the procedure for preparing (including tailoring) and finalising the Method of Work Plan for Airfield Activities under clause 7.4;

the procedure for regularly reviewing, updating and amending the Method of Work Plan for Airfield Activities under clause 7.4;

the procedure for ensuring subconsultant compliance with the Method of Work Plan for Airfield Activities; and

any other matters required by the:

Subcontract; or

Consultant's Representative.

Milestone

A milestone described in the Subcontract Particulars.

Moral Rights

The right of integrity of authorship, the right of attribution of authorship and the right not to have authorship falsely attributed, as defined in the Copyright Act 1968 (Cth).

NATA

National Association of Testing Authorities Australia.

National Construction Code

The National Construction Code that applies in the State or Territory where the Works are located, as amended or replaced from time to time, produced and maintained by the Australian Building Codes Board on behalf of the Commonwealth Government and each State and Territory Government.

Other Contractor

Any contractor, supplier, subcontractor, consultant, artist, tradesperson or other person (including the Contractor and the Regional Base Services Contractor) engaged to do work other than the Subconsultant.

Pandemic

The disease known as Coronavirus (COVID-19) which was characterised to be a pandemic by the World Health Organisation on 11 March 2020.

Pandemic Adjustment Event

Means any of the following events which arise as a direct result of the Pandemic and first occurs after the Award Date:

a change in Statutory Requirements (including a change in border requirements or quarantine requirements); or

such other events as may be specified in the Subcontract Particulars,

in each case which directly impacts the supply of labour, equipment, materials or services required for the carrying out of the Subcontract Services.

Personal Information

Has the meaning given in the Privacy Act.

Planning Phase

The period commencing on the Award Date and continuing until the earlier of:

if applicable, the date of commencement of the Delivery Phase;

if a notice is issued under clause 9.4(b), the date the Planning Phase Subcontract Services have been completed in accordance with the Subcontract; and

the date of termination of the Subcontract.

Planning Phase Fee

The amount specified in the Subcontract Particulars, as adjusted in accordance with the Subcontract.

Planning Phase Subcontract Services

The services described or reasonably to be inferred from the Subcontract as Planning Phase Subcontract Services, including those Subcontract Services described in the Brief.

Preliminary Design Solution

The preliminary design solution (if any) specified in the Subcontract Particulars.

Privacy Act

The Privacy Act 1988 (Cth).

Professional Indemnity Insurance

A policy of insurance to cover claims made against the insured for:

civil liability for breach of professional duty (whether owed in contract or otherwise); and

unintentional breaches of third party intellectual property,

by the Subconsultant in carrying out the Subcontract Services.

Project Documents

Means:

Design Documentation;

Project Plans;

Approvals;

IT Equipment, to the extent relating to software;

the documents which the Subconsultant is obliged to maintain under clause 11.15; and

without limiting paragraphs (a) - (e), any other data, documents, drawings, records, programs and information (including Estate Information and information relating to the Subconsultant's compliance with the WHS Legislation) and material:

produced; or

provided, or required to be provided, to the Consultant or the Consultant's Representative,

under, for the purposes of, arising out of or in connection with the Subcontract, the Subcontract Services or the Works by, for or on behalf of the Subconsultant.

Project Lifecycle and HOTO Plan

The plan prepared by the Subconsultant in accordance with, and for the purposes of, the HOTO Requirements and finalised under clause 7.4, which must not be inconsistent with the Consultant's Project Lifecycle and HOTO Plan and must:

be prepared in accordance with the HOTO Plan and Checklist;

meet all applicable HOTO Requirements and Statutory Requirements; and

include any other matters required by the:

Subcontract; or

Consultant’s Representative.

Project Plans

The:

Design Management Plan;

Environmental Management and Sustainability Plan;

Estate Information Provision Plan;

Project Lifecycle and HOTO Plan;

Quality Plan;

Site Management Plan;

Work Health and Safety Plan;

if clause 2.15 applies, Method of Work Plan for Airfield Activities; and

additional plans specified in the Subcontract Particulars and finalised by the Subconsultant under clause 7.4(a)(ii),

as updated or amended under clause 7.4.

Prolongation Event

Means:

a suspension instructed by the Commonwealth under a Construction Contract;

a variation directed by the Commonwealth under a Construction Contract; or

an Act of Prevention (as defined in the Construction Contract) under a Construction Contract,

which has the effect of extending the duration of the performance of the Subcontract Services beyond the Subcontract Services End Date.

Public Liability Insurance

- A policy of liability insurance covering the:

Subconsultant for its liabilities; and

Consultant for all legal liabilities arising out of or in connection with any act, error, omission, negligence or breach of contract by the Subconsultant,

- to third parties and to each other, for loss of, loss of use of or damage to property and death of or injury to any person, arising out of or in connection with, the Subcontract Services.

This policy is not required to cover liabilities or losses insured under Workers Compensation Insurance, Employers’ Liability Insurance or Professional Indemnity Insurance.

Quality Manager

The person specified in the Subcontract Particulars or any other person from time to time appointed as the Quality Manager for the Subcontract Services in accordance with clause 4.4.

Quality Objectives

Means to:

encourage best practice quality management through the planning, development, implementation and continuous improvement of quality assurance procedures, systems or frameworks during the Subcontract Services;

prevent and minimise adverse quality impacts during the Subcontract Services (including non-complying Subcontract Services before, at and after Completion) and Defects (or similar term used or defined in the Construction Contract) before, at and after Completion (as defined in the Construction Contract);

optimise the value for money achieved by the Commonwealth in respect of the Subcontract Services; and

achieve the additional objectives specified in the Subcontract Particulars.

Quality Plan

The plan prepared by the Subconsultant and finalised under clause 7.4, which must set out in adequate detail the procedures the Subconsultant will implement to manage the Subcontract Services from a quality perspective to:

ensure compliance with the Smart Infrastructure Handbook and Statutory Requirements; and

maximise the achievement of the Quality Objectives.

- The Quality Plan must not be inconsistent with the Consultant’s Quality Plan and must address, at a minimum:

all Statutory Requirements;

all Quality Objectives;

the Subconsultant’s quality assurance procedure, system or framework (which may or may not be a certified quality assurance procedure, system or framework);

the roles and responsibilities of all Subconsultant personnel (including the Quality Manager and the Subconsultant’s key people under clause 4.4(a)(i)) regarding quality;

the procedure for consultation, co-operation and co-ordination of activities with the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative and Other Contractors regarding quality generally during the Subcontract Services;

the training and awareness programmes provided to Subconsultant personnel regarding quality;

the procedure for preparing (including tailoring) and finalising the Quality Plan to meet the requirements of the Subcontract under clause 7.4 (including how the Subconsultant will ensure maximum consistency between the Subconsultant’s quality assurance procedure, system or framework and the Quality Plan);

the procedure for regularly reviewing, updating and amending the Quality Plan under clause 7.4;

the procedure for regularly identifying, controlling and monitoring possible and actual impacts on quality associated with the Subcontract Services, including the procedures for recording, reporting, responding to and finalising:

matters arising out of or in connection with such identification, control and monitoring; and

complaints regarding quality during the Subcontract Services;

the procedure for regular auditing or other monitoring of Subconsultant compliance with the Quality Plan, including the procedures for recording, reporting, responding to and finalising:

matters arising out of or in connection with such audits or other monitoring; and

complaints regarding quality during the Subcontract Services;

the additional matters specified in the Subcontract Particulars; and

any other matters required by the:

Subcontract; or

Consultant’s Representative.

Regional Base Services Contractor

- The person specified in the Subcontract Particulars or any other person nominated by the Commonwealth from time to time to replace that person.

Schedule of Collateral Documents

The schedule of proforma contracts and other documents applicable to the Defence Design Services Subcontract:

posted on the Defence Website, as amended from time to time by the Commonwealth; and

which as at the Award Date include the contracts and other documents specified in the Subcontract Particulars.

Security of Payment Legislation

Means:

Building and Construction Industry Security of Payment Act 1999 (NSW);

Building and Construction Industry Security of Payment Act 2002 (Vic);

Building Industry Fairness (Security of Payment) Act 2017 (Qld);

in Western Australia:

the Construction Contracts Act 2004 (WA); or

if this subcontract is executed after the date on which a provision of the Building and Construction Industry (Security of Payment) Act 2021 (WA) commences, then the Building and Construction Industry (Security of Payment) Act 2021 (WA) and any provision of the Construction Contracts Act 2004 (WA) which has not been repealed;

Construction Contracts (Security of Payments) Act 2004 (NT);

Building and Construction Industry Security of Payment Act 2009 (Tas);

Building and Construction Industry (Security of Payment) Act 2009 (ACT);

Building and Construction Industry Security of Payment Act 2009 (SA); and

any legislation in any State or Territory of Australia addressing security of payment in the building and construction industry.

Security or Confidentiality Incident

Means:

  - a "Security Incident" as defined in Control 77.1 of the DSPF insofar as the relevant approach, event or action arises out of or in any way in connection with this Subcontract or the carrying out of the Subcontract Services or otherwise relates to the Subconsultant or any Related Body Corporate of the Subconsultant; or

any other incident or circumstance involving Confidential Information (including any Sensitive and Classified Information) having been held, disclosed, accessed or used in a way that is inconsistent with the terms of the Subcontract.

Sensitive and Classified Information

Means:

any document, drawing, information or communication (whether in written, oral or electronic form) issued or communicated to the Subconsultant by the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative or anyone on the Commonwealth's or Consultant’s behalf, whether or not owned by the Commonwealth or Consultant:

marked as "sensitive information", "for official use only" or "OFFICIAL: Sensitive";

identified at the time of issue or communication as "Sensitive Information";

marked with a national security classification or as "Classified Information";

identified at the time of issue or communication as "Classified Information"; or

the Subconsultant knows or ought to know is subject to, or ought to be treated as, sensitive or classified information in accordance with any Statutory Requirement (including the Information Security Requirements); and

everything recording, containing, setting out or making reference to the document, drawing, information or communication (whether in written, oral or electronic form) referred to in paragraph (a) above, including documents, notes, records, memoranda, materials, software, disks and all other media, articles or things.

- Shadow Economy Procurement Connected Policy

The Shadow Economy Procurement Connected Policy – Increasing the Integrity of Government Procurement – October 2024, as amended or replaced from time to time.

- Significant Event

- Means:

any adverse findings made by a court, commission, tribunal or other statutory or professional body regarding the conduct or performance of the Subconsultant (or any officers, employees or agents of the Subconsultant) that impacts or could be reasonably perceived to impact on their professional capacity, capability, fitness or reputation; or

any other significant matters, including the commencement of legal, regulatory or disciplinary action involving the Subconsultant (or any officers, employees or agents of the Subconsultant) that may adversely impact on compliance with Commonwealth policy and legislation or the Consultant's or the Commonwealth’s reputation.

Site

The site or sites for the Works described in the Subcontract Particulars.

Site Management Plan

The plan prepared by the Subconsultant and finalised under clause 7.4, which must set out in adequate detail all procedures the Subconsultant will implement to manage the Subcontract Services on and near the Site.

The Site Management Plan must not be inconsistent with the Consultant’s Site Management Plan and must address, at a minimum:

all Statutory Requirements;

the roles and responsibilities of all Subconsultant personnel (including the Subconsultant’s Representative and the Subconsultant’s key people under clause 4.4(a)(i)) regarding management of the Subcontract Services on and near the Site;

the procedure for consultation, co-operation and co-ordination of activities with the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative and any Other Contractors regarding the occupation, use, operation and maintenance of Commonwealth property and the Site (including for the purpose of military activities, expeditions and exercises) during the Subcontract Services;

procedures for access to:

Commonwealth property (including any Defence location); and

the Site,

- by Subconsultant personnel, visitors, pedestrians and vehicles, including procedures for:

ensuring security (including identification and pass procedures and any physical security measures);

minimising disruption and inconvenience to the Consultant, the Commonwealth and Other Contractors;

vehicle and traffic management; and

noise management;

without limiting paragraph (d), Site inductions, training and other awareness programmes provided to Subconsultant personnel in respect of Commonwealth property and the Site;

procedures for (as applicable):

establishing the Site (including site amenities, laydown areas and parking zones);

cleaning, maintenance, waste management and debris control on Commonwealth property and the Site; and

any dangerous or prohibited substances, material or goods (including Commonwealth property) on the Site relevant to the Subcontract Services;

the procedure for preparing (including tailoring) and finalising the Site Management Plan under clause 7.4;

the procedure for regularly reviewing, updating and amending the Site Management Plan under clause 7.4 (including as a result of any Site management complaint, incident, near-miss and other situation or accident on Commonwealth property or the Site during the Subcontract Services);

the procedure for regularly identifying, controlling and monitoring possible and actual Site management impacts on Commonwealth property and the Site associated with the Subcontract Services, including the procedures for recording, reporting, responding to and finalising:

matters arising out of or in connection with such identification, control and monitoring; and

complaints, incidents, near-misses and other situations or accidents on Commonwealth property and the Site during the Subcontract Services;

the procedure for managing the effects of the Pandemic on the carrying out of the Subcontract Services;

the procedure for regular auditing or other monitoring of Subconsultant compliance with the Site Management Plan, including the procedures for recording, reporting, responding to and finalising:

matters arising out of or in connection with such audits or other monitoring; and

complaints, incidents, near-misses and other situations or accidents on Commonwealth property and the Site during the Subcontract Services;

the additional matters specified in the Subcontract Particulars; and

any other matters required by the:

Subcontract; or

Consultant’s Representative.

Smart Infrastructure Handbook

The Defence Smart Infrastructure Handbook: Planning, Design and Construction available on the Defence Website, as amended or replaced from time to time.

Spatial Data Management Plan

The plan setting out standards and specifications for spatial data management, available on the Defence Website, as amended or replaced from time to time.

Special Conditions

The special conditions as set out in Annexure 2.

Statement of Tax Record or STR

Has the meaning given in the Shadow Economy Procurement Connected Policy.

Statutory Requirements

Means:

any law applicable to the Subcontract Services and the Works, including Acts, ordinances, regulations, by-laws and other subordinate legislation;

Approvals (including any condition or requirement under an Approval);

Defence Requirements;

Environmental Requirements; and

Information Security Requirements.

Strategic Notice Event

Means:

a Material Change;

a Defence Strategic Interest Issue;

a Significant Event; or

any known or suspected Fraud or Corruption which is occurring or has occurred in connection with the Subcontract or the Subcontract Services.

Strategic Notice Event Remediation Plan

The plan (if any) prepared by the Consultant and finalised under clause 19.4.

Subconsultant

The person specified in the Subcontract Particulars.

Subconsultant Deed of Covenant

A subconsultant deed of covenant in the form set out in the Schedule of Collateral Documents.

Subconsultant Design Certificate

A subconsultant design certificate in the form set out in the Schedule of Collateral Documents.

Subconsultant Estate Information Obligation

Means any task, function, requirement or obligation relating to the assessment, creation, recording, updating and management of Estate Information which a Defence Estate Information Management Requirement allocates, or would reasonably be inferred as allocating, to the Subconsultant, including (as applicable to the Subcontract Services) those allocated to a Data Supplier.

Subconsultant HOTO Obligation

Any task, function, requirement or obligation relating to the HOTO Process (including commissioning of the Works or a Stage (as defined in the Construction Contract)) required to be performed by the Subconsultant under this Subcontract or which a HOTO Requirement allocates, or would reasonably be inferred as allocating, to the Subconsultant, including (as applicable to the Subcontract Services) those that the HOTO Plan and Checklist expressly allocates to the "Contractor Representative (Design Services Contractor)" (as that term is used in the HOTO Plan and Checklist).

Subconsultant's Representative

The person specified in the Subcontract Particulars or any other person from time to time appointed as the Subconsultant's Representative in accordance with clause 4.4.

Subcontract

The contractual relationship between the parties constituted by:

the Formal Agreement;

these Conditions of Subcontract;

the Subcontract Particulars;

the Special Conditions;

the Brief; and

the other documents (if any) specified in the Subcontract Particulars.

Subcontract Particulars

The particulars annexed to these Conditions of Subcontract and entitled "Subcontract Particulars".

Subcontract Services

The professional services described in, or reasonably to be inferred from, the Brief and comprising (if they are phased) the Planning Phase Subcontract Services and (subject to clause 9) the Delivery Phase Subcontract Services.

Subcontract Services End Date

The date which is 12 months after the last Date for Completion under the Construction Contract (as at the Award Date under the Construction Contract).

Sustainable Procurement Guide

The Sustainable Procurement Guide published by the Department of Agriculture, Fisheries and Forestry, as amended or replaced from time to time.

Table of Variation Rates and Prices

The table (if any) in Annexure 4, containing rates and prices to be used for the purposes of valuing Variations under clause 10.3.

Updated Delivery Phase Fee Proposal

The updated Delivery Phase Fee Proposal prepared and submitted by the Subconsultant under and in accordance with clause 9.2(a).

Variation

Unless otherwise stated in the Subcontract, means any change to the Subcontract Services, including any addition, increase, decrease, omission, deletion or removal to or from the Subcontract Services.

WHS Legislation

Means any of the following:

Work Health and Safety Act 2011 (Cth) and Work Health and Safety Regulations 2011 (Cth); and

any corresponding WHS law as defined in section 4 of the Work Health and Safety Act 2011 (Cth).

WOL

Whole of life.

WOL Cost

The total of the direct/indirect, recurring/non-recurring, fixed/variable financial costs to the Commonwealth arising out of or in connection with the Works over the whole life of the Works, including the costs of designing and constructing the Works prior to Completion (as defined in the Construction Contract) and occupying, using, operating and maintaining the Works after Completion (as defined in the Construction Contract).

WOL Objectives

Means balancing the:

WOL Cost;

useful life of the Works;

reliability and availability of the Works throughout their useful life;

operability and maintainability of the Works throughout their useful life;

value for money achieved by the Commonwealth from the design, construction, use, occupation, operation and maintenance of the Works;

opportunity to reduce resource use during the occupation, use, operation and maintenance of the Works throughout their useful life and the achievement of the other requirements of the Smart Infrastructure Handbook; and

achievement of the additional matters specified in the Subcontract Particulars.

Work Health and Safety Plan

The plan prepared by the Subconsultant and finalised under clause 7.4 (which is either Subcontract specific or Site specific) and which must set out in adequate detail the procedures the Subconsultant will implement to manage the Subcontract Services from a work health and safety perspective to ensure compliance with all Statutory Requirements (including the WHS Legislation).

The Work Health and Safety Plan must not be inconsistent with the Consultant’s Work Health and Safety Plan and must address, at a minimum:

the names, positions and responsibilities of all persons at the workplace whose positions or roles involve specific health and safety responsibilities in connection with the Subcontract Services;

the arrangements in place, or to be implemented, between any persons conducting a business or undertaking (PCBU) at the workplace where the Subcontract Services are being undertaken regarding consulting, co-operating and co-ordinating activities where the PCBU(s) at the workplace and the Subconsultant owe a work health and safety duty in relation to the same work health and safety matter (including procedures for information sharing and communication);

the arrangements in place, or to be implemented, for managing any work health and safety incidents that occur at a workplace where the Subcontract Services are carried out, including:

incident (including notifiable incident) reporting procedures;

preventative and corrective action procedures; and

record-keeping and reporting requirements, including reporting to the DSC Contract Administrator and Consultant’s Representative with respect to incidents and accidents under clause 6.15(c);

any Site-specific health and safety rules, and the arrangements for ensuring that all persons at the workplace are informed of these rules;

the arrangements for the collection and recording, and any assessment, monitoring and review of safe work method statements at the workplace;

the procedures for:

conducting design risk assessments to ensure compliance with Statutory Requirements (including the WHS Legislation), including regarding design changes relevant to work health and safety;

carrying out calculations, analysis, testing or examinations regarding design to ensure compliance with WHS Legislation; and

ensuring the results of such calculations, analysis, testing or examinations are provided to the Commonwealth prior to Completion (as defined in the Construction Contract) and prior to the expiry of the Defects Liability Period (as defined in the Construction Contract);

procedures and arrangements for the management of work health and safety generally, including:

details of the Subconsultant's work health and safety policy;

details of any work health and safety management system (whether certified or uncertified);

inductions, training and other awareness programmes regarding work health and safety and any workplace specific work health and safety induction, training and other awareness programmes; and

emergency procedures, emergency management planning, the use of emergency equipment and the establishment of workplace specific first aid facilities;

procedures for ensuring the provision of written assurances to the Consultant’s Representative under clause 6.15(e) regarding compliance with the WHS Legislation by the Subconsultant and Other Contractors;

procedures for the preparation, finalisation and regular reviewing of the Work Health and Safety Plan under clause 7.4 (including as a consequence of any review of hazards, risks and control measures regarding the Subcontract Services and any notifiable incident or systemic risk management failure);

details of the project and Subcontract specific hazards and risks identified by the Subconsultant and the Subconsultant's approach to the management of these hazards and risks including how the Subconsultant will identify hazards and eliminate or minimise risks so far as is reasonably practicable:

prior to commencing the Subcontract Services; and

during the delivery of the Subcontract Services;

the approach the Subconsultant will adopt in identifying, controlling and managing work health and safety hazards and risks concerning Hazardous Substances, including, where they are used or handled in the delivery of the Subcontract Services, incorporated into the Works, stored by the Subconsultant at the workplace or transported by the Subconsultant to or from the workplace;

the actions the Subconsultant will take to proactively identify and manage risks to ensure it avoids systematic work health and safety risk management failures occurring during the delivery of the Subcontract Services;

the procedures the Subconsultant will adopt to audit or otherwise monitor and verify its compliance with the Work Health and Safety Plan and the WHS Legislation (including details of the regularity, form and content of such audit, monitoring and verification activities);

the procedures the Subconsultant will adopt to ensure it provides to the Consultant, when conducting handover and takeover activities, all information regarding hazards and risks present in or arising out of or in connection with the use of the Works including for the purpose for which they were designed or manufactured (including the supply of information in accordance with clause 6.15(n));

any additional matters specified in the Subcontract Particulars; and

any other matters required by the:

Subcontract; or

Consultant’s Representative.

Workers Compensation Insurance

A policy of insurance prescribed by Statutory Requirements in the State and Territory in which the Subcontract Services are performed or the Subconsultant's employees perform work, are employed or normally reside to insure against or make provision for the liability of the Subconsultant to its employees for death or injuries arising out of or in connection with their employment.

Works

The works described in the Subcontract Particulars.

Interpretation

In the Subcontract, unless the context otherwise indicates:

words in the singular include the plural and vice versa;

references to a person include an individual, firm, corporation or unincorporated body;

except in clause 1.1, headings are for convenience only and do not affect the interpretation of the Subcontract;

references to any party to the Subcontract include its successors or permitted assigns;

a reference to a party, clause, Annexure, Attachment, Schedule, or exhibit is a reference to a party, clause, Annexure, Attachment, Schedule or exhibit of or to the Subcontract;

references to the Subcontract and any deed, agreement or instrument are deemed to include references to the Subcontract or such other deed, agreement or instrument as amended, novated, supplemented, varied or replaced from time to time;

words denoting any gender include all genders;

references to any legislation or to any section or provision of any legislation include any:

statutory modification or re-enactment of or any statutory provision substituted for that legislation, section or provision; and

ordinances, by-laws, regulations and other statutory instruments issued under that legislation, section or provision;

no rule of construction applies to the disadvantage of a party on the basis that the party put forward the Subcontract or any part;

a reference to "dollars" or "$" is to Australian currency;

amounts expressed in dollars are exclusive of GST;

where under the Subcontract:

a direction is required to be given or must be complied with; or

payment of money must be made (other than under clause 11.5),

within a period of 7 days or less from a specified event, then Saturdays, Sundays and public holidays in the place in which the Site is situated will not be counted in computing the number of days;

for the purposes of clauses 8.8 and 8.9, any:

extension of time stated in days; or

reference to "day",

- will exclude public holidays and include only those days which are stated in the Subconsultant's then current program under clause 8.2 as working days;

for the purposes of clauses 11.4, 11.5, 16.13, and 19, to the extent that the Subcontract Services are to be carried out in:

the Australian Capital Territory, "business day" has the same meaning as defined at Part 1 of the Legislation Act 2001 (ACT);

New South Wales, "business day" has the same meaning as defined in section 4 of the Building and Construction Industry Security of Payment Act 1999 (NSW);

the Northern Territory, "business day" has the same meaning as "working day" as defined in section 4 of the Construction Contracts (Security of Payments) Act 2004 (NT);

Queensland, "business day" has the same meaning as defined in Schedule 2 of the Building Industry Fairness (Security of Payment) Act 2017 (Qld);

South Australia, "business day" has the same meaning as defined in section 4 of the Building and Construction Industry Security of Payment Act 2009 (SA);

Tasmania, "business day" has the same meaning as defined in section 4A of the Building and Construction Industry Security of Payment Act 2009 (Tas);

Victoria, "business day" has the same meaning as defined in section 4 of the Building and Construction Industry Security of Payment Act 2002 (Vic); and

Western Australia, "business day" has the same meaning as defined in section 4 of the Building and Construction Industry (Security of Payment) Act 2021 (WA);

other than as set out in paragraphs (l), (m) and (n) references to "day" are references to calendar days;

the words "including" and "includes", and any variants of those words, will be read as if followed by the words "without limitation";

where a clause contains two options, the option specified in the Subcontract Particulars will apply;

derivatives of a word or expression which has been defined in clause 1.1 will have a corresponding meaning to that assigned to it in clause 1.1;

unless agreed or notified in writing by the Consultant's Representative or the date of the standard or reference document is specified in the Brief, a reference to Standards Australia standards, overseas standards or other similar reference documents in the Brief is a reference to the edition last published prior to the submission of the relevant Design Documentation. If requested by the Consultant's Representative, the Subconsultant must make copies of all Standards Australia standards, overseas standards or other similar reference documents referred to in the Brief and the Design Documentation available to the Consultant's Representative;

for the purposes of clauses 2.11(c), 2.13(b), 2.14(d)(i)B, 8.4(b)(ii)B, 8.10(c), 8.11(c)(ii) and 16.3(e)(ii), a reference to "extra costs" includes a reference to extra costs reasonably incurred by the Subconsultant as a direct result of the applicable event delaying the Subconsultant;

requirements contained in the Brief:

whether or not they include the expression "the Subconsultant must" or "the Subconsultant shall" or any equivalent expression, will be deemed to be requirements to be satisfied by the Subconsultant, unless stated otherwise;

represent the Consultant's minimum requirements, which must be met or exceeded by the Subconsultant in performing the Subcontract Services; and

will not operate to limit or exclude the Subconsultant's obligations under the Subcontract; and

where an absolute discretion is conferred on the Consultant or the Consultant's Representative:

neither the Consultant nor the Consultant's Representative is required to exercise such discretion for the benefit of the Subconsultant; and

the exercise or failure to exercise such discretion is not capable of being the subject of a dispute or difference for the purposes of clause 13.1 or otherwise subject to review.

Miscellaneous

The Subcontract is subject to and is to be construed in accordance with the laws of the State or Territory specified in the Subcontract Particulars.

None of the terms of the Subcontract can be waived, discharged or released at law or in equity unless:

to the extent that the term involves a right of the party seeking to waive the term or one party seeking to waive an obligation of the other party - this is done by written notice to the other party; or

otherwise, both parties agree in writing.

The Subcontract constitutes the entire agreement and understanding between the parties and will take effect according to its tenor despite:

any prior agreement in conflict or at variance with the Subcontract; or

any correspondence or other documents relating to the subject matter of the Subcontract which may have passed between the parties prior to the Award Date and which are not included in the Subcontract.

Where a party comprises two or more persons, each person will be jointly and severally bound by the party's obligations under the Subcontract.

Any provision in the Subcontract which is illegal, void or unenforceable will be ineffective to the extent only of such illegality, voidness or unenforceability and such illegality, voidness or unenforceability will not invalidate any other provision of the Subcontract.

The Subconsultant must indemnify the Consultant against:

any liability to or claim by a third party including the Contractor or an Other Contractor; and

all costs, expenses, losses, damages and liabilities suffered or incurred by the Consultant,

- caused by any breach by the Subconsultant of a term of the Subcontract.

All obligations to indemnify under the Subcontract survive termination of the Subcontract on any basis.

If a document referred to as being available on the Defence Website is not so available, the Consultant's Representative may provide such document to the Subconsultant by other means.

Unless expressly stated to the contrary in the Subcontract, the Subconsultant must perform the Subcontract Services at its cost.

ROLE OF THE SUBCONSULTANT

Engagement

- The Subconsultant must carry out the Subcontract Services in accordance with the Subcontract.

Standard of Care

The Subconsultant:

must exercise the standard of skill, care and diligence in the performance of the Subcontract Services that would be expected of an expert professional provider of the Subcontract Services;

must:

ensure that the Design Documentation complies with the requirements of the Subcontract; and

use its best endeavours to ensure that the Design Documentation will be fit for the purposes as set out in, or reasonably to be inferred from, the Brief;

must ensure that the Subcontract Services are provided economically and in accordance with any budgetary requirements of the Consultant notified to the Subconsultant; and

must exercise the utmost good faith in the best interests of the Consultant and keep the Consultant fully and regularly informed as to all matters affecting or relating to the Subcontract Services and the Works.

Authority to Act

Other than as expressly authorised, the Subconsultant has no authority to, and must not:

enter into any contracts, commitments or other legal documents or arrangements in the name of, or on behalf of, the Consultant; or

take any act or step to bind or commit the Consultant in any manner, whether as a disclosed agent of the Consultant or otherwise.

The Subconsultant is an independent consultant and is not, and must not purport to be, a partner or joint venturer of the Consultant.

Knowledge of the Consultant's Requirements

The Subconsultant must:

inform itself of the Consultant’s requirements for the Subcontract Services and the Works;

refer to the Consultant Material and the Consultant's Program; and

consult the Consultant during the Subcontract Services and the Works.

Notice of Matters Impacting on the Subcontract Services or the Works

Without limiting clauses 14.1 - 14.5, if the Subconsultant becomes aware of any matter which:

is likely to change or which has changed the scope, timing or cost of the Subcontract Services or the Works;

affects or may affect the Consultant's Program or the Subconsultant's then current program under clause 8.2;

involves any error, omission or defect in any continuing or completed aspect of the Subcontract Services; or

involves any Defect (or similar term used or defined in the Construction Contract) in any continuing or completed aspect of the Works,

the Subconsultant must promptly give written notice of that matter to the Consultant's Representative containing, as far as practicable in the circumstances:

particulars of the change, error, omission or defect;

its likely effect; and

the Subconsultant's recommendation as to how to minimise its effect upon the scope, timing and cost of the Subcontract Services and the Works.

Co-operation with Other Contractors

Without limiting clause 6.15(a)(iii), the Subconsultant must:

permit Other Contractors to carry out their work;

fully co-operate with Other Contractors;

carefully co-ordinate and integrate the Subcontract Services with the work carried out or to be carried out by Other Contractors;

carry out the Subcontract Services so as to avoid inconveniencing, interfering with, disrupting or delaying the work of Other Contractors; and

without limitation, provide whatever advice, support and co-operation is reasonable to facilitate the work carried out or to be carried out by Other Contractors.

Access to Subconsultant's Premises

Without limiting clause 6.11, the Subconsultant must at all reasonable times:

give to the Consultant's Representative, or to any persons authorised in writing by the Consultant's Representative, access to premises occupied by the Subconsultant where the Subcontract Services are being carried out; and

permit those persons referred to in paragraph (a) to inspect the carrying out of the Subcontract Services and any Design Documentation or other Project Documents.

Conflict of Interest

The Subconsultant warrants that:

at the Award Date, no conflict of interest exists or is likely to arise in the performance of its obligations under the Subcontract; and

if any such conflict of interest or risk of such conflict of interest arises, the Subconsultant will:

notify the Consultant's Representative immediately in writing of that conflict or risk; and

take all steps required by the Consultant's Representative to avoid or minimise the conflict of interest or risk of conflict of interest.

Subcontracting

The Subconsultant must not subcontract any Subcontract Services.

Statutory Requirements

In carrying out the Subcontract Services, the Subconsultant must:

unless otherwise specified in the Subcontract Particulars, comply with all applicable Statutory Requirements;

apply for and obtain all Approvals specified in the Subcontract Particulars;

give all notices and pay all fees and other amounts which it is required to pay in respect of the carrying out of its Subcontract obligations; and

promptly give the Consultant's Representative copies of all documents (including Approvals and other notices) that any authority, body or organisation having jurisdiction over the Site, the Subcontract Services or the Works issues to the Subconsultant.

Change in Statutory Requirements or Variance with Subcontract

If:

there is any change in a Statutory Requirement after the Award Date; or

a Statutory Requirement is at variance with the Subcontract,

then the party discovering the change or variance must promptly give the Consultant’s Representative and the other party notice in writing.

The Consultant's Representative must, within 14 days of receipt of a notice under paragraph (a), instruct the Subconsultant as to the course it must adopt insofar as the Subcontract Services are affected by the change or variance.

Subject to paragraph (d), the Subconsultant will be entitled to have the Fee increased by the extra costs reasonably incurred by the Subconsultant after the giving of the notice under paragraph (a) which arise directly from the change or variance and the Consultant’s Representative’s instruction under paragraph (b), as determined by the Consultant’s Representative.

The Fee will be decreased by any savings made by the Subconsultant which arise directly from the change or variance and the Consultant’s Representative’s instruction under paragraph (b), as determined by the Consultant’s Representative.

To the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with the change or variance or the Consultant's Representative’s instruction under paragraph (b), other than under paragraph (c).

Subconsultant Deed of Covenant and Novation

If requested by the Consultant’s Representative, the Subconsultant must execute a Subconsultant Deed of Covenant, duly completed with all relevant particulars, within the period specified by the Consultant's Representative in such request and deliver the executed Subconsultant Deed of Covenant to the Consultant's Representative.

The parties acknowledge that if the Commonwealth provides a written notice to the parties requiring novation of the Subcontract to the Commonwealth (or its nominee) in accordance with the Subconsultant Deed of Covenant, then the Subcontract will be deemed to have been novated in accordance with the Subconsultant Deed of Covenant.

The Environment

The Subconsultant must:

ensure that in carrying out the Subcontract Services:

other than to the extent identified in writing by the Consultant's Representative, it complies with all Statutory Requirements and other requirements of the Subcontract for the protection of the Environment;

it does not cause or contribute to any Environmental Incident;

without limiting subsubparagraph B, it does not cause or contribute to Contamination of the Site or any other land, air or water or cause or contribute to any Contamination emanating from the Site;

it immediately notifies the Consultant's Representative of:

any non-compliance with the requirements of clause 2.13;

any breach of a Statutory Requirement for the protection of the Environment;

any Environmental Incident; or

the receipt of any notice, order or communication received from an authority for the protection of the Environment; and

clean up and restore the Environment, including any Contamination or Environmental Harm arising out of or in connection with the Subcontract Services, whether or not it has complied with all Statutory Requirements and other requirements of the Subcontract for the protection of the Environment.

To the extent that the requirement to clean up and restore the Environment under paragraph (a)(ii) arises other than as a result of a failure by the Subconsultant to carry out the Subcontract Services strictly in accordance with all Statutory Requirements and other requirements of the Subcontract, the Subconsultant will be entitled to have the Fee increased by the extra costs reasonably incurred by the Subconsultant which arise directly from the cleaning up and restoration of the Environment under clause 2.13, as determined by the Consultant’s Representative.

Pandemic Adjustment Event

If either party considers that there has been a Pandemic Adjustment Event, then the party discovering it must promptly give the Consultant’s Representative and the other party notice in writing, together with detailed particulars of the relevant event and such other information as the Consultant's Representative may require.

The Consultant’s Representative must, within 14 days of receipt of a notice under paragraph (a), notify the Subconsultant and the Consultant of its determination whether a Pandemic Adjustment Event has occurred.

Where the Consultant’s Representative has determined a Pandemic Adjustment Event has occurred, the Consultant’s Representative may, without being under any obligation to do so, instruct the Subconsultant as to the course it must adopt insofar as the Subcontract Services are affected by the Pandemic Adjustment Event, including to prepare (and thereafter comply with) a plan satisfactory to the Consultant's Representative specifying the steps that the Subconsultant will implement to avoid, mitigate, resolve and otherwise manage the effects of the Pandemic on the Subcontract Services and the Works.

If a Pandemic Adjustment Event occurs:

subject to paragraph (f), the Subconsultant will be entitled to:

an extension of time to any relevant Date for Completion where it is otherwise so entitled under clause 8.8; and

have the Fee increased by the extra costs reasonably incurred by the Subconsultant after the giving of the notice under paragraph (a) which arise directly from the Pandemic Adjustment Event or any instruction of the Consultant’s Representative under paragraph (c) as determined by the Consultant's Representative; and

subject to paragraph (f), the Fee will be decreased by any savings made (or which would have been made if the Subconsultant had taken all reasonable steps to maximise savings) by the Subconsultant which arise directly from the Pandemic Adjustment Event or any instruction of the Consultant's Representative under paragraph (c), as determined by the Consultant's Representative; and

the Subconsultant must comply with any direction of the Consultant’s Representative in relation to the Pandemic Adjustment Event.

To the extent permitted by law:

the entitlement of the parties in respect of a Pandemic Adjustment Event will be determined solely under this clause 2.14; and

without limiting subparagraph (i), the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with a Pandemic Adjustment Event or any instruction of the Consultant’s Representative under paragraph (c), other than under paragraph (d)(i).

The Consultant’s Representative:

will reduce any entitlement the Subconsultant would have otherwise had under paragraph (d)(i)B to the extent that the Subconsultant has failed to take all reasonable steps to:

avoid or overcome any adverse effects of the Pandemic Adjustment Event (including by complying with its obligations under the Subcontract); or

minimise any additional cost to the Consultant in respect of the Pandemic Adjustment Event; and

will take into account, for the purposes of paragraph (d)(ii), the extent that the Subconsultant has failed to take all reasonable steps to maximise any savings to the Consultant in respect of the Pandemic Adjustment Event.

Method of Work Plan for Airfield Activities and Operating Airfield

Clause 2.15 does not apply unless the Subcontract Particulars state that it does apply.

Without limiting clause 7.4, as the Subcontract Services are to be carried out on or in the vicinity of an airfield, the Subconsultant must carry out the Subcontract Services in accordance with, and otherwise implement, a Method of Work Plan for Airfield Activities.

The Subconsultant must ensure that the Subcontract Services do not compromise aircraft operations or the safety of aircraft.

Without limiting clause 6.15(a)(iii) and as part of the Subcontract Services, the Subconsultant must liaise with the Consultant and the Consultant's Representative as required to co-ordinate the Subcontract Services with, and prevent interruption of, Commonwealth activities including aircraft operations and the safety of aircraft.

Role of the CONSULTANT

Information and Subcontract Services

The Consultant must as soon as practicable make available to the Subconsultant:

all relevant information, documents and particulars relating to the Works and to the Consultant’s requirements for the Works, including the Consultant's Program; and

details of the budget for the Works, as relevant to the Subcontract Services.

Additional Information

If:

the Subconsultant, in its reasonable opinion, considers that any additional information, documents or particulars are needed to enable it to carry out the Subcontract Services; and

the additional information, documents or particulars are not provided by the Consultant under the Subcontract or by an Other Contractor,

then:

the Subconsultant must give notice in writing to the Consultant's Representative of the details of the additional information, documents or particulars and the reasons why they are required; and

the Consultant must, if the Consultant's Representative believes that the additional information, documents or particulars are needed by the Subconsultant, use its best endeavours to arrange the provision of the additional information, documents or particulars.

Access to the Site

Subject to:

the Design Services Contract;

the Construction Contract;

any other agreement or arrangement with a party other than the Subconsultant (including any Other Contractor);

the Environmental Management and Sustainability Plan, the Site Management Plan, the Work Health and Safety Plan and, if clause 2.15 applies, the Method of Work Plan for Airfield Activities having been finalised under clause 7.4;

the Subconsultant having provided to the Consultant’s Representative evidence satisfactory to the Consultant’s Representative under clause 5.1(e) that the Subconsultant has caused to be effected and maintained or otherwise have the benefit of the insurances required under clause 5.1; and

any other conditions specified in the Subcontract Particulars or elsewhere in the Subcontract,

the Consultant must:

as soon as practicable, provide the Subconsultant with access to the Site upon which the Works are to be constructed; and

arrange access to any other property which may be necessary for the Subconsultant to carry out the Subcontract Services.

Personnel

Consultant's Representative

The Consultant's Representative will give directions and carry out all of the other functions of the Consultant's Representative under the Subcontract as the agent of the Consultant (and not as an independent certifier, assessor or valuer).

The Subconsultant must:

comply with any direction by the Consultant's Representative given or purported to be given under a provision of the Subcontract; and

not comply with any direction of the Commonwealth other than as expressly stated in the Subcontract.

Except where the Subcontract otherwise provides, the Consultant's Representative may give a direction orally but will as soon as practicable confirm it in writing.

Replacement of Consultant's Representative

The Consultant may at any time replace the Consultant's Representative, in which event the Consultant will appoint another person as the Consultant's Representative and notify the Subconsultant of that appointment.

Any substitute Consultant's Representative appointed under clause 4.2 will be bound by anything done by the former Consultant's Representative to the same extent as the former Consultant's Representative would have been bound.

Parties' Conduct

Without limiting any of the rights or obligations of the Consultant and Subconsultant under the Subcontract, the Consultant and Subconsultant must co-operate with each other in carrying out their obligations under the Subcontract.

Key People for the Subcontract Services

The Subconsultant must:

employ those people specified in the Subcontract Particulars, including the Subconsultant's Representative and Quality Manager in the jobs specified in the Subcontract Particulars;

subject to subparagraph (iii), not replace the people referred to in subparagraph (i) without the Consultant's Representative's prior written approval; and

if any of the people referred to in subparagraph (i) die, become seriously ill or resign from the employment of the Subconsultant, replace them with persons approved by the Consultant's Representative of at least equivalent experience, ability and expertise.

A direction is deemed to be given to the Subconsultant if it is given to the Subconsultant’s Representative.

Removal of Persons

The Consultant's Representative may by notice in writing instruct the Subconsultant to remove any person from the Site or the Subcontract Services who in the reasonable opinion of the Consultant's Representative is guilty of misconduct or is incompetent or negligent.

The Subconsultant must ensure that this person is not again involved in the Subcontract Services.

Monthly Meeting

The Subconsultant must:

meet monthly (or at such other times as the Consultant's Representative may require) with the Consultant's Representative and any other persons whom the Consultant's Representative nominates;

discuss the report it has prepared under clause 4.7 and such other matters as the Consultant's Representative may from time to time require;

promptly and fully respond to any questions which the Consultant's Representative asks in relation to any report; and

if it requires instructions from the Consultant, make all necessary recommendations with respect to the instructions required.

The Consultant's Representative must:

before each meeting:

prepare an agenda for the meeting; and

issue an agenda for the meeting; and

after each meeting:

prepare minutes of the meeting; and

issue minutes of the meeting.

Subconsultant’s Monthly Report

At least 7 days prior to each meeting under clause 4.6, the Subconsultant must provide the Consultant’s Representative with a monthly report in such form as the Consultant’s Representative requires from time to time and which must include, at a minimum:

detailed particulars of the progress of the Subcontract Services and the Works including:

key activities, meetings and other events in the previous month;

the status of all Design Documentation (including any alternative solutions or dispensations being pursued);

the status of all Approvals;

photographs of the Subcontract Services and the Works; and

any deviations from the Subconsultant’s then current program under clause 8.2;

detailed particulars of all:

payment claims, payment statements and payments;

Variation Price Requests, responses, Variation Orders and proposed adjustments to the Fee;

written claims and notices given and received under clause 8 in respect of delays and extensions of time;

other Claims made by the Subconsultant (including in respect of Statutory Requirements and the resolution of ambiguities under clause 6.10);

calls, attendances, recommendations and actions taken in respect of non-conforming Subcontract Services (in accordance with clause 7.3);

calls, attendances, recommendations and actions taken in respect of all Defects (or similar term used or defined in the Construction Contract);

disputes under clause 13; and

notices under clause 14.1 or 14.2;

detailed particulars of any risks, opportunities, issues or matters which in the Subconsultant’s opinion:

are significantly impacting; or

have the potential to significantly impact,

the Subcontract Services or the Works (in terms of time, cost or quality) and the preventative and remedial action which has been, is being or is proposed to be taken in respect of such risks, opportunities, issues or matters;

confirmation of compliance with the WHS Legislation and detailed particulars of all work health and safety matters arising out of or in connection with clause 6.15, including:

the Work Health and Safety Plan (including all reviews, updates and amendments to the Work Health and Safety Plan in accordance with clause 7.4);

details of all proactive risk management measures implemented by the Subconsultant to prevent systemic work health and safety issues, incidents or accidents during the Subcontract Services;

written assurances from the Subconsultant and each Other Contractor confirming their ongoing compliance with the WHS Legislation in accordance with clause 6.15(e)(ii)A;

details of lead indicator data, including:

inductions, training and other work health and safety awareness programmes conducted;

Site audits and verification activities (including copies of Site audit reports and verification activity reports); and

inspections of Plant, Equipment and Work (or similar term used or defined in the Construction Contract);

without limiting the Subconsultant’s obligations to notify the DSC Contract Administrator and the Consultant’s Representative under:

clause 6.15(c)(i) and (d), summary data regarding notifiable incidents, including any notices issued to or from the relevant regulator, copies of all witness statements and investigation reports, actions to be taken and any impact on the Subcontract due to the notifiable incident;

clause 6.15(c)(ii), work health and safety incidents or accidents (which are not notifiable incidents) where the nature of the incident or accident indicates a potential systemic failure to identify hazards and manage risks to health and safety and the preventative, corrective and remedial action which has been, is being or is proposed to be taken; and

clause 6.15(c)(iii), details of all incidents and accidents (which are not notifiable incidents) and the preventative, corrective and remedial action which has been, is being or is proposed to be taken;

relevant statistics and other information regarding lost time injury days; and

all other work health and safety matters required by the Subcontract or the Consultant’s Representative;

confirmation of compliance with, and (as applicable) an update in respect of:

quality assurance requirements, including the Quality Plan;

Site-related requirements, including the Site Management Plan;

commissioning and handover requirements, including the Project Lifecycle and HOTO Plan;

environmental requirements, including the Environmental Management and Sustainability Plan;

information security requirements, including clause 18; and

any other security requirements,

together with detailed particulars of all matters relevant to the items described in subparagraphs (i) - (vi) above;

in respect of Hazardous Substances (if any) any information as required by the Special Conditions, including providing all ChemAlert Information and any subsequent updates to the ChemAlert Information;

such information as the Consultant's Representative may reasonably require to enable the Consultant to comply with its obligations under the Environmentally Sustainable Procurement Policy (as published on https://www.finance.gov.au/government/procurement/buying-australian-government/procurement-connected-policies); and

any other matters required by the Consultant’s Representative.

Insurance

Subconsultant Insurance Obligations

The Subconsultant must:

from the Award Date cause to be effected and maintained or otherwise have the benefit of the following insurance:

Public Liability Insurance;

Workers Compensation Insurance;

if the Subcontract Services are performed, or the Subconsultant's employees perform work, are employed or normally reside, in any jurisdiction outside Australia, Employers' Liability Insurance;

Professional Indemnity Insurance; and

such other insurances on such terms as are specified in the Subcontract Particulars,

each of which must be:

for the amounts specified in the Subcontract Particulars;

with insurers having a Standard and Poors, Moodys, A M Best, Fitch's or equivalent rating agency's financial strength rating of A- or better; and

on terms which are satisfactory to the Consultant's Representative (confirmation of which must not be unreasonably withheld or delayed);

in relation to the Public Liability Insurance, ensure the insurance:

names the Consultant as a party to whom the benefit of the insurance cover extends; and

is not subject to any worldwide or jurisdictional limits which might limit or exclude the jurisdictions in which the Subcontract Services are being carried out;

in relation to the Workers Compensation Insurance and Employers’ Liability Insurance, ensure that, to the extent permitted by law the insurance extends to provide indemnity to the Commonwealth as the Consultant's principal and the Consultant in respect of any statutory and common law liability to the Subconsultant's employees;

in relation to the Professional Indemnity Insurance, ensure the insurance:

has a retroactive date of no later than the commencement of the Subcontract Services; and

is not subject to any worldwide or jurisdictional limits which might limit or exclude the jurisdictions in which the Subcontract Services are being carried out;

promptly provide the Consultant's Representative with evidence satisfactory to the Consultant's Representative that:

it has complied with clause 5.1; and

each insurance required under clause 5.1 is current and complies with clause 5.1,

as required by the Consultant's Representative from time to time;

ensure that:

if the insurer gives the Subconsultant notice of expiry, cancellation or rescission of any required insurance policy, the Subconsultant as soon as possible informs the Consultant in writing that the notice has been given and effects replacement insurance as required by the Subcontract and informs the Consultant's Representative in writing as soon as possible of the identity of the replacement insurer, and provides such evidence as the Consultant's Representative reasonably requires that the replacement insurance complies in all relevant respects with the requirements of the Subcontract; and

if the Subconsultant cancels, rescinds or fails to renew any required insurance policy, the Subconsultant as soon as possible obtains replacement insurance as required by the Subcontract and informs the Consultant in writing as soon as possible of the identity of the replacement insurer, and provides such evidence as the Consultant's Representative reasonably requires that the replacement insurance complies in all relevant respects with the requirements of the Subcontract;

ensure that it:

does not do or omit to do anything whereby any insurance may be prejudiced;

complies at all times with the terms of each insurance policy;

if necessary, takes all possible steps to rectify any situation which might prejudice any insurance;

punctually pays all premiums and other amounts payable in connection with all of the required insurance policies, and gives the Consultant's Representative copies of receipts for payment of premiums upon request by the Consultant's Representative;

renews any required insurance policy if it expires during the relevant period, unless appropriate replacement insurance is obtained;

immediately notifies the Consultant's Representative (in writing) if the Subconsultant fails to renew any required insurance policy or pay a premium;

does not cancel or allow an insurance policy to lapse during the period for which it is required by the Subcontract without the prior written consent of the Consultant's Representative;

immediately notifies the Consultant's Representative (in writing) of any event which may result in a required insurance policy lapsing, being cancelled or rescinded;

complies fully with its duty of disclosure and obligations of utmost good faith toward the insurer and in connection with all of the required insurance policies;

does everything reasonably required by the Consultant's Representative, the Consultant and the DSC Contract Administrator to enable the Consultant and the Commonwealth to claim and to collect or recover money due under any of the insurances in respect of which they are required to have the benefit of coverage under this Subcontract; and

maintains full and appropriate records of incidents relevant to any insurance claim for a period of 10 years from the date of the claim; and

bear the excess applicable to any insurance claim made under any of the insurance policies required to be maintained by the Subconsultant under this clause 5.1.  Any excess borne by the Consultant will be a debt due from the Subconsultant to the Consultant.

For the purpose of paragraph (e), such evidence may include certificates of currency (no more than 20 days old), current policy wordings (except where such insurances are prescribed by Statutory Requirement) and written confirmation from a relevant insurer or reputable broker stating that the relevant insurance is current and complies with clause 5.1.

The obtaining of insurance as required under clause 5.1 will not in any way limit, reduce or otherwise affect any of the obligations, responsibilities and liabilities of the Subconsultant under the Subcontract or otherwise at law or in equity.

Consultant Insurance Obligations

The Consultant must:

from the Award Date cause to be effected and maintained or otherwise have the benefit of the insurance (if any) specified in the Subcontract Particulars; and

promptly provide the Subconsultant with evidence satisfactory to the Subconsultant that the insurance required under subparagraph (i) are current, as required by the Subconsultant from time to time.

The insurance referred to in paragraph (a) is subject to the exclusions, conditions and excesses noted on the policy or policies and the Subconsultant must:

satisfy itself of the nature and extent of the Consultant's insurance; and

if required by the Subconsultant, take out insurance to:

insure any risks not insured by the Consultant's insurance; or

cover any such exclusions, conditions or excesses in that insurance,

- which the Subconsultant wants to insure against or cover.

Failure to Insure

If the Subconsultant fails to comply with clause 5.1, the Consultant may (in its absolute discretion and without prejudice to any other rights it may have) take out the relevant insurance and the cost of such insurances will be a debt due from the Subconsultant to the Consultant.

The Subconsultant must take all necessary steps to assist the Consultant in exercising its discretion under paragraph (a).  For the purpose of this paragraph (b), "all necessary steps" includes providing all relevant information and documents (including insurance proposals), answering questions, co-operating with and doing everything necessary to assist the Consultant’s Representative or anyone else acting on behalf of the Consultant.

Period of Insurance

The insurance which the Subconsultant is required to cause to be effected and maintained or otherwise have the benefit of under clause 5.1 and the insurance the Consultant is required to cause to be effected and maintained or otherwise have the benefit of under clause 5.2 must be maintained:

in the case of Public Liability Insurance:

written on an occurrence basis, until the completion of the Subcontract Services; or

written on a claims made basis, until the expiration of the run-off period specified in the Subcontract Particulars following the latest of the:

end of the last Defects Liability Period (as defined in the Construction Contract); and

completion of the Subcontract Services;

in the case of Workers Compensation Insurance and Employers' Liability Insurance, until the latest of the:

end of the last Defects Liability Period (as defined in the Construction Contract); and

completion of the Subcontract Services; and

in the case of Professional Indemnity Insurance, until the expiration of the run-off period specified in the Subcontract Particulars following the latest of the:

end of the last Defects Liability Period (as defined in the Construction Contract); and

completion of the Subcontract Services.

Notice of Potential Claim

The Subconsultant must:

as soon as possible inform the Consultant in writing of any fact, matter or occurrence that may give rise to a claim under an insurance policy required under clause 5.1 or any claim actually made against the Subconsultant or the Consultant which may be covered by an insurance policy required by clause 5.1;

keep the Consultant informed of all significant developments concerning the claim, except in circumstances where the Consultant is making a claim against the Subconsultant,

provided that, in respect of Professional Indemnity Insurance, the Subconsultant:

subject to paragraph (d), is not required to provide details of individual claims; and

must notify the Consultant if the estimated total combined value of claims made against the Subconsultant and claims which may arise from circumstances reported by the Subconsultant to its insurer in a policy year would potentially reduce the available limit of policy indemnity for that year below the amount required by the Subcontract.

Cross Liability

Clause 5.6 does not apply to Professional Indemnity Insurance or Workers Compensation Insurance.

Where the Subcontract requires insurance to provide cover to more than one insured, the Subconsultant must ensure that, to the extent permitted by law, the insurance policy provides that:

the insurer agrees to treat each insured as a separate insured as though a separate contract of insurance had been entered into with each insured, without increasing the overall limit of indemnity;

the insurer will not impute to any insured any knowledge or intention or a state of mind possessed or allegedly possessed by any other insured;

the insurer waives all rights, remedies or relief to which it might become entitled by subrogation against any of the parties to whom the benefit of insurance cover extends and that failure by any insured to observe and fulfil the terms of the policy will not prejudice the insurance in regard to any other insured;

a notice to the insurer by one insured will be deemed to be notice on behalf of all insureds; and

the insurer agrees not to reduce or exclude the insurance cover of an insured because the:

liability of the insured is limited by the operation of the proportionate liability legislation of any Australian jurisdiction; or

proportionate liability legislation of any Australian jurisdiction is lawfully excluded by the contract.

Insurances Secondary

The Consultant is not obliged to make a claim or institute proceedings against any insurer under the insurances before enforcing any of its rights or remedies under the indemnities referred to in this Subcontract or generally.

The Subconsultant is not relieved from and remains fully responsible for its obligations and liabilities in accordance with this Subcontract and at law regardless of whether the insurances respond or fail to respond to any claim and regardless of the reason why any insurance responds or fails to respond.

Exclusion of Consequential Loss and Limitation on Liability

Subject to paragraphs (b) and (c):

neither the Consultant nor the Subconsultant will be liable to the other for any Consequential Loss howsoever arising; and

to the extent permitted by law, the maximum aggregate liability of the Subconsultant to the Consultant arising out of or in connection with the Subcontract (whether arising in contract, in equity, tort (including negligence), by way of indemnity, under statute or otherwise at law) is limited to the amount specified in the Subcontract Particulars.

Paragraph (a) does not apply to a liability of the Subconsultant:

for any deliberate breach or repudiation of the Subcontract;

under the indemnities in clauses 1.3(f)(i), 6.8(b), 16.5(a)(xii) and 18.5(b);

for Fraud;

to the extent that:

payments are received by the Subconsultant; or

the Subconsultant is entitled to be indemnified (other than in circumstances where the relevant insurer is insolvent),

- under any insurance policy or policies required to be effected and maintained under the Subcontract in relation to that liability or payments would have been received by the Subconsultant or the Subconsultant would have been entitled to be indemnified under such insurance policy or policies but for:

the failure of the Subconsultant to effect and maintain the required insurance policy or insurance policies;

any failure of an insurance policy to respond due to the misconduct of the Subconsultant (including a misrepresentation to the insurer or failure to make proper disclosure or to comply with the requirements of the policy);

the failure by the Subconsultant to diligently pursue any claim for indemnity under any insurance policy or insurance policies; or

the reliance by the insurer of the required insurance on this clause 5.8 to deny liability on the basis that the party has no liability to the Consultant; and

for fines or penalties incurred by the Consultant arising from the Subcontract Services.

Paragraph (a)(i) does not apply to a liability of the Consultant for:

any deliberate breach or repudiation of the Subcontract;

Fraud; or

fines or penalties incurred by the Subconsultant arising from an act or omission of the Consultant.

For the purposes of this clause 5.8, Consequential Loss means any loss of income, loss of revenue, loss of profit, loss of financial opportunity, loss of business or loss of business opportunity, loss of goodwill, loss of use (other than loss of use of the Works or other Commonwealth property) or loss of production or financing costs, whether present or future, fixed or unascertained, actual or contingent.

DESIGN AND Documentation

Subconsultant's Documentation Program

The Subconsultant must as part of the program it is to prepare under clause 8.2, submit to the Consultant's Representative for approval a documentation program which makes allowance for the Design Documentation to be submitted to the Consultant's Representative in a manner and at a rate which will give the Consultant's Representative a reasonable opportunity to review the Design Documentation within the period of time within which the Consultant's Representative may review the Design Documentation under clause 6.3.

Subconsultant's Design

The Subconsultant must:

design the parts of the Works which the Subcontract requires it to design in accordance with the Brief, the Preliminary Design Solution and the other requirements of the Subcontract and for this purpose (but without limitation) prepare all relevant Design Documentation;

conduct design reviews at each of the Milestones identified in the Brief; and

submit the Design Documentation it prepares to the Consultant's Representative in accordance with the documentation program approved by the Consultant's Representative under clause 6.1.

Consultant's Representative May Review Design Documentation

The Consultant's Representative may (in its absolute discretion):

review any Design Documentation, or any resubmitted Design Documentation, prepared and submitted by the Subconsultant; and

within the number of days specified in the Subcontract Particulars of the submission by the Subconsultant of such Design Documentation or resubmitted Design Documentation, reject the Design Documentation.

If any Design Documentation is rejected, the Subconsultant must submit amended Design Documentation to the Consultant's Representative.

No Obligation to Review

Without limiting the Consultant’s obligations and liability to the Commonwealth under the Design Services Contract:

the Consultant's Representative does not assume or owe any duty of care to the Subconsultant to review, or in reviewing, the Design Documentation submitted by the Subconsultant for errors, omissions or compliance with the Subcontract; and

no review of, comments upon, consent to or rejection of, or failure to review or comment upon or consent to or reject, any Design Documentation prepared by the Subconsultant or any other direction by the Consultant's Representative about, or any other act or omission by the Consultant's Representative or otherwise by or on behalf of the Consultant in relation to, the Design Documentation will:

relieve the Subconsultant from, or alter or affect, the Subconsultant's obligations under the Subcontract or otherwise at law or in equity; or

prejudice the Consultant's rights against the Subconsultant whether under the Subcontract or otherwise at law or in equity.

Copies of Design Documentation

For the purposes of clauses 6.2(c) and 6.3, the Subconsultant must submit or resubmit to the Consultant's Representative the number of copies specified in the Subcontract Particulars of Design Documentation in:

hard copy; and

electronic copy,

in accordance with the requirements specified in the Subcontract Particulars.

Licence over Project Documents

The Subconsultant grants to the Consultant a perpetual, royalty-free, irrevocable, non-exclusive, worldwide licence to exercise all rights of the owner of the Intellectual Property Rights in the Project Documents, including to use, re-use, reproduce, communicate to the public, modify and adapt any of the Project Documents.

The licence referred to in paragraph (a):

arises, for each Project Document, immediately when the Project Document is:

produced; or

provided, or required to be provided, to the Consultant or the Consultant's Representative,

- under, for the purposes of, arising out of or in connection with the Subcontract, the Subcontract Services or the Works by, for or on behalf of the Subconsultant;

includes an unlimited right to sub-licence;

without limitation, extends to:

any subsequent occupation, use, operation and maintenance of or additions, alterations or repairs to the Works; and

in the case of the corresponding licence granted by the Consultant to the Commonwealth - use in any way for any other Commonwealth project; and

survives the termination of the Subcontract on any basis.

Intellectual Property Warranties

The Subconsultant warrants that:

the Subconsultant owns all Intellectual Property Rights in the Project Documents or, to the extent that it does not, is entitled to grant the assignments and licences contemplated by the Subcontract;

use by the Consultant or any sublicensee or subsublicensee of the Project Documents in accordance with the Subcontract will not infringe the rights (including Intellectual Property Rights and Moral Rights) of any third party;

neither the Consultant nor any sublicensee or subsublicensee is liable to pay any third party any licence or other fee in respect of the use of the Project Documents, whether by reason of Intellectual Property Rights or Moral Rights of that third party or otherwise; and

the use by the Consultant or by any sublicensee or subsublicensee of the Project Documents in accordance with the Subcontract will not breach any laws (including any laws in respect of Intellectual Property Rights and Moral Rights).

Intellectual Property Rights

The Subconsultant must:

ensure that the Subcontract Services do not infringe any patent, registered design, trade mark or name, copyright, Moral Rights or other protected right; and

indemnify the Consultant in respect of all claims against, and costs, losses, damages, or liabilities suffered or incurred by the Consultant arising out of or in connection with any actual or alleged infringement of any patent, registered design, trade mark or name, copyright, Moral Rights or other protected right.

Consultant Material

The Consultant Material will remain the property of the Consultant.

The Consultant must inform the Subconsultant of any Consultant Material in which third parties hold the copyright and of any conditions attaching to the use of that material because of that copyright. The Subconsultant may use that material only in accordance with those conditions.

Without limiting clause 18, the Subconsultant will be responsible for the protection, maintenance and return of the Consultant Material in its possession.

Resolution of Ambiguities

If there is any ambiguity, discrepancy or inconsistency in the documents which make up the Subcontract or between the Subcontract and any Design Documentation or any other Project Document:

subject to paragraphs (b) and (c), the order of precedence specified in the Subcontract Particulars will apply;

where the ambiguity, discrepancy or inconsistency is between the Brief and any other requirement of the Contract (including any other requirement of the Brief), the greater, higher or more stringent requirement, standard, level of service or scope (as applicable) will prevail;

where the ambiguity, discrepancy or inconsistency is between the Subcontract and any part of the Design Documentation or any other Project Document, the higher standard, quality or quantum will prevail but if this does not resolve the ambiguity, discrepancy or inconsistency, the Subcontract will prevail; and

irrespective of whether paragraphs (a) to (c) apply, if it is discovered by:

the Subconsultant or the Consultant, then the party discovering it must promptly give the Consultant’s Representative and the other party notice in writing. After receipt of a notice from a party the Consultant's Representative must, within 14 days of receipt of the notice, instruct the Subconsultant as to the course it must adopt; or

the Consultant's Representative, then the Consultant's Representative must promptly give the parties notice in writing together with an instruction to the Subconsultant as to the course it must adopt,

- including, where applicable, by applying the principles in paragraphs (a) to (c) above.

Access to Premises and Project Documents

The Subconsultant must:

at the request of the Commonwealth or the Consultant's Representative at any time during the Subcontract Services and the period of 10 years following the latest of the:

end of the last Defects Liability Period (as defined in the Construction Contract); and

completion of the Subcontract Services,

provide and make available:

access to its premises and make the Project Documents available for inspection by the Consultant's Representative or anyone else acting on behalf of the Commonwealth or the Consultant;

such copies of the Project Documents as the Consultant's Representative or anyone else acting on behalf of the Commonwealth or the Consultant may require, in such formats as may be required;

all such facilities and assistance, answer all questions of, co-operate with and do everything necessary to assist the Consultant's Representative or anyone else acting on behalf of the Commonwealth or the Consultant; and

any officers, employees or agents for interviews with the Consultant's Representative or anyone else acting on behalf of the Commonwealth or the Consultant; and

within the time required by the Consultant's Representative prior to Completion (as defined in the Construction Contract), deliver to the Consultant's Representative a copy of the installed version of each item of software comprising the IT Equipment incorporated in the Works or the Stage (as defined in the Construction Contract) in a storage medium reasonably satisfactory to the Consultant, together with a copy of all documentation, including licence terms, warranty terms and operating manuals associated with each item of such software.

Measurements and Dimensions

Unless expressly stated to the contrary in the Subcontract or directed by the Consultant's Representative:

the Subconsultant must obtain and check all relevant measurements and dimensions on the Site before proceeding with the Subcontract Services;

the layout of plant, equipment, duct work, pipework and cabling shown in the Brief (if any) is to be taken as diagrammatic only and all measurements and dimensions information concerning the Site required to carry out the Subcontract Services must be obtained and checked by the Subconsultant; and

to the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with the Subconsultant's failure to obtain and check measurements and dimension information concerning the Site as required by clause 6.12.

Design Certification

Without limiting the Consultant's obligations to the Commonwealth under the Design Services Contract and the Subconsultant's obligations under the Subcontract or otherwise at law or in equity, the Subconsultant must, with each submission of Design Documentation under clause 6.2, payment claim under clause 11.2 and prior to Completion (as defined in the Construction Contract), provide the Consultant's Representative with a certificate in the form of the Subconsultant Design Certificate which certifies that (to the extent then applicable):

the Design Documentation complies with:

subject to clause 2.10(a), all Statutory Requirements (including the WHS Legislation); and

the requirements of the Subcontract; and

the Works comply or the Stage (as defined in the Construction Contract) complies with the Design Documentation which has not been rejected by the Consultant's Representative under clause 6.3,

except to the extent set out in such certificate.

Samples

The Subconsultant must:

obtain each sample or range of samples required by the Subcontract; and

submit the sample or range of samples it obtains to the Consultant's Representative in accordance with the program it is to prepare under clause 8.2.

The Consultant's Representative may:

review the sample or range of samples, or any resubmitted sample or range of samples, submitted by the Subconsultant; and

within the number of days specified in the Subcontract Particulars of the submission of such sample or range of samples or resubmitted sample or range of samples, reject the sample or range of samples if, in the reasonable opinion of the Consultant's Representative, the sample or range of samples does not comply with the requirements of the Subcontract.

If any sample or range of samples is rejected, the Subconsultant must submit an amended or substituted sample or range of samples to the Consultant's Representative.

Without limiting the Consultant’s obligations and liability to the Commonwealth under the Design Services Contract:

the Consultant's Representative does not assume or owe any duty of care to the Subconsultant to review, or in reviewing, the sample or range of samples submitted by the Subconsultant for errors, omissions or compliance with the Subcontract; and

no review of, comments upon, consent to or rejection of, or failure to review or comment upon or consent to or reject, any sample or range of samples submitted by the Subconsultant or any other direction by the Consultant's Representative about, or any other act or omission by the Consultant's Representative or otherwise by or on behalf of the Consultant in relation to, the sample or range of samples will:

relieve the Subconsultant from, or alter or affect, the Subconsultant's obligations whether under the Subcontract or otherwise at law or in equity; or

prejudice the Consultant’s rights against the Subconsultant under the Subcontract or otherwise at law or in equity.

Work Health and Safety

The Subconsultant must:

ensure that in carrying out the Subcontract Services:

it complies with all Statutory Requirements and other requirements of the Subcontract in respect of work health and safety, including the applicable WHS Legislation;

where the applicable WHS Legislation does not prescribe a duty referred to in this Subcontract as one the Subconsultant must comply with, it complies with the duty contained in the Commonwealth WHS Legislation;

it complies with the duty under the WHS Legislation to consult, co-operate and co-ordinate activities with all other persons who have a work health and safety duty in relation to the same matter;

it complies with the duty under the WHS Legislation to notify the relevant regulator immediately upon becoming aware that a notifiable incident (within the meaning of the WHS Legislation) has occurred arising out of its business or undertaking; and

it complies with the duty under the WHS Legislation to, where a notifiable incident has occurred, to ensure, so far as is reasonably practicable, that the site where the notifiable incident has occurred is not disturbed until an inspector arrives at the site or any earlier time that an inspector directs, unless:

it is to assist an injured person or remove a deceased person;

it is to make the area safe or to minimise the risk of a further notifiable incident; or

the relevant regulator/inspector has given permission to disturb the site;

carry out the Subcontract Services to ensure the health and safety of persons is not put at risk;

without limiting the Subconsultant’s obligations under the Subcontract or otherwise at law or in equity, notify the Consultant's Representative and the DSC Contract Administrator in respect of:

notifiable incidents within the meaning of the WHS Legislation, immediately;

work health and safety incidents or accidents (which are not notifiable incidents) where the nature of the incident or accident indicates a potential systemic failure to identify hazards and manage risks to health and safety, so far as is reasonably practicable, within 24 hours of the incident or accident occurring; and

all other work health and safety matters arising out of or in connection with the Subcontract Services, including the occurrence of any other incident or accident (not required to be reported in accordance with subparagraphs (i) or (ii)), in the reports under clause 4.7;

for the purposes of paragraphs (a)(iv) and (c) above, in respect of any notifiable incident:

immediately provide the Consultant's Representative and the DSC Contract Administrator with a copy of the notice required to be provided to the relevant Commonwealth, State or Territory regulator;

promptly provide the Consultant's Representative and the DSC Contract Administrator with a copy of all witness statements and the investigation report relating to the notifiable incident;

promptly provide the Consultant's Representative and the DSC Contract Administrator with copies of any notice(s) or other documentation issued by the relevant Commonwealth, State or Territory regulator; and

within 10 days of the date of notification to the relevant Commonwealth, State or Territory regulator, provide the Consultant's Representative and the DSC Contract Administrator with a summary of the related investigations, actions to be taken, and any impact on the Subcontract that may result from the notifiable incident;

institute systems to:

obtain regular written assurances from each Other Contractor about their ongoing compliance with the WHS Legislation; and

provide, in a format specified by the Consultant's Representative, the written assurances regarding the Subconsultant’s ongoing compliance with the WHS Legislation:

on a monthly basis in the reports under clause 4.7;

on a quarterly basis (when requested by the Consultant's Representative); and

as otherwise directed by the Consultant's Representative;

provide the written assurances obtained under paragraph (e) to the Consultant's Representative in accordance with paragraph (e);

without limiting the Subconsultant’s obligations under the Subcontract or otherwise at law or in equity within 10 days of receipt provide to the Consultant's Representative copies of all:

formal notices and written communications issued by a regulator or agent of the regulator under or in compliance with the applicable WHS Legislation to the Subconsultant relating to work health and safety matters;

formal notices issued by a health and safety representative of the Subconsultant under or in compliance with the applicable WHS Legislation; and

formal notices, written communications and written undertakings given by the Subconsultant to the regulator or agent of the regulator under or in compliance with the applicable WHS Legislation,

arising out of or in connection with the Subcontract Services;

exercise a duty of the utmost good faith to the Consultant and the Commonwealth in carrying out the Subcontract Services to enable the Consultant and the Commonwealth to discharge their duties under the WHS Legislation;

ensure that, if any Statutory Requirement requires that:

a person:

be authorised or licensed (in accordance with the WHS Legislation) to carry out any work at that workplace, that person is so authorised or licensed, and complies with any conditions of such authorisation or licence; or

has prescribed qualifications or experience, or if not, is to be supervised by a person who has prescribed qualifications or experience (as defined in the WHS Legislation), that person has the required qualifications or experience or is so supervised; or

a workplace, plant or substance (or design), or work (or class of work) be authorised or licensed, that workplace, plant or substance, or work is so authorised or licensed;

not direct or allow a person to carry out work, or use plant or a substance (or design) at a workplace unless the authorisation, licensing, prescribed qualifications or experience required by any Statutory Requirement and paragraph (i) are met;

immediately notify the Consultant's Representative and the DSC Contract Administrator giving full particulars, so far as they are known to it, upon becoming aware of any intention on the part of a regulatory authority to cancel, revoke, suspend or amend an authorisation relating to work health and safety;

without limiting the Subconsultant’s obligations under the Subcontract (including paragraph (d) in respect of notifiable incidents) or otherwise at law or in equity, within 10 days of a request by the Consultant's Representative, the DSC Contract Administrator or anyone else acting on behalf of the Commonwealth or the Consultant, provide all information or copies of documentation held by the Subconsultant to the Consultant's Representative, the DSC Contract Administrator or anyone else acting on behalf of the Consultant or the Commonwealth to enable the Consultant and the Commonwealth to comply with their obligations under the WHS Legislation;

if requested by the Consultant's Representative or required by the WHS Legislation, produce evidence of any Approvals including any authorisations, licences, registrations, prescribed qualifications or experience, or any other information relevant to work health and safety to the satisfaction of the Consultant's Representative before the Subconsultant commences such work;

where the Subconsultant is a supplier, manufacturer, designer or importer for the purposes of the WHS Legislation, provide to the Consultant's Representative prior to Completion (as defined in the Construction Contract) and before the expiry of the Defects Liability Period (as defined in the Construction Contract) information concerning:

the purpose for which any plant, structure or substance (as defined in the WHS Legislation) has been designed or manufactured;

the results of any calculations, analysis, testing or examination carried out concerning the safety of the plant, substances or structures referred to in subparagraph (i) (and the risks to the health and safety of persons); and

any conditions necessary to ensure the plant, substances or structures are without risks to health and safety when used for the purpose for which they were designed or manufactured;

ensure that the Design Documentation eliminates or minimises the need for any hazardous manual tasks to be carried out in connection with a plant or structure;

prior to each submission of Design Documentation under clause 6.2, it:

reviews the Asbestos Management Plan and the Defence Asbestos Register; and

ensures that the design addresses all Asbestos related risks identified in its review performed in accordance with subparagraph (i);

not use Asbestos or ACM in carrying out the Subcontract Services;

ensure that the Design Documentation does not provide for Asbestos or ACM to be used in (or incorporated into) the Works;

with each submission of Design Documentation under clause 6.2, provide the Consultant's Representative with a certificate in a form satisfactory to the Consultant's Representative which states that:

all materials, goods, products, equipment and plant (including any imported materials, goods, products, equipment and plant) described in the Design Documentation to be used in (or incorporated into) the Works are entirely (meaning 100%) free of Asbestos and ACM; and

the Subconsultant has otherwise complied with all Statutory Requirements in relation to Asbestos and ACM in carrying out the Subcontract Services;

without limiting paragraph (s), if any imported materials, goods, products, equipment and plant described in the Design Documentation are to be used in (or incorporated into) the Works, the Subconsultant must provide to the Consultant's Representative with each submission of Design Documentation under clause 6.2:

sample test reports; and

test report information, in the form of an analysis certificate from a NATA accredited laboratory or an equivalent international laboratory (listed at the NATA website) accredited for the relevant test method,

in relation to the imported materials, goods, products, equipment or plant to be used in (or incorporated into) the Works; and

if the Subconsultant is a designer of a structure (or part of a structure) for the purposes of the WHS Legislation, the Subconsultant must provide to the Consultant's Representative with each submission of Design Documentation under clause 6.2, a written report that specifies the hazards relating to the design of the structure (or part) which, as far as the Subconsultant is reasonably aware:

create a risk to health or safety to those carrying out construction work on the structure (or part); and

are associated only with that particular design.

Quality

Quality Assurance

The Subconsultant:

must implement the quality assurance process, system or framework in its Quality Plan;

without limiting clause 6.11, must allow the Consultant's Representative or anyone else acting on behalf of the Consultant access to the quality assurance process, system or framework of the Subconsultant so as to enable auditing or other monitoring; and

will not be relieved from compliance with its obligations under the Subcontract or otherwise at law or in equity as a result of:

the implementation of, and compliance with, the quality assurance requirements of the Subcontract;

any direction by the Consultant's Representative concerning the Subconsultant’s quality assurance process, system or framework or its compliance or non-compliance with the quality assurance process, system or framework;

any audit or other monitoring by the Consultant's Representative or anyone else acting on behalf of the Consultant of the Subconsultant’s compliance with the process, system or framework; or

any failure by the Consultant's Representative, or anyone else acting on behalf of the Consultant, to detect any Subcontract Services which are not in accordance with the requirements of the Subcontract including where any such failure arises from any negligence on the part of the Consultant's Representative or other person.

Non-Complying Subcontract Services

If the Consultant's Representative discovers or believes that any Subcontract Services have not been performed in accordance with the Subcontract, the Consultant's Representative may give the Subconsultant a direction specifying the non-complying Subcontract Services and doing one or more of the following:

requiring the Subconsultant to:

reperform the non-complying Subcontract Services and specifying the time within which this must occur; and

take all such steps as are reasonably necessary to:

mitigate the effect on the Consultant of the failure to carry out the Subcontract Services in accordance with the Subcontract; and

put the Consultant (as closely as possible) in the position in which it would have been if the Subconsultant had carried out the Subcontract Services in accordance with the Subcontract; or

advising the Subconsultant that the Consultant will accept the non-complying Subcontract Services despite the non-compliance.

Reperformance of the Non-complying Subcontract Services

If a direction is given under clause 7.2(a), the Subconsultant must reperform the non-complying Subcontract Services:

within the time specified in the Consultant's Representative's direction; and

if after the Date for Completion, so as to minimise the delay and disruption to the Subcontract Services or the Works.

Project Plans

The Subconsultant:

must carry out the Subcontract Services in accordance with, and otherwise implement, the Project Plans; and

for the purposes of subparagraph (i), must:

prepare Project Plans based, where applicable, on the draft Project Plans lodged by the Subconsultant in its tender for the Subcontract Services, and otherwise in accordance with the requirements of the Subcontract and submit them to the Consultant's Representative so as to ensure that there is no delay or disruption to the Subcontract Services and in any event no later than the number of days specified in the Subcontract Particulars after the Award Date for each Project Plan;

not commence any of the Subcontract Services to which any Project Plan applies, unless the Consultant's Representative has had the number of days specified in the Subcontract Particulars for each Project Plan to review the Project Plan and has not rejected the Project Plan;

if any Project Plan is rejected, submit an amended Project Plan to the Consultant's Representative;

in any event, finalise each Project Plan so as to ensure that there is no delay or disruption to the Subcontract Services and in any event in accordance with the requirements of the Subcontract to the satisfaction of the Consultant's Representative;

after each Project Plan has been finalised:

regularly review, update and amend each Project Plan in accordance with the process set out in each Project Plan and otherwise at least:

a)	on each anniversary of the Award Date; and

b)	if clause 9 applies, prior to the Date for Delivery Phase Agreement;

update or amend a Project Plan on request of the Consultant's Representative; and

continue to correct any defects in or omissions from a Project Plan (whether identified by the Consultant's Representative or the Subconsultant),

and submit an updated or amended Project Plan to the Consultant's Representative, after which:

the Subconsultant must continue to comply with the requirements of the then current Project Plan until the process in subparagraph (ii) has been completed in respect of the updated or amended Project Plan; and

subsubparagraphs B - E will apply (to the extent applicable); and

document and maintain detailed records of all:

reviews, updates, amendments and submissions of each Project Plan;

audits or other monitoring of each Project Plan; and

training and awareness programs and communications provided to Subconsultant personnel in respect of each Project Plan (including each updated or amended Project Plan).

The Consultant must promptly provide the Subconsultant with a copy of amendments to any Consultant's Project Plan insofar as they are relevant to the Subcontract Services or a Project Plan.

The Subconsultant will not be relieved from compliance with any of its obligations under the Subcontract or otherwise at law or in equity as a result of:

the implementation of, and compliance with, the requirements of any Project Plan;

any direction by the Consultant's Representative concerning a Project Plan or the Subconsultant's compliance or non-compliance with a Project Plan;

any audit or other monitoring by the Consultant's Representative or anyone else acting on behalf of the Consultant of the Subconsultant's compliance with a Project Plan; or

any failure by the Consultant's Representative, or anyone else acting on behalf of the Consultant, to detect any defect in or omission from a Project Plan including where any such failure arises from any negligence on the part of the Consultant's Representative or other person.

Drawings

Without limiting the Subconsultant's obligations under the Subcontract or otherwise at law or in equity, all drawings which the Subconsultant is required to provide under the Subcontract must be prepared by competent draftspersons in accordance with:

the standard prescribed in the Subcontract (or, to the extent it is not so prescribed, a standard consistent with the best industry standard for drawings of a nature similar to those required for the Works);

all Statutory Requirements; and

the directions of the Consultant’s Representative.

Time

Progress

The Subconsultant must:

regularly and diligently progress the Subcontract Services; and

subject to clause 8.10, achieve Completion of each Milestone by its Date for Completion.

Programming

The Consultant must:

on the Award Date, provide the Subconsultant with a copy of the Consultant's Program insofar as it is relevant to the Subcontract Services; and

thereafter, promptly provide the Subconsultant with a copy of amendments to the Consultant's Program insofar as they are relevant to the Subcontract Services.

The Subconsultant must:

within 14 days of the Award Date, prepare a program of the Subcontract Services which must:

be based upon the Consultant's Program and otherwise developed based on the initial program lodged by the Subconsultant in its tender for the Subcontract Services (as may be updated prior to the Award Date with the approval of the Consultant); and

contain the details required by the Subcontract or which the Consultant's Representative otherwise reasonably directs;

update the program:

periodically, at least at intervals of no less than that specified in the Subcontract Particulars, to take account of:

changes to the program;

changes to the Consultant's Program;

delays which may have occurred, including any for which the Subconsultant is granted an extension of time under clause 8.8; and

if clause 9 applies (and without limiting subsubparagraph A), prior to the Date for Delivery Phase Agreement for any changes in the Delivery Phase Subcontract Services and submit the updated program to the Consultant's Representative by no later than the date notified in writing by the Consultant's Representative;

give the Consultant's Representative copies of all programs; and

provide all programs in a format compatible with the software specified in the Subcontract Particulars.

The Consultant's Representative may review and comment on any program given under this clause 8.2.

Subconsultant Not Relieved

Any review of, comment upon, or any failure to review or comment upon, a program by the Consultant's Representative will not:

relieve the Subconsultant from or alter its obligations under the Subcontract especially (without limitation) the obligation to achieve Completion of each Milestone by its Date for Completion;

evidence or constitute the granting of an extension of time or an instruction by the Consultant's Representative to accelerate, disrupt, prolong or vary any, or all, of the Subcontract Services; or

affect the time for the carrying out of the Consultant's or Consultant's Representative's Subcontract obligations.

Suspension

The Consultant's Representative:

may instruct the Subconsultant to suspend and, after a suspension has been instructed, to re-commence, the carrying out of all or a part of the Subcontract Services; and

is not required to exercise the Consultant's Representative's power under subparagraph (i) for the benefit of the Subconsultant.

If a suspension under clause 8.4 arises as a result of:

the Subconsultant's failure to carry out its obligations in accordance with the Subcontract, to the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with the suspension; or

a cause other than the Subconsultant's failure to carry out its obligations in accordance with the Subcontract, an instruction to suspend under clause 8.4 will entitle the Subconsultant to:

an extension of time to any relevant Date for Completion where it is otherwise so entitled under clause 8.8; and

have the Fee increased by the extra costs reasonably incurred by the Subconsultant as a direct result of the suspension, as determined by the Consultant's Representative.

The Subconsultant must take all steps possible to mitigate any extra costs incurred by it as a direct result of the suspension. To the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with the suspension, other than under paragraph (b)(ii).

Except to the extent permitted by the relevant Security of Payment Legislation, the Subconsultant may only suspend the Subcontract Services when instructed to do so under clause 8.4.

Delays Entitling Claim in Extension of Time

If the Subconsultant becomes aware of any occurrence that is likely to delay it in carrying out the Subcontract Services it must, as soon as practicable, and in any event within 14 days of becoming aware, inform the Consultant's Representative in writing of the occurrence and the likely delay.

If the Subconsultant has been delayed in carrying out the Subcontract Services:

prior to the Date for Completion of a Milestone by an Act of Prevention or a Pandemic Adjustment Event in a manner which has delayed, or is likely to delay, the Consultant in achieving Completion of the Milestone; or

after the Date for Completion of a Milestone by an Act of Prevention in a manner which has delayed, or is likely to delay, the Consultant in achieving Completion of the Milestone,

- the Subconsultant may claim an extension of time.

Claim for Extension of Time

To claim an extension of time, the Subconsultant must:

not later than 28 days after the commencement of the delay, submit a written claim to the Consultant's Representative for an extension to the relevant Date for Completion, which:

gives detailed particulars of the delay and the occurrence causing the delay; and

states the number (not exceeding 28) of days extension of time claimed together with the basis of calculating that period, including evidence that it has been, or is likely to be, delayed in achieving Completion in the manner set out in clause 8.5(b)(i) or 8.5(b)(ii); and

if the delay continues beyond 28 days from the commencement of that delay, and the Subconsultant wishes to claim an extension of time in respect of any further period, submit a further written claim to the Consultant's Representative:

every 28 days after the last date for submitting the first written claim, provided however that the final written claim must be submitted not later than 7 days after the end of the delay; and

containing the information required by paragraph (a).

Conditions Precedent to Extension

It is a condition precedent to the Subconsultant’s entitlement to an extension of time that the:

Subconsultant must give the written claim required by clause 8.6 as required by that clause;

cause of the delay was beyond the reasonable control of the Subconsultant;

Subconsultant must have actually been, or be likely to be, delayed in the manner set out in clause 8.5(b)(i) or 8.5(b)(ii); and

Subconsultant must not have been given a direction under clause 8.10(a) with which it has been able to comply.

Extension of Time

If the conditions precedent in clause 8.7 have been satisfied, the relevant Date for Completion will be extended by a reasonable period determined by the Consultant's Representative and notified to the Consultant and the Subconsultant within 21 days of the Subconsultant's written claim under clause 8.6(a) or 8.6(b) as applicable.

In determining a reasonable period under paragraph (a), the Consultant's Representative must not include any period of delay in respect of which the Subconsultant:

contributed to the delay; or

failed to take all steps necessary both to preclude the cause of the delay and to avoid or minimise the extent of the delay.

Unilateral Extension of Time

Whether or not the Subconsultant has made, or is entitled to make, a claim for an extension of time under clause 8, the Consultant may (in its absolute discretion) at any time and from time to time by written notice to the Subconsultant and the Consultant's Representative, unilaterally extend any Date for Completion.

The Subconsultant acknowledges that clause 8.9 does not give the Subconsultant any rights.

Acceleration

The Consultant's Representative may (in its absolute discretion) at any time and from time to time, by written notice to the Subconsultant require the Subconsultant to use its best endeavours to achieve a Milestone by a date earlier than the Date for Completion (Accelerated Date for Completion).

If a direction is given by the Consultant's Representative under paragraph (a), the Subconsultant must:

use its best endeavours to:

accelerate the performance of the Subcontract Services; and

otherwise do all things necessary,

to achieve Completion of the Milestone by the Accelerated Date for Completion; and

keep the Consultant's Representative fully and regularly informed of the progress of the Subcontract Services against the Accelerated Date for Completion.

The Subconsultant will be entitled to have the Fee increased by the extra costs reasonably incurred by the Subconsultant as a direct result of complying with paragraph (b).

To the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with a direction by the Consultant's Representative under paragraph (a), other than under paragraph (c).

If the Subconsultant does not achieve Completion of a Milestone by its Accelerated Date for Completion, the Subconsultant must nevertheless:

use its best endeavours to accelerate the performance of the Subcontract Services and otherwise do all things necessary to achieve Completion of the Milestone as soon as possible after the Accelerated Date for Completion; and

in any event, achieve Completion of the Milestone no later than its Date for Completion.

Prolongation

If a Prolongation Event occurs:

either:

if clause 9 applies, after the date on which the Consultant issues a notice under clause 9.4(a); or

if clause 9 does not apply, after the Award Date;

which causes, or is likely to cause, a Material Adverse Effect;

which is not caused or contributed to by an act or omission of the Subconsultant (including any failure by the Subconsultant to perform the Subcontract Services in accordance with the Subcontract); and

in circumstances where the Subconsultant has done everything it is required to do under the Subcontract to prevent or mitigate the effect of the Prolongation Event,

- the Subconsultant may submit a "Prolongation Proposal" to the Consultant's Representative within 14 days of the date on which the Subconsultant becomes aware, or should reasonably have become aware, of the Prolongation Event, which sets out:

full details of the Prolongation Event;

the Material Adverse Effect directly caused by the Prolongation Event, which must be demonstrated by the Subconsultant on a fully open book cost transparent basis; and

the Subconsultant's proposal to address the Prolongation Event, including all possible steps to mitigate the cost and other effects of the Prolongation Event and provide the Consultant with value for money.

If the Prolongation Proposal submitted by the Subconsultant under paragraph (a):

demonstrates that a Prolongation Event has occurred which has caused a Material Adverse Effect, and otherwise complies with paragraph (a), then the Consultant's Representative must give the Subconsultant a written response within 20 days of the Prolongation Proposal being received by the Consultant's Representative, stating that the Consultant:

accepts the Prolongation Proposal;

requires the Subconsultant to submit an amended Prolongation Proposal having regard to the matters stated in the Consultant's response to the Prolongation Proposal, after which this paragraph (b) will reapply; or

requires a meeting with the Subconsultant to negotiate the Prolongation Proposal having regard to the matters stated in the Consultant's response; or

does not:

demonstrate that a Prolongation Event has occurred which has caused a Material Adverse Effect; or

comply with paragraph (a),

- then the:

Consultant's Representative may give the Subconsultant a written notice rejecting the Prolongation Proposal; and

Subconsultant will not be entitled to bring any Claim against the Consultant arising out of or in connection with the Prolongation Proposal.

If the Consultant's Representative notifies the Subconsultant that the Consultant requires a meeting to negotiate the Prolongation Proposal under paragraph (b)(i)C, then:

the parties must undertake good faith negotiations (and exchange such documents and information and make available such people as may be necessary) to agree the costs payable to the Subconsultant as a result of the Prolongation Event; and

if the parties are unable to agree an amount under subparagraph (i) within 40 days of the Prolongation Proposal being received by the Consultant's Representative (or such longer period as the Consultant's Representative and the Subconsultant may agree), the Subconsultant will be entitled to the reasonable extra costs incurred by the Subconsultant as a result of the Material Adverse Effect after the date of the Subconsultant's "Prolongation Proposal" under paragraph (a) as determined by the Consultant's Representative.

To the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with a Prolongation Event, other than under this clause 8.11.

Notwithstanding the existence of a Prolongation Event, the Subconsultant must:

continue to carry out the Subcontract Services; and

otherwise comply with its obligations under the Subcontract.

PLANNING PHASE AND DELIVERY PHASE

Clause 9 applies unless the Subcontract Particulars state that it does not apply.

Planning Phase and Delivery Phase

The Subconsultant acknowledges and agrees that the Consultant has divided the Subcontract Services into two distinct phases, being the:

Planning Phase; and

subject to this clause 9, Delivery Phase.

The Subconsultant acknowledges and agrees that the purpose of this division is to:

allow for various departmental, government, parliamentary and other approvals required for the Works to be achieved;

enable the Consultant to be satisfied (in its absolute discretion) that it will maximise value for money for the Commonwealth and the Consultant to have the Subconsultant proceed with the Delivery Phase Subcontract Services; and

give the Consultant an opportunity to elect (in its absolute discretion) not to proceed with the Subconsultant to the Delivery Phase.

The Subconsultant acknowledges and agrees that, as a result of the matters described in paragraph (b):

there may not be a Delivery Phase;

even if there is Delivery Phase, the Subconsultant may not be engaged to carry out the Delivery Phase Subcontract Services; and

there may be periods of inactivity of various durations in and between the Planning Phase and Delivery Phase, whether as a result of a delay in any notice or direction under clause 9.2, 9.3, 9.4 or otherwise. Such periods of inactivity will not amount to a suspension under clause 8.4 and, to the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with such periods of inactivity.

Notwithstanding paragraph (c)(iii), the Subconsultant must ensure that, in and between the Planning Phase and Delivery Phase, it retains appropriate, suitably qualified personnel available to perform the Subcontract Services required by the Consultant.

Updated Delivery Phase Fee Proposal

Prior to the Date for Delivery Phase Agreement, the Subconsultant must prepare and submit to the Consultant's Representative for approval an Updated Delivery Phase Fee Proposal for the Delivery Phase Subcontract Services, which is based on the Delivery Phase Fee Proposal and must, as a minimum:

include a resource schedule for the Delivery Phase Subcontract Services, which is based on the minimum resource schedule included in the Delivery Phase Fee Proposal, and identifies in detail:

the Delivery Phase Subcontract Services which an expert professional provider of the Subcontract Services would anticipate and provide for in its resource schedule for the Delivery Phase Subcontract Services (including identifying in detail all changes (if any) to the Delivery Phase Subcontract Services required as a result of design development, cost planning and programming carried out in the Planning Phase);

all changes (if any) to the resources required for the Delivery Phase Subcontract Services as a result of:

changes (if any) to the Delivery Phase Subcontract Services identified in subsubparagraph A; or

otherwise, design development, cost planning and programming carried out in the Planning Phase;

identify in detail:

proposed adjustments (if any) to the:

Indicative Delivery Phase Fee, including a detailed cost breakdown of each part or discipline of the Delivery Phase Subcontract Services and all disbursements; and

Fee Payment Schedule (if a Fee Payment Schedule applies in the Delivery Phase) including, if payments will be monthly in the Delivery Phase, a detailed explanation of proposed adjustments (if any) to cashflow for the Delivery Phase (for evaluation and cost planning purposes only); and

how the Subconsultant has calculated the adjustment (if any) to the Indicative Delivery Phase Fee and Fee Payment Schedule (if any) by reference to the Delivery Phase Fee Proposal;

be prepared having regard to all relevant considerations, including:

the Delivery Phase Fee Proposal (including the minimum resource schedule);

the paramount importance to the Commonwealth and the Consultant of balancing between minimising the cost of the Subcontract Services and achieving Completion (on the one hand) and optimising the level of resources provided by the Subconsultant for the performance of the Delivery Phase Subcontract Services (on the other hand);

demonstrably maximising value for money for the Commonwealth and the Consultant and complying with the Commonwealth Procurement Rules; and

all other relevant considerations, arising out of or in connection with or reasonably incidental to or to be inferred from the considerations in subsubparagraphs A - C, which the Consultant's Representative may from time to time notify to the Subconsultant in writing; and

include all such other matters as the Consultant's Representative may require in writing.

Following the submission of the Updated Delivery Phase Fee Proposal under paragraph (a), the Subconsultant must undertake genuine and good faith negotiations with the Consultant's Representative to reach agreement as to the matters set out in the Updated Delivery Phase Fee Proposal, including:

the resource schedule for the Delivery Phase Subcontract Services and details contemplated in clause 9.2(a)(i);

the adjustment (if any) to the Indicative Delivery Phase Fee, as a result of any design development, cost planning and programming carried out by the Subconsultant in the Planning Phase; and

if a Fee Payment Schedule applies in the Delivery Phase, the adjustment (if any) required to the Fee Payment Schedule,

- in each case having regard to the Delivery Phase Fee Proposal and, in the case of the adjustment (if any) to the Indicative Delivery Phase Fee, the Table of Variation Rates and Prices.

The Subconsultant must:

if any Updated Delivery Phase Fee Proposal submitted by the Subconsultant is rejected by the Consultant's Representative (in the Consultant's Representative's absolute discretion), promptly submit a revised Updated Delivery Phase Fee Proposal; and

take all possible steps necessary to ensure that the proposed Delivery Phase Fee in its Updated Delivery Phase Fee Proposal does not exceed the Indicative Delivery Phase Fee, including all such reasonable steps directed by the Consultant's Representative.

Approval (or otherwise) of Updated Delivery Phase Fee Proposal

If agreement is reached on all of the matters in clause 9.2(b) and the Consultant's Representative (in its absolute discretion) approves any Updated Delivery Phase Fee Proposal (or revised Updated Delivery Phase Fee Proposal) submitted by the Subconsultant in accordance with clause 9.2(a) or 9.2(c)(i) (as the case may be), then the Consultant's Representative will:

record the agreement and approval in the form of minutes set out in the Schedule of Collateral Documents (Delivery Phase Agreement Minutes), including the resource schedule for the Delivery Phase Subcontract Services, the lump sum Delivery Phase Fee and any Fee Payment Schedule for the Delivery Phase; and

provide the finalised Delivery Phase Agreement Minutes to the Subconsultant.

The Subconsultant acknowledges that, for the purpose of determining whether or not to approve any Updated Delivery Phase Fee Proposal (or revised Updated Delivery Phase Fee Proposal) submitted by the Subconsultant in accordance with clause 9.2(a) or 9.2(c)(i) (as the case may be), the:

Consultant's Representative may engage a third party to perform an external audit of any Updated Delivery Phase Fee Proposal (or revised Updated Delivery Phase Fee Proposal); and

Subconsultant must:

co-operate with the Consultant's Representative and any third parties required by the Consultant's Representative;

provide such other documents and information as the Consultant's Representative may require for the purposes of such external audit under subparagraph (i); and

provide such other documents and information as the Consultant's Representative may require.

If agreement is not reached on all of the matters in clause 9.2(b), and the Consultant's Representative (in its absolute discretion) does not approve any Updated Delivery Phase Fee Proposal (or revised Updated Delivery Phase Fee Proposal), prior to the Date for Delivery Phase Agreement, then the Consultant may (in its absolute discretion) elect to issue a notice under clause 9.4(b).

If the Consultant's Representative provides finalised Delivery Phase Agreement Minutes to the Subconsultant under paragraph (a)(ii):

the Subconsultant must sign the Delivery Phase Agreement Minutes and return them to the Consultant's Representative by the date required by the Consultant's Representative;

the Consultant will execute the Delivery Phase Agreement Minutes on the same day that it issues a notice under clause 9.4(a); and

subject to clause 9.4, the parties' rights and obligations under the Subcontract will be subject to the matters agreed, as recorded in the Delivery Phase Agreement Minutes.

Notice to Proceed (or not Proceed) with Delivery Phase Subcontract Services

If the Subconsultant has signed and returned the Delivery Phase Agreement Minutes to the Consultant's Representative under clause 9.3(d), the Consultant may (in its absolute discretion) elect to issue a notice in writing directing the Subconsultant to proceed with the Delivery Phase Subcontract Services and the Subconsultant must immediately commence to perform the Delivery Phase Subcontract Services.

If:

various departmental, government, parliamentary and other approvals required for the Works are not achieved;

clause 9.3(c) applies;

the Consultant is not satisfied (in its absolute discretion) that it will maximise value for money for the Commonwealth and the Consultant to have the Subconsultant proceed with the Delivery Phase Subcontract Services; or

the Consultant has elected (in its absolute discretion) not to proceed with the Subconsultant to the Delivery Phase,

- then the Consultant may (in its absolute discretion) elect to issue a notice in writing directing the Subconsultant not to proceed with the Delivery Phase Subcontract Services.

If the Consultant issues a notice under paragraph (b), the Subconsultant:

will be entitled to payment of the Planning Phase Fee due and payable for the Planning Phase Subcontract Services completed in accordance with the Subcontract before the issue of the notice;

will not be entitled to:

perform the Delivery Phase Subcontract Services; or

payment of the Delivery Phase Fee or any other portion of the Fee;

to the extent permitted by law, will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with the notice, the Subcontract or the Delivery Phase Subcontract Services, other than for the amount payable under subparagraph (i); and

must:

comply with clause 18.4 (including by handing over to the Consultant's Representative copies of Project Documents prepared by the Subconsultant before the issue of the notice (whether complete or not));

co-operate with the Consultant, the Consultant's Representative and any third parties required by the Consultant's Representative;

provide such other documents and information as the Consultant's Representative may require; and

take all other steps necessary to ensure that the Consultant is able to re-tender or procure the performance of the Delivery Phase Subcontract Services.

If the Consultant issues a notice under paragraph (b), the Consultant may (in its absolute discretion):

re-tender the performance of the Delivery Phase Subcontract Services (whether with or without obtaining a tender from the Subconsultant) or procure the performance of the Delivery Phase Subcontract Services in any other manner which the Consultant may (in its absolute discretion) determine; and

use the Project Documents for the purpose of re-tendering or procuring the performance of the Delivery Phase Subcontract Services under subparagraph (i).

The issue of a notice under paragraph (b) will not limit or affect the Subconsultant's obligations or liabilities under the Subcontract nor prejudice the right of the Consultant to exercise any right or remedy (including recovery of damages, whether while electing to keep the Subcontract on foot or after termination) which it may have where the Subconsultant breaches the Subcontract, whether under the Subcontract or otherwise at law or in equity.

The Consultant may (in its absolute discretion) at any time and from time to time unilaterally extend the Date for Delivery Phase Agreement by notice in writing to the Subconsultant. The Subconsultant acknowledges that paragraph (f) does not give the Subconsultant any rights.

VariationS

Variation Price Request

At any time prior to completion of the Subcontract Services, the Consultant's Representative may issue a document titled "Variation Price Request" to the Subconsultant which will set out details of a proposed Variation which the Consultant is considering.

Within 14 days of the receipt of a Variation Price Request (or such longer period as may be agreed by the Consultant's Representative), the Subconsultant must provide the Consultant's Representative with a written notice in which the Subconsultant sets out the:

adjustment (if any) to the Fee to carry out the proposed Variation; and

effect (if any) which the proposed Variation will have on the then current program, including each Date for Completion.

Variation Order

- Whether or not the Consultant's Representative has issued a "Variation Price Request" under clause 10.1, the Consultant's Representative may, at any time prior to completion of the Subcontract Services, instruct the Subconsultant to carry out a Variation by a written document titled "Variation Order", in which the Consultant's Representative will state one of the following:

the proposed adjustment to the Fee set out in the Subconsultant's notice under clause 10.1 (if any) is agreed and the Fee will be adjusted accordingly; or

any adjustment to the Fee will be determined under clauses 10.3(b) and 10.3(c).

- No Variation will invalidate the Subcontract irrespective of the nature, extent or value of the work the subject of the Variation.

Valuation of Variation

The Fee will be increased or decreased for all Variations which have been the subject of a direction by the Consultant's Representative:

as agreed under clause 10.2(a);

if paragraph (a) does not apply, in accordance with the rates and prices included in the Table of Variation Rates and Prices, if and insofar as the Consultant's Representative determines that those rates and prices are applicable to or it is reasonable to use them for valuing the Variation; or

to the extent paragraphs (a) and (b) do not apply, by a reasonable amount:

agreed between the parties; or

failing agreement, determined by the Consultant's Representative.

Table of Variation Rates and Prices

Where the rates and prices in the Table of Variation Rates and Prices are used under clause 10.3(b), the rates and prices will be deemed to cover:

all labour, materials, overheads and profit related to the work the subject of the Variation and compliance with the Subconsultant’s obligations under the Subcontract; and

all costs which will be incurred by the Subconsultant arising out of or in connection with the Variation.

Omissions

If a Variation the subject of a direction by the Consultant's Representative omits any part of the Subcontract Services, the Consultant may thereafter carry out this omitted work either itself or by engaging Other Contractors.

Payment

Payment Obligation

Subject to clause 11.11 and to any other right to set-off which the Consultant may have, the Consultant will pay the Subconsultant:

the Fee; and

any other amounts which are payable by the Consultant to the Subconsultant under the Subcontract.

Payment Claims

The Subconsultant must give the Consultant's Representative claims for payment on account of the Fee and all other amounts then payable by the Consultant to the Subconsultant under the Subcontract:

at the times specified in the Subcontract Particulars until completion of the Subcontract Services or termination of the Subcontract (whichever is earlier);

unless terminated earlier, after completion of the Subcontract Services, within the time required by clause 11.7;

in the format set out in the Schedule of Collateral Documents or in any other format which the Consultant's Representative reasonably requires;

which are based on the Table of Variation Rates and Prices to the extent it is relevant;

which show separately the amounts (if any) claimed on account of:

the Fee; and

all other amounts then payable by the Consultant to the Subconsultant under the Subcontract; and

which set out or attach sufficient details, calculations, supporting documentation and other information in respect of all amounts claimed by the Subconsultant:

to enable the Consultant's Representative to fully and accurately determine (without needing to refer to any other documentation or information) the amounts then payable by the Consultant to the Subconsultant under the Subcontract; and

including any such documentation or information which the Consultant's Representative may by written notice from time to time require the Subconsultant to set out or attach, whether in relation to a specific payment claim or all payment claims generally.

Certification to Accompany Submission of Payment Claim

- The Subconsultant must, with each payment claim submitted under clause 11.2, certify to the Consultant's Representative that it has:

if an election or request has been made under clause 2.12, complied with clause 2.12;

complied with clause 5.1;

complied with clause 6.13;

complied with clause 6.15;

complied with clause 8.2;

complied with clause 11.12;

complied with clause 11.16; and

complied with clause 21.

Payment Statement

The Consultant's Representative:

must, within 10 business days of receiving a payment claim submitted or purported to be submitted in accordance with clause 11.2; or

may, if the Subconsultant fails to submit any such claim in accordance with clause 11.2, at any time,

give the Subconsultant (with a copy to the Consultant), on behalf of the Consultant, a payment statement which is in the form set out in the Schedule of Collateral Documents and which states:

the payment claim to which it relates (if any);

the amount previously paid to the Subconsultant on account of the Fee and otherwise in accordance with the Subcontract;

the amount (if any) which the Consultant's Representative believes to be then payable by the Consultant to the Subconsultant on account of the Fee and otherwise in accordance with the Subcontract and which the Consultant proposes to pay to the Subconsultant; and

if the amount in paragraph (e) is less than the amount claimed in the payment claim:

the reason why the amount in paragraph (e) is less than the amount claimed in the payment claim; and

if the reason for the difference is that the Consultant has retained, deducted, withheld or set-off payment for any reason, the reason for the retention, deduction, withholding or setting-off.

Any evaluation, or issue of a payment statement, by the Consultant's Representative will not constitute:

approval of any Subcontract Services nor will it be taken as an admission or evidence that the part of the Subcontract Services covered by the payment statement has been satisfactorily carried out in accordance with the Subcontract;

a waiver of the requirements of clauses 11.2 and 11.3 in relation to any payment claim other than to the extent (if any) to which the Consultant expressly waives such requirements in respect of the payment claim the subject of the payment statement;

an admission or evidence of the value of the Subcontract Services or that the Subcontract Services comply with the Subcontract;

an admission or evidence of liability; or

otherwise, any approval, admission or evidence by the Consultant or the Consultant's Representative of the Subconsultant’s performance or compliance with the Subcontract.

Payment

Within 3 business days of the Subconsultant receiving a payment statement under clause 11.4, the Subconsultant must give the Consultant's Representative, with a copy to the email address set out in the Subcontract Particulars, a tax invoice for the amount stated as then payable by the Consultant to the Subconsultant in the payment statement.

Subject to clause 11.13(c), within the number of business days specified in the Subcontract Particulars of the Consultant receiving a payment statement under clause 11.4, the Consultant will pay the Subconsultant the amount stated as then payable by the Consultant to the Subconsultant in the payment statement.

Payment on Account

Any payment of moneys under clause 11.5 will not constitute:

approval of the Subcontract Services nor will it be taken as an admission or evidence that the part of the Subcontract Services covered by the payment has been satisfactorily carried out in accordance with the Subcontract;

a waiver of the requirements of clauses 11.2 and 11.3 in relation to any payment claim other than to the extent (if any) to which the Consultant expressly waives such requirements in respect of the payment claim the subject of the payment;

an admission or evidence of the value of the Subcontract Services or that the Subcontract Services comply with the Subcontract;

an admission or evidence of liability; or

otherwise, any approval, admission or evidence by the Consultant or the Consultant's Representative of the Subconsultant’s performance or compliance with the Subcontract,

but is only to be taken as payment on account.

Completion Payment Claim and Notice

Within 28 days (or such longer period agreed in writing by the Consultant's Representative) of completion of the Subcontract Services, the Subconsultant must give the Consultant's Representative:

a payment claim which complies with clause 11.2 and which must include all amounts which the Subconsultant claims from the Consultant on account of the Fee and all other amounts payable under the Subcontract; and

notice of any other amounts which the Subconsultant claims from the Consultant,

- in respect of any fact, matter or thing arising out of or in connection with the Subcontract Services or the Subcontract which occurred prior to completion of the Subcontract Services.

The payment claim and notice required under paragraph (a) are in addition to the other notices which the Subconsultant must give to the Consultant's Representative under the Subcontract in order to preserve its entitlements to make any such Claims.

Without limiting the previous paragraph, the Subconsultant cannot include in this payment claim or notice any Claims which are barred by clause 14.5.

Release after Completion Payment Claim and Notice

After the date for submitting the payment claim and notice under clause 11.7 has passed, the Subconsultant releases the Consultant from any Claim in respect of any fact, matter or thing arising out of or in connection with the Subcontract Services or the Subcontract which occurred prior to completion of the Subcontract Services, except any Claim:

included in a payment claim or notice under clause 11.7 which is given to the Consultant's Representative within the time required by, and in accordance with the terms of, clause 11.7; or

directly arising as a result of a Claim made by a third party against the Subconsultant which could not have been reasonably foreseen by the Subconsultant at the time of submitting the payment claim and notice under clause 11.7.

Interest

The Consultant will pay simple interest at the rate specified in the Subcontract Particulars on any:

amount stated as then payable by the Consultant in a payment statement under clause 11.4, but which is not paid by the Consultant within the time required by the Subcontract; and

damages.

This will be the Subconsultant’s sole entitlement to interest including damages for loss of use of, or the cost of borrowing, money.

Correction of Payment Statements

The Consultant's Representative may, in any payment statement:

correct any error in any previous payment statement; and

modify any previous payment statement,

given by the Consultant's Representative.

Right of Set-Off

The Consultant may:

deduct from moneys otherwise due to the Subconsultant:

any debt or other moneys due from the Subconsultant to the Consultant; and

any claim to money which the Consultant asserts in good faith against the Subconsultant whether for damages or otherwise under the Subcontract or otherwise at law or in equity arising out of or in connection with the Subcontract Services or the Works; and

without limiting paragraph (a), deduct any debt, other moneys due or any claim to money referred to in paragraph (a)(i) or (a)(ii) from any amount which may be or thereafter become payable to the Subconsultant by the Consultant in respect of any Variation the subject of a Variation Order under clause 10.2.

Payment of Workers

The Subconsultant must with each payment claim submitted under clause 11.2 provide the Consultant's Representative with a duly completed declaration in the form set out in the payment claim (in the format set out in the Schedule of Collateral Documents) for each applicable jurisdiction in which the Subcontract Services were carried out during the relevant period.

GST

Subject to paragraph (b), where any supply arises out of or in connection with the Subcontract or the Subcontract Services for which GST is not otherwise provided, the party making the supply (Supplier) will be entitled to increase the amount payable for the supply by the amount of any applicable GST.

Where an amount is payable to the Supplier for a supply arising out of or in connection with the Subcontract or the Subcontract Services which is based on the actual or reasonable costs incurred by the Supplier, the amount payable for the supply will be reduced by the amount of any input tax credits available to the Supplier (or a representative member on the Supplier's behalf) in respect of such costs before being increased for any applicable GST under paragraph (a).

As a condition precedent to any amount on account of GST being due from the recipient to the Supplier in respect of a taxable supply, the Supplier must provide a tax invoice to the recipient in respect of that supply.

If the amount paid to the Supplier in respect of the GST (whether because of an adjustment or otherwise):

is more than the GST on the supply, then the Supplier shall refund the excess to the recipient; or

is less than the GST on the supply, then the recipient shall pay the deficiency to the Supplier.

In clause 11.13, subject to clause 1.1, terms defined in GST Legislation have the meaning given to them in GST Legislation.

Security of Payment Legislation

The Subconsultant agrees with the Consultant that:

a payment claim submitted to the Consultant's Representative under clause 11.2 which also purports to be (or is at law) a payment claim under the relevant Security of Payment Legislation is received by the Consultant's Representative as agent for the Consultant;

the Consultant's Representative will give payment statements and carry out all other functions of the Consultant under the relevant Security of Payment Legislation as the agent of the Consultant (without affecting the Consultant's right to carry out those functions itself);

to the extent permitted by and for the purposes of the relevant Security of Payment Legislation, the "reference dates" are those of the dates prescribed in clauses 11.2(a) and 11.2(b) on which the Subconsultant has satisfied the requirements of clause 11.3; and

a reference to a "payment statement" is also a reference to a "payment schedule" for the purposes of the relevant Security of Payment Legislation.

Failure by the Consultant's Representative to state in a payment statement issued under the relevant Security of Payment Legislation or otherwise an amount which the Consultant is entitled to retain, deduct, withhold or set-off from the amount which would otherwise then be payable by the Consultant to the Subconsultant will not prejudice:

the Consultant's Representative's ability or power to state in a subsequent payment statement an amount which the Consultant is entitled to retain, deduct, withhold or set-off from the amount which would otherwise then be payable by the Consultant to the Subconsultant; or

the Consultant's right to subsequently exercise its right to retain, deduct, withhold or set-off any amount under the Subcontract or otherwise at law or in equity.

The Subconsultant agrees that the amount stated in the payment statement as then payable by the Consultant to the Subconsultant under clause 11.4 is, subject to clause 11.12, to the extent permitted by and for the purposes of the relevant Security of Payment Legislation, the amount of the "progress payment" calculated in accordance with the terms of the Subcontract and which the Subconsultant is entitled to be paid in respect of the Subcontract.

The Subconsultant irrevocably chooses the person specified in the Subcontract Particulars as, to the extent permitted by and for the purposes of the relevant Security of Payment Legislation, and to the extent that the relevant Subcontract Services are to be carried out in:

the Northern Territory, the appointed adjudicator or, where there is no appointed adjudicator, the prescribed appointer;

Western Australia, the appointed adjudicator or the adjudicator (as the case may be) or, where there is no appointed adjudicator or adjudicator, the prescribed appointor or authorised nominating authority (as the case may be); or

any other State or Territory (other than Queensland) in which Security of Payment Legislation applies, the authorised nominating authority.

The Subconsultant must not at any time, without the written consent of the Consultant, divulge or suffer or permit its servants or agents to divulge to any person any communication, submission or statement made or evidence or information used by or relied upon by the Consultant or any details thereof in respect of an adjudication application made under the relevant Security of Payment Legislation (in this paragraph, the Information).

- For the avoidance of doubt:

to the extent permitted by law, the Subconsultant's obligations in respect of the Information apply to any subsequent proceedings before a court, arbitrator, expert or tribunal;

notwithstanding the Subconsultant's obligations in respect of the Information, the Consultant has absolute discretion to divulge or permit its servants, subconsultants or agents to divulge to any person the Information;

the Consultant may divulge or permit its servants, subconsultants or agents to divulge to any person any communication, submission or statement made or evidence or information used by or relied upon by the Subconsultant or any details thereof in respect of an adjudication application made under the relevant Security of Payment Legislation; and

any Information which the Consultant provides or relies upon in respect of an adjudication application made under the relevant Security of Payment Legislation is made without prejudice to the Consultant's right to vary, modify, supplement or withdraw the Information in any subsequent proceedings before a court, arbitrator, expert or tribunal.

Accounting Records

The Subconsultant must keep accurate and up to date accounting records including books of account, labour time sheets, invoices for materials, plant hire, final accounts and any other documents or papers which show all details in relation to:

all Variations; and

without limiting paragraph (a), all amounts paid to the Subconsultant on account of the Fee and otherwise in accordance with the Subcontract.

Cost Allocation Advice

Without limiting clause 11.2, for the purposes of assisting the Commonwealth to report on an accrual basis, the Subconsultant must with each payment claim under clause 11.2, provide the Consultant's Representative with accurate information which apportions monthly costs against buildings, infrastructure and expenses for all Subcontract Services completed since the Consultant’s previous payment to the Subconsultant.

Facilities and Infrastructure Accounting

Without limiting clause 11.2, for the purposes of assisting the Commonwealth to bring all completed facilities and infrastructure to account, prior to Completion (as defined in the Construction Contract), the Subconsultant must provide a cost report to the Consultant's Representative which sets out:

details of the Fee and all other amounts payable under the Subcontract paid by the Consultant to the Subconsultant in respect of the Works or a Stage (as defined in the Construction Contract);

the matters specified in the Subcontract Particulars; and

any other matters required by the Consultant's Representative.

Fee Payment Schedule

- If the Fee is adjusted under the Subcontract and a Fee Payment Schedule applies, the Fee Payment Schedule will be adjusted:

as agreed between the parties; or

failing agreement, as determined by the Consultant's Representative.

Termination

Preservation of Rights

Subject to clause 12.6, nothing in clause 12 or that the Consultant does or fails to do pursuant to clause 12 will prejudice any right or remedy of the Consultant (including the recovery of damages) where the Subconsultant breaches (including repudiates) the Subcontract.

Subconsultant Default

The Consultant may give a written notice under clause 12.3 to the Subconsultant if the Subconsultant is in breach of the Subcontract.

Contents of Notice of Default

A notice under clause 12.3 must state:

that it is a notice under clause 12.3;

the failure or breach relied upon; and

that the Consultant requires the Subconsultant to remedy the failure or breach within the number of days specified in the Subcontract Particulars of receiving the notice.

Termination for Insolvency or Breach

If:

an Insolvency Event occurs to the Subconsultant or, where the Subconsultant comprises two or more persons, to any one of those persons;

the Subconsultant does not remedy a failure or breach the subject of a notice under clause 12.3 within the number of days specified in the Subcontract Particulars of receiving the notice under clause 12.3;

a direction has been given under clause 7.2, the Subconsultant fails to comply with clause 7.3; or

the Subconsultant fails to comply with any of clauses 16.13(b)(i), 16.13(b)(ii), 16.16, 18 or 19,

then the Consultant may by written notice to the Subconsultant immediately (and without having to first give a notice under clause 12.3 (except in the case of paragraph (b)) terminate the Subcontract.

Consultant's Entitlements after Termination by Consultant

Subject to clause 12.1, if the Consultant terminates the Subcontract under clause 12.4 or if the Subconsultant repudiates the Subcontract and the Consultant otherwise terminates the Subcontract:

the Consultant will:

to the extent permitted by the relevant Security of Payment Legislation, not be obliged to make any further payments to the Subconsultant, including any amount the subject of a payment claim under clause 11.2 or a payment statement under clause 11.4; and

be entitled to recover from the Subconsultant all costs, expenses, losses, damages or liabilities suffered or incurred by the Consultant arising out of or in connection with such termination; and

the Subconsultant must comply with clause 18.4 (including by handing over to the Consultant's Representative copies of Project Documents prepared by the Subconsultant to the date of termination (whether complete or not)).

Clause 12.5 will survive the termination of the Subcontract.

Subconsultant's Entitlements after Termination by Subconsultant

If the Consultant repudiates the Subcontract and the Subconsultant terminates the Subcontract, the Subconsultant will:

be entitled to payment of an amount determined in accordance with clause 12.8 as if the Consultant had terminated the Subcontract under clause 12.7; and

not be entitled to a quantum meruit.

Clause 12.6 will survive the termination of the Subcontract.

Termination for Convenience

Without prejudice to any right or remedy of the Consultant under the Subcontract or otherwise at law or in equity, the Consultant may:

at any time for its sole convenience, and for any reason, by written notice to the Subconsultant terminate the Subcontract effective from the time stated in the Consultant’s notice or if no such time is stated, at the time the notice is given to the Subconsultant; and

thereafter (at its absolute discretion), complete the uncompleted part of the Subcontract Services either itself or by engaging Other Contractors.

Subconsultant’s Entitlements after Termination for Convenience by Consultant

If the Consultant terminates the Subcontract under clause 12.7, the Subconsultant:

will be entitled to payment of the following amounts, as determined by the Consultant's Representative:

for Subcontract Services carried out prior to the date of termination, the amount which would have been payable if the Subcontract had not been terminated and the Subconsultant submitted a payment claim for Subcontract Services carried out to the date of termination; and

the cost of goods or materials reasonably ordered by the Subconsultant for the Subcontract Services for which the Subconsultant is legally bound to pay provided that:

the value of the goods or materials is not included in the amount payable under subsubparagraph A; and

title in the goods and materials will vest in the Consultant upon payment; and

must:

take all steps possible to mitigate the costs referred to in subparagraph (i)B; and

comply with clause 18.4 (including by handing over to the Consultant's Representative copies of Project Documents prepared by the Subconsultant to the date of termination (whether complete or not)).

The amounts to which the Subconsultant is entitled under paragraph (a)(i) will be a limitation upon the Consultant’s liability to the Subconsultant arising out of or in connection with the termination of the Subcontract (whether under clause 12.7 or deemed to be under clause 12.7 through the operation of clause 12.6(a)) and, to the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with the termination of the Subcontract other than for the amount payable under clause 12.8.

Clause 12.8 will survive the termination of the Subcontract by the Consultant under clause 12.7 or by the Subconsultant following repudiation by the Consultant.

Termination of Design Services Contract

If the Design Services Contract is terminated at any time for any reason, the Consultant may:

terminate the Subcontract by notice in writing to the Subconsultant; or

without the consent of the Subconsultant, novate the Subcontract to the Commonwealth or a person nominated by the Commonwealth.

If the Subcontract is novated under paragraph (a)(ii), the Subconsultant must upon demand by the Consultant execute any instrument required by the Consultant to give effect to the novation.

Consequences Following Design Services Contract Termination

If the Subcontract is terminated under clause 12.9(a)(i), then the Subconsultant:

will be entitled to the payment for work carried out prior to the date of termination in the amount (as determined by the Consultant's Representative) which would have been payable if the Subcontract had not been terminated and the Subconsultant submitted a payment claim for work carried out to the date of termination; and

must comply with clause 18.4 (including by handing over to the Consultant’s Representative copies of Project Documents prepared by the Subconsultant to the date of termination (whether complete or not)).

The amounts to which the Subconsultant is entitled under clause 12.10 will be a limitation upon the Consultant’s liability to the Subconsultant arising out of or in connection with the termination of the Subcontract under clause 12.9 and the Subconsultant will not be entitled to make a Claim against the Consultant arising out of or in connection with the termination of the Subcontract other than for the amount payable under paragraph (a)(i).

Clauses 12.9 and 12.10 will survive termination of the Subcontract by the Consultant under clause 12.9.

DisputeS

Notice of Dispute

If a dispute or difference arises between the Subconsultant and the Consultant or between the Subconsultant and the Consultant's Representative in respect of any fact, matter or thing arising out of or in connection with the Subcontract Services, the Works or the Subcontract, or either party's conduct before the Subcontract, the dispute or difference must be determined in accordance with the procedure in clause 13.

Where such a dispute or difference arises, either party may give a notice in writing to the Consultant's Representative and the other party specifying:

the dispute or difference;

particulars of the party's reasons for being dissatisfied; and

the position which the party believes is correct.

Expert Determination

Unless otherwise agreed between the parties, to the extent the dispute or difference is in relation to a direction of the Consultant's Representative under one of the clauses specified in the Subcontract Particulars and is not resolved within 14 days after a notice is given under clause 13.1, the dispute or difference must be submitted to expert determination.

The Expert

The expert determination under clause 13.2 is to be conducted by:

the independent industry expert specified in the Subcontract Particulars; or

where no such independent industry expert is specified or paragraph (b) applies, an independent industry expert appointed by the person specified in the Subcontract Particulars.

If the expert appointed under paragraph (a):

is unavailable;

declines to act;

does not respond within 14 days to a request by one or both parties for advice as to whether he or she is able to conduct the determination;

does not enter into the Expert Determination Agreement or other agreement in accordance with clause 13.9(b) within 14 days of his or her appointment under paragraph (a); or

does not make a determination within the time required by clause 13.8,

the jurisdiction of the expert shall lapse and a further expert must be appointed under paragraph (a).

If there has been an appointment under paragraph (a) and one of the events in paragraph (b) has occurred, the further expert appointed under paragraph (a) shall not be an expert previously appointed under paragraph (a) in respect of the same dispute or difference.

Not Arbitration

An expert determination conducted under clause 13 is not an arbitration and the expert is not an arbitrator. The expert may reach a decision from his or her own knowledge and expertise.

Procedure for Determination

The expert will:

act as an expert and not as an arbitrator;

proceed in any manner he or she thinks fit;

conduct any investigation which he or she considers necessary to resolve the dispute or difference;

examine such documents, and interview such persons, as he or she may require; and

make such directions for the conduct of the determination as he or she considers necessary.

Disclosure of Interest

The expert must:

disclose to the parties any:

interest he or she has in the outcome of the determination;

conflict of interest;

conflict of duty;

personal relationship which the expert has with either party, or either party's representatives, witnesses or experts; and

other fact, matter or thing which a reasonable person may regard as giving rise to the possibility of bias; and

not communicate with one party to the determination without the knowledge of the other.

Costs

Each party will:

bear its own costs in respect of any expert determination; and

pay one-half of the expert’s costs.

Conclusion of Expert Determination

Unless otherwise agreed between the parties, the expert must notify the parties of his or her decision upon an expert determination conducted under clause 13 within 28 days from the acceptance by the expert of his or her appointment.

Expert Determination Agreement

The expert will not be liable to the parties arising out of or in connection with the expert determination process, except in the case of fraud.

The parties must enter into the Expert Determination Agreement with the appointed expert or an agreement with the appointed expert on such other terms as the parties and the expert may agree.

Determination of Expert

The determination of the expert:

must be in writing;

will be substituted for the relevant direction of the Consultant's Representative unless a party gives notice of appeal to the other party within 21 days of receiving such determination in which case, subject to clauses 13.11 and 13.12, any such appeal will be by way of a hearing de novo; and

will be final and binding, unless a party gives notice of appeal to the other party within 21 days of receiving such determination.

Executive Negotiation

If:

clause 13.2 applies, and a notice of appeal is given under clause 13.10; or

clause 13.2 does not apply,

the dispute or difference is to be referred to the Executive Negotiators.

The Executive Negotiators must within:

21 days of:

if the dispute or difference is not one which is to be referred to expert determination under clause 13.2, the notice of dispute given under clause 13.1; or

otherwise, the notice of appeal given under clause 13.10; or

such longer period of time as the Executive Negotiators may agree in writing,

meet and undertake genuine and good faith negotiations with a view to resolving the dispute or difference and, if they cannot resolve the dispute or difference, endeavour to agree upon a procedure to resolve the dispute or difference (such as mediation or further expert determination).

Arbitration Agreement

If, within:

21 days of:

if the dispute or difference is not one which is to be referred to expert determination under clause 13.2, the notice of dispute given under clause 13.1; or

otherwise, the notice of appeal given under clause 13.10; or

such longer period of time as the Executive Negotiators may agree in writing,

the Executive Negotiators:

or either party refuse or fail to meet and undertake genuine and good faith negotiations with a view to resolving the dispute or difference;

cannot resolve the dispute or difference; or

have not reached agreement upon a procedure to resolve the dispute or difference,

the dispute or difference will be referred to arbitration by a written notice by either party to the other party.

Arbitration

Arbitration pursuant to clause 13.13 will be conducted in accordance with the Rules of Arbitration of the International Chamber of Commerce (ICC Rules) current at the time of the reference to arbitration and as otherwise set out in clause 13.13.

The seat of the arbitration will be Melbourne, Australia and hence the proper law of the arbitration shall be Victoria.

The second sentence of Article 35(6) of the ICC Rules (in force from 1 March 2017) or its equivalent in any subsequent version of the ICC Rules shall not apply.

The parties agree that:

they have entered into the arbitration agreement under clause 13 for the purposes of achieving a just, quick and cheap resolution of any dispute or difference;

any arbitration conducted pursuant to clause 13.13 will not mimic court proceedings of the seat of the arbitration and the practices of those courts will not regulate the conduct of the proceedings before the arbitrator; and

in conducting the arbitration, the arbitrator must take into account the matters set out in subparagraphs (i) and (ii).

One arbitrator will be appointed.

All evidence in chief will be in writing unless otherwise ordered by the arbitrator.

Discovery will be governed by the substantive and procedural rules and practices adopted by the Federal Court of Australia at the time of arbitration.

The oral hearing will be conducted as follows:

the oral hearing will take place in Melbourne, Australia and all outstanding issues must be addressed at the oral hearing;

the date and duration of the oral hearing will be fixed by the arbitrator at the first preliminary conference. The arbitrator must have regard to the principles set out in paragraph (d) when determining the duration of the oral hearing;

oral evidence in chief at the hearing will be permitted only with the permission of the arbitrator for good cause;

the oral hearing will be conducted on a stop clock basis with the effect that the time available to the parties will be split equally between the parties so that each party will have the same time to conduct its case unless, in the opinion of the arbitrator, such a split would breach the rules of natural justice or is otherwise unfair to one of the parties;

not less than 28 days prior to the date fixed for the oral hearing, each party will give written notice of those witnesses (both factual and expert) of the other party that it wishes to attend the hearing for cross examination; and

in exceptional circumstances, the arbitrator may amend the date of hearing and extend the time for the oral hearing set under subparagraph (ii).

Unless otherwise ordered, each party may only rely upon one expert witness in respect of any recognised area of specialisation.

DSC Dispute Procedures

Under the Design Services Contract, disputes and differences between the Consultant and the Commonwealth and the Consultant and the DSC Contract Administrator are required to be determined in accordance with certain procedures which include expert determination, executive negotiation and arbitration.

Within 7 days of the Award Date, the Consultant must provide the Subconsultant with a copy of the provisions in the Design Services Contract setting out the DSC Dispute Procedures.

The Subconsultant agrees that certain disputes and differences of the kind referred to in clause 13.1 will be determined under the DSC Dispute Procedures as set out in clauses 13.15 to 13.17 in lieu of the procedures set out in clauses 13.2 to 13.13.

DSC Disputes

If:

the Subconsultant gives a notice under clause 13.1;

the dispute or difference relates, in whole or in part, to either:

an alleged breach of the Subcontract by the Consultant, which, assuming the breach has actually occurred, has been caused, or contributed to, by an act or omission (including breach of the Design Services Contract) of the Commonwealth; or

a direction given by the Consultant's Representative relating to a particular subject matter, in circumstances where a direction has been given by the DSC Contract Administrator to the Consultant relating, in whole or in part, to that subject matter; and

the Consultant is not barred from making, or has not waived its entitlement to make, a Claim against the Commonwealth in respect of the act, omission or direction,

the Consultant may within 7 days of receipt of the notice give a notice to the Subconsultant stating that clause 13.16 applies in relation to the dispute or difference.

Procedure for DSC Disputes

If a notice is given under clause 13.15 stating that clause 13.16 applies:

subject to clause 13.17, the Consultant must:

take such steps as are reasonably necessary to progress the Subconsultant’s dispute or difference under the DSC Dispute Procedures;

regularly consult with the Subconsultant to ascertain its views as to the progression of the Subconsultant's dispute or difference; and

use its best endeavours to ensure that the Subconsultant’s views, where relevant, are put to any expert or arbitrator appointed under the DSC Dispute Procedures or any court which may hear any matter relating to the Subconsultant's dispute or difference as between the Consultant and the Commonwealth; and

the Subconsultant must:

comply with the Consultant’s reasonable requirements relating to the conduct of the DSC Dispute Procedures or any relevant court proceedings insofar as they relate to the Subconsultant's dispute or difference;

indemnify the Consultant against all costs and expenses incurred by the Consultant in complying with paragraph (a); and

from time to time as required by the Consultant, lodge with the Consultant reasonable cash or other security against the costs and expenses referred to in paragraph (b)(ii).

Further Procedures

Where clause 13.16 applies, the following provisions also apply:

the Consultant must not without the prior consent of the Subconsultant agree to a settlement with the Commonwealth or any other relevant person of the Subconsultant’s dispute or difference; and

where a determination is made by an expert, an arbitrator or a court in relation to the Subconsultant's dispute or difference as between the Commonwealth and Consultant:

if the determination is not final and binding upon the Consultant:

the Consultant is not obliged to appeal against that determination unless the Subconsultant gives a notice to the Consultant requiring such an appeal:

within such time as to reasonably enable the Consultant to comply with any relevant requirements relating to the time for commencement of such appeals; and

which contains any particulars required to reasonably enable the Consultant to progress the appeal in accordance with any relevant requirements; and

the parties will be bound by and are to give effect to the determination including any findings as to law or fact unless and until it is reversed, overturned or otherwise changed on appeal as between the Commonwealth and the Consultant; and

if the determination is final and binding upon the Consultant, the parties:

will be bound by and are to give effect to the determination including any findings as to law or fact; and

release each other from any Claim which they may have arising out of or in connection with the subject matter of the Subconsultant's dispute or difference insofar as the determination relates to the dispute or difference.

Proportionate Liability

To the extent permitted by law, the expert or the arbitrator (as the case may be) will have no power to apply or to have regard to the provisions of the proportionate liability legislation of any Australian jurisdiction which might, in the absence of this provision, have applied to any dispute referred to arbitration or expert determination pursuant to clause 13.18.

Continuation of Subcontract Services

Despite the existence of a dispute or difference between the parties the Subconsultant must:

continue to carry out the Subcontract Services; and

otherwise comply with its obligations under the Subcontract.

Notices

Notice of Variation

If a direction by the Consultant's Representative, other than a Variation Order under clause 10.2, constitutes or involves a Variation, the Subconsultant must, if it wishes to make a Claim against the Consultant arising out of or in connection with the direction:

within 7 days of receiving the direction and before commencing services the subject matter of the direction, give notice to the Consultant's Representative that it considers the direction constitutes or involves a Variation;

within 21 days after giving the notice under paragraph (a), submit a written claim to the Consultant's Representative which includes the details required by clause 14.3(b); and

continue to carry out the Subcontract Services in accordance with the Subcontract and all directions of the Consultant's Representative, including any direction in respect of which notice has been given under clause 14.1.

Notices of Other Claims

Except for claims for:

an extension of time under clause 8.6;

payment under clause 11 of the original Fee specified in the Subcontract Particulars;

a Variation instructed in accordance with clause 10.2 or to which clause 14.1 applies; or

contribution or indemnity for loss or damage caused or contributed to by the negligence of the Consultant where a third party (other than a party for whom the Subconsultant is legally responsible) makes a claim (whether in tort, under statute or otherwise at law) against the Subconsultant,

the Subconsultant must give the Consultant's Representative the notices required by clause 14.3 if it wishes to make a Claim against the Consultant in respect of any direction by the Consultant's Representative or any other fact, matter or thing (including a breach of the Subcontract by the Consultant) under, arising out of or in connection with the Subcontract Services or the Subcontract, including anything in respect of which:

it is otherwise given an express entitlement under the Subcontract; or

the Subcontract expressly provides that:

amounts are to be added to the Fee; or

otherwise the Fee will be increased or adjusted,

as determined by the Consultant's Representative.

Prescribed Notices

The notices referred to in clause 14.2 are:

a written notice within 21 days of the first occurrence of the direction or other fact, matter or thing upon which the Claim is based, expressly specifying:

that the Subconsultant proposes to make a Claim; and

the direction or other fact, matter or thing upon which the Claim will be based; and

a written Claim within 21 days of giving the written notice under paragraph (a), which must include:

detailed particulars concerning the direction or other fact, matter or thing upon which the Claim is based;

the legal basis for the Claim, whether based on a term of the Subcontract or otherwise, and if based on a term of the Subcontract, clearly identifying the specific term;

the facts relied upon in support of the Claim in sufficient detail to permit verification; and

details of the amount claimed and how it has been calculated in sufficient detail to permit verification.

Continuing Events

If the direction or fact, matter or thing upon which the Claim under clause 14.1(b) or clause 14.2 is based or the consequences of the direction or fact, matter or thing are continuing, the Subconsultant must continue to give the information required by clause 14.3(b) every 28 days after the written claim under clause 14.1(b) or 14.3(b) (as the case may be) was submitted or given to the Consultant's Representative, until after the direction or fact, matter or thing upon which the Claim is based has, or the consequences thereof have, ceased.

Time Bar

If the Subconsultant fails to comply with clause 14.1, 14.2, 14.3 or 14.4, the:

Consultant will not be liable (insofar as it is possible to exclude such liability) upon any Claim by the Subconsultant; and

Subconsultant will be absolutely barred from making any Claim against the Consultant,

arising out of or in connection with the relevant direction or fact, matter or thing (as the case may be) to which clause 14.1 or 14.2 applies.

Other Provisions Unaffected

Nothing in clauses 14.1 - 14.5 will limit the operation or effect of any other provision of the Subcontract which requires the Subconsultant to give notice to the Consultant's Representative in order to preserve an entitlement to make a Claim against the Consultant.

Address for Service

Any notice to be given or served under or arising out of a provision of the Subcontract must:

be in writing;

be delivered by hand, sent by prepaid express post or sent by email (except for notices under clauses 12 and 13 which, if sent by email, must additionally be delivered by hand or sent by prepaid express post) to the relevant address or email address:

specified in the Subcontract Particulars; or

last notified in writing to the party giving or serving the notice,

for the party to whom or upon which the notice is to be given or served;

be signed by the party giving or serving the notice or (on the party's behalf) by the solicitor for or attorney, director, secretary or authorised agent of the party giving or serving the notice; and

in the case of notices sent by email:

be in Portable Document Format (pdf) and appended as an attachment to the email; and

include the words "This is a notice under clause 14.7 of the Subcontract" in the subject field of the email.

Receipt of Notices

Subject to paragraph (b), a notice given or served in accordance with clause 14.7 is taken to be received by the party to whom or upon whom the notice is given or served in the case of:

delivery by hand, on delivery;

prepaid express post sent to an address in the same country, on the fifth day after the date of posting;

prepaid express post sent to an address in another country, on the seventh day after the date of posting; and

email, the earlier of:

delivery to the email address to which it was sent; and

one hour after the email enters the server of the email address to which it was sent, provided that no delivery or transmission error is received by the sender within one hour of the time of sending shown on the "sent" email.

In the case of notices under clauses 12 and 13, if the notice is sent by email as well as being delivered by hand or sent by prepaid express post in accordance with clause 14.7(b), the notice is taken to be received by the party to whom or upon whom the notice is given or served on the earlier of the:

date the notice sent by email is taken to be received; or

date the notice delivered by hand or sent by prepaid express post is taken to be received,

as determined in accordance with paragraph (a).

Whole of Life

General

Without limiting the Subconsultant's obligations under the Subcontract or otherwise at law or in equity, the Subconsultant must prepare the Design Documentation and carry out the Subcontract Services in a manner which maximises the achievement of the WOL Objectives.

Consultation

The Subconsultant must meet with the Consultant's Representative, the Consultant, the DSC Contract Administrator, the Commonwealth and Other Contractors at such times as the Consultant's Representative may require from time to time to:

review the progress of the Design Documentation and the Subcontract Services against the WOL Objectives; and

consult with the Consultant's Representative, the Consultant, the DSC Contract Administrator, the Commonwealth and Other Contractors as to any designs, materials or methods of construction which they might recommend to maximise the achievement of the WOL Objectives.

WOL Proposals

Without limiting the Subconsultant's obligations under the Subcontract or otherwise at law or in equity, the Subconsultant must at all times in preparing the Design Documentation and otherwise carrying out the Subcontract Services:

use its best endeavours to identify and recommend to the Consultant's Representative, all reasonably available proposals for maximising the achievement of the WOL Objectives; and

consult with the Consultant's Representative, the Consultant, the DSC Contract Administrator, the Commonwealth and Other Contractors as to:

proposals which it is considering making under paragraph (a); and

possible proposals under paragraph (a) identified by the Consultant.

HOTO Process

Without limiting clause 2.6, the Subconsultant must:

fully co-operate with the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant’s Representative and Other Contractors and take all steps necessary to ensure the timely, efficient, comprehensive and smooth completion of the HOTO Process; and

without limiting paragraph (a):

carry out all Subconsultant HOTO Obligations;

ensure that all Subconsultant HOTO Obligations are carried out within any applicable timeframe prescribed by, or determined in accordance with, the HOTO Requirements;

comply with:

all applicable HOTO Requirements; and

all commissioning, handover and takeover requirements described in the Subcontract;

as and when required by the Consultant's Representative, provide the Consultant with such other specific assistance as may be required by the Consultant to facilitate the timely, efficient, comprehensive and smooth completion of the HOTO Process; and

as and when required by the Consultant's Representative, meet with the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant's Representative and Other Contractors for the purpose of ensuring that the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant's Representative and Other Contractors have sufficient Project Documents to enable the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant's Representative and Other Contractors to:

occupy, use, operate and maintain the Works or the Stage (as defined in the Construction Contract); and

perform such other activities as may be required by the Commonwealth in respect of the Works or the Stage (as defined in the Construction Contract).

Post Occupancy Evaluation

The Consultant's Representative may:

at any time carry out (or procure an Other Contractor to carry out) a post occupancy evaluation of the Works; and

without limiting subparagraph (i):

inspect the Works to review the extent to which the Subconsultant has maximised the achievement of the WOL Objectives in the design of the Works; and

issue a report to the Commonwealth, the Consultant and the Subconsultant:

stating the extent to which the Subconsultant has maximised the achievement of the WOL Objectives in the design of the Works; and

containing a list of any aspects of the Works which do not conform with the requirements of the Construction Contract, comparing the actual resource intensity performance to the predicted design performance target.

The Subconsultant:

must consult with the Commonwealth, the DSC Contract Administrator, the Consultant, the Consultant's Representative and Other Contractors, and must provide such other assistance as is reasonably necessary, for the purposes of the Consultant's Representative carrying out the requirements in paragraphs (a)(i) and (a)(ii); and

acknowledges and agrees that the Commonwealth and the Consultant may take the results of the post occupancy evaluation into account in any registration of interest process, tender process or similar procurement process in connection with any other Commonwealth project.

Rights and Obligations Not Affected

Neither the Consultant's rights or remedies, nor the Subconsultant's obligations under the Subcontract or otherwise at law or in equity, will be affected or limited by:

the rights conferred upon the Consultant or Consultant's Representative by clause 15 or the failure by the Consultant or the Consultant's Representative to exercise any such rights;

the obligations imposed upon the Subconsultant by clause 15 or the Subconsultant's compliance with those obligations; or

any direction of the Consultant's Representative under or purported to be given under the Subcontract, including any comment or direction upon or review, acceptance or rejection of:

any advice, recommendation or other assistance provided by the Subconsultant under clause 15; or

any post occupancy evaluation carried out (including any report prepared and finalised) under clause 15.5.

General

Workplace Gender Equality

The Subconsultant must comply with its obligations under the Workplace Gender Equality Act 2012 (Cth).

Indigenous Procurement Policy

- The Subconsultant must use its reasonable endeavours to increase its:

purchasing from Indigenous Enterprises; and

employment of Indigenous Australians,

in carrying out the Subcontract Services, in accordance with the Indigenous Procurement Policy.

Defence's Security Alert System

Nothing that the Subconsultant is or may be required to do under clause 16.3 will derogate from, or otherwise limit, the Subconsultant's obligations under the Subcontract.

The Subconsultant must be fully familiar with the requirements of Defence's Security Alert System.

The Subconsultant must:

attend any security briefing requested by the Consultant's Representative from time to time; and

participate in any rehearsal of Defence's Security Alert System directed by the Consultant's Representative from time to time.

In carrying out the Subcontract Services, the Subconsultant must comply with the requirements of Defence's Security Alert System:

at the level specified in the Subcontract Particulars; and

at any alternative level (or individual measure from a higher level to meet a specific threat or threats) applicable to the Site from time to time.

If there is any change to Defence's Security Alert System level specified in the Subcontract Particulars (or individual measure from a higher level to meet a specific threat or threats) applicable to the Site from time to time after the Award Date:

the Consultant's Representative will notify the Subconsultant of the change to the level (or individual measure from a higher level to meet a specific threat or threats) and instruct the Subconsultant as to the course it is to adopt insofar as the Subcontract Services are affected by the change to the level (or individual measure from a higher level to meet a specific threat or threats); and

subject to subparagraph (iii), the Subconsultant will be entitled to have the Fee increased by the extra costs reasonably incurred by the Subconsultant which arise directly from the change and the Consultant's Representative's instruction under subparagraph (i), as determined by the Consultant's Representative; or

the Fee will be decreased by any saving made by the Subconsultant after the giving of the notice under subparagraph (i) which arise directly from the change and the Consultant's Representative's instruction under subparagraph (i), as determined by the Consultant's Representative.

The amount (if any) under paragraph (e)(ii) will be a limitation on the Consultant's liability to the Subconsultant arising out of or in connection with the:

change to Defence's Security Alert System level (or individual measure from a higher level to meet a specific threat or threats); and

Consultant's Representative's instruction,

and, to the extent permitted by law, the Subconsultant will not be entitled to make (nor will the Consultant be liable upon) any Claim arising out of or in connection with any change to Defence's Security Alert System level (or individual measure from a higher level to meet a specific threat or threats) or the Consultant's Representative's instruction under paragraph (e)(i), other than under paragraph (e)(ii).

IT Equipment

Without limiting the Subconsultant’s obligations under the Subcontract, the Subconsultant warrants that:

each item of IT Equipment:

is free of defects in materials and workmanship;

complies and operates in accordance with any technical or descriptive specifications of functional, operational, performance or other characteristics specified for that item of IT Equipment in the Subcontract or in any documentation accompanying that IT Equipment; and

correctly interprets dates and correctly performs calculations or functions using dates and its operation, including with related IT Equipment and other parts of the Works, will not be adversely affected by the date; and

no virus will be introduced into the Consultant's or the Commonwealth's systems as a result of the supply by the Subconsultant of any IT Equipment or as a result of any other act or omission of the Subconsultant in connection with carrying out the Subcontract Services.

The Subconsultant must assign to the Consultant the benefits of warranties given by any supplier from whom the Subconsultant sources any IT Equipment and for that purpose must execute any instrument necessary to give effect to the assignment within 7 days of the Subconsultant becoming entitled to the benefit of such warranties. The assignment of a warranty pursuant to clause 16.4 does not in any way relieve the Subconsultant of the obligation to comply with warranties given by the Subconsultant under the Subcontract.

Privacy

The Subconsultant must:

comply with its obligations under the Privacy Act;

comply with the Australian Privacy Principles when doing any act or engaging in any practice for the purposes of the Subcontract, as if it were an agency as defined in the Privacy Act;

use Personal Information received, created or held by the Subconsultant for the purposes of, under, arising out of or in connection with the Subcontract only for the purposes of fulfilling its obligations under the Subcontract;

not disclose Personal Information received, created or held by the Subconsultant for the purposes of, under, arising out of or in connection with the Subcontract without the prior written approval of the Consultant's Representative;

not collect, transfer, store or otherwise use Personal Information received, created or held by the Subconsultant for the purposes of, under, arising out of or in connection with the Subcontract outside Australia, or allow parties outside Australia to have access to it, without the prior written approval of the Consultant's Representative;

co-operate with demands or inquiries made by the Federal Privacy Commissioner or the Consultant's Representative in relation to the management of Personal Information in connection with the Subcontract;

ensure that any person whom the Subconsultant allows to access Personal Information which is received, created or held by the Subconsultant for the purposes of, under, arising out of or in connection with the Subcontract is made aware of, and undertakes in writing to observe, the Australian Privacy Principles, as if the person was an agency as defined in the Privacy Act;

comply with policy guidelines laid down by the Commonwealth or issued by the Federal Privacy Commissioner from time to time relating to Personal Information;

ensure that records (as defined in the Privacy Act) containing Personal Information received, created or held by the Subconsultant for the purposes of, under, arising out of or in connection with the Subcontract are, at the expiration or earlier termination of the Subcontract, at the Consultant's election, to be either returned to the Consultant or deleted or destroyed in the presence of a person duly authorised by the Consultant's Representative to oversee such deletion or destruction;

agree to the naming or other identification of the Subconsultant in reports by the Federal Privacy Commissioner;

not use Personal Information collected by the Subconsultant for the purposes of, under, arising out of or in connection with the Subcontract for, or in any way relating to, any direct marketing purpose; and

indemnify the Consultant in respect of all costs, expenses, losses, damages or liabilities suffered or incurred by the Consultant arising out of or in connection with:

a breach of the obligations of the Subconsultant under clause 16.5;

the misuse of Personal Information held for the purposes of, under, arising out of or in connection with the Subcontract by the Subconsultant; or

the disclosure of Personal Information held for the purposes of, under, arising out of or in connection with the Subcontract by the Subconsultant in breach of an obligation of confidence.

For the purposes of paragraph (a)(xii), costs, expenses, losses, damages or liabilities includes any compensation paid to a person by or on behalf of the Consultant to settle a complaint arising out of or in connection with a breach of clause 16.5.

The Subconsultant must immediately notify the Consultant in writing if the Subconsultant:

becomes aware of a breach of the obligations under this clause 16.5;

becomes aware that a disclosure of Personal Information may be required by law; or

is approached or contacted by the Federal Privacy Commissioner or by a person claiming that their privacy has been interfered with.

The Subconsultant acknowledges that, in addition to the requirements of clause 16.5, the Subconsultant may also be obliged to comply with other obligations in relation to the handling of Personal Information, including State and Territory legislation.

Nothing in clause 16.5 limits any of the Subconsultant's obligations under the Subcontract or otherwise at law or in equity.

In clause 16.5, received includes collected.

Moral Rights

The Subconsultant must:

to the extent permitted by law and for the benefit of the Consultant, ensure that each of the personnel engaged by the Subconsultant in the production or creation of Project Documents or the Works gives genuine consent in writing to the use of the Project Document or the Works (as applicable) for the Specified Acts, notwithstanding that such use would otherwise be an infringement of their Moral Rights; and

provide copies of such consents to the Consultant's Representative on request at such times as the Consultant's Representative may require.

In this clause 16.6, Specified Acts means:

falsely attributing the authorship of any Project Document or the Works, or any content in a Project Document or the Works (including literary, dramatic, artistic works and cinematograph films within the meaning of the Copyright Act 1968 (Cth));

materially altering the style, format, colours, content or layout of a Project Document or the Works and dealing in any way with the altered Project Document or Works;

reproducing, communicating, adapting, publishing or exhibiting any Project Document or the Works; and

adding any additional content or information to a Project Document or the Works.

Freedom of Information

The Freedom of Information Act 1982 (Cth) (FOI Act) gives members of the public rights of access to official documents of the Commonwealth Government and its agencies. The FOI Act extends, as far as possible, rights to access information (generally documents) in the possession of the Commonwealth Government, limited only by considerations for the protection of essential public interest and of the private and business affairs of persons in respect of whom information is collected and held by departments and public authorities.

The Subconsultant acknowledges that Commonwealth requirements and policies will require certain identifying details of the Subcontract to be made available to the public via the internet.

Long Service Leave

Clause 16.8 only applies if the Long Service Leave Legislation applies to the Subcontract Services.

Without limiting the Subconsultant’s obligations under the Subcontract or otherwise at law or in equity, the Subconsultant must comply with its obligations under the Long Service Leave Legislation.

If required by the Long Service Leave Legislation, the Subconsultant must pay any levy, charge, contribution or associated amount in respect of the Subcontract Services.

Any amount paid by the Subconsultant under paragraph (b) is deemed to be included in the Fee and the Subconsultant will have no Claim against the Consultant arising out of or in connection with its obligations under clause 16.8 or the Long Service Leave Legislation.

Assignment

The Subconsultant must not, without the prior written approval of the Consultant and except on such terms and conditions notified by the Consultant, assign, mortgage, charge or encumber the Subcontract or any part or any benefit or moneys or interest under the Subcontract.

For the purpose of but without limiting paragraph (a), an assignment of the Subcontract will be deemed to have occurred where there has been a Change of Control.

Publicity

Without limiting clause 18, the Subconsultant must:

not furnish any information or issue any document or other written or printed material concerning the Subcontract Services or the Works for publication in the media without the prior written approval of the DSC Contract Administrator; and

refer any enquiries from the media concerning the Subcontract Services or the Works to the Consultant's Representative.

Building Works Manual and National Construction Code Certification

Without limiting clauses 2.10, 2.11 and 6.13, the Subconsultant must provide to the Consultant's Representative written certification from an Accredited Building Surveyor:

at the time it submits any Design Documentation to the Consultant's Representative under clause 6.2 - that the Design Documentation submitted at that time complies with the Building Works Manual and the National Construction Code;

before issue of any Design Documentation for the purpose of engaging a Contractor - that the Design Documentation to be issued complies with the Building Works Manual and the National Construction Code; and

prior to Completion (as defined in the Construction Contract) - that the Works comply or the Stage (as defined in the Construction Contract) complies with the Building Works Manual and the National Construction Code,

except to the extent of any dispensation granted by the Assistant Secretary Environment and Engineering and identified in the certification. To the extent that there is any inconsistency between the Building Works Manual and the National Construction Code, the Building Works Manual prevails.

Applicable Standards

Without limiting the Subconsultant's obligations under this Subcontract, the Subconsultant must comply with the Applicable Standards in performing the Subcontract Services.

The Consultant's Representative may, at any time, request that the Subconsultant provides:

evidence of relevant certifications demonstrating compliance with the Applicable Standards; and

a certificate which certifies that (to the extent then applicable) the Design Documentation or the Subcontract Services complies with the Applicable Standards.

The Subconsultant acknowledges that the Consultant may exercise any of its rights under this Subcontract (including under clause 6.11) to carry out periodic auditing of the Subconsultant's compliance with clause 16.12.

In this clause 16.12, Applicable Standards means the specific international or Australian standards which are applicable to the Services as identified in the Subcontract.

Shadow Economy Procurement Connected Policy

Clause 16.13 does apply unless the Subcontract Particulars state that it does not apply.

The Subconsultant:

warrants that at the Award Date it holds all valid and satisfactory STRs required for its entity type in accordance with the requirements of the Shadow Economy Procurement Connected Policy; and

must hold all valid and satisfactory STRs required for its entity type in accordance with the requirements of the Shadow Economy Procurement Connected Policy at all times during the Subcontract Services and, on request by the Consultant’s Representative, provide to the Consultant’s Representative a copy of any such STR.

The Subconsultant must obtain and hold additional STRs in the circumstances set out in the table below within 10 business days of the Subconsultant becoming aware of the circumstances arising:

| If the Subconsultant is: | Additional STRs required arising from changed circumstances: |
| --- | --- |
| - a partner acting for and on behalf of a partnership | a valid and satisfactory STR in respect of any additional partner that becomes directly involved in the delivery of the Subcontract. |
| - a trustee acting in its capacity as trustee of an Australian or foreign trust | a valid and satisfactory STR in respect of any new trustee appointed to the trust. |
| - a joint venture participant | a valid and satisfactory STR in respect of any new: - participant in the joint venture; and - joint venture operator if the new operator is not already a participant in the joint venture. |
| - a member or head company of a Consolidated Group | a valid and satisfactory STR in respect of any new head company of the Consolidated Group. |
| - a member of a GST Group | a valid and satisfactory STR in respect of any new representative for the GST Group. |

The Subconsultant must provide the Consultant with copies of the STRs referred to in paragraph (c) within 5 business days after a written request by the Consultant.

For the purposes of the Subcontract, an STR is taken to be:

satisfactory if the STR states that the entity has met the conditions, as set out in the Shadow Economy Procurement Connected Policy, of having a satisfactory engagement with the Australian tax system; and

valid if the STR has not expired as at the date on which the STR is required to be provided or held.

Commonwealth Publication and Reporting Requirements

The Subconsultant acknowledges that the Commonwealth and the Consultant are and will be subject to a number of Commonwealth requirements and policies which support internal and external scrutiny of tendering and contracting processes and the objectives of transparency, accountability and value for money including to:

publish details of agency agreements, Commonwealth contracts, amendments and variations to any agreement or contract and standing offers with an estimated value of $10,000 or more on AusTender (the Commonwealth's business opportunity website located at www.tenders.gov.au);

report and post on the internet a list of contracts valued at $100,000 or more and identify confidentiality requirements in accordance with the Senate Order on Department and Agency Contracts;

report and post on the internet information about contracts in other ways pursuant to other reporting and disclosure obligations, including annual reporting requirements and disclosure to any House or Committee of the Parliament of the Commonwealth of Australia; and

disclose information to other Commonwealth departments, agencies, or authorities by virtue of or in connection with their functions, or statutory or portfolio responsibilities or for any legitimate government purpose or process.

Modern Slavery

The Subconsultant must take reasonable steps to identify, assess and address risks of Modern Slavery practices arising in connection with the Subcontract, including in the operations and supply chains used in the performance of the Subcontract Services.

The Subconsultant must ensure the Subconsultant's key people under clause 4.4 and other personnel responsible for managing the operations and supply chains used in the performance of the Subcontract Services have undertaken suitable training to be able to identify and report Modern Slavery.

If at any time the Subconsultant becomes aware of Modern Slavery practices arising in connection with the Subcontract, including in the operations and supply chains used in the performance of the Subcontract Services, the Consultant must:

promptly notify the Consultant’s Representative of the Modern Slavery practices and provide any relevant information requested by the Consultant’s Representative;

as soon as reasonably practicable take all reasonable action to address or remove these practices, including where relevant by addressing any practices of other entities in its supply chains; and

regularly update the Consultant’s Representative of the steps taken by it in accordance with subparagraph (ii).

For the purposes of this clause 16.15, Modern Slavery has the same meaning as it has in the Modern Slavery Act 2018 (Cth).

Compliance with the Commonwealth Supplier Code of Conduct

The Subconsultant must comply with, and ensure that its officers, employees and agents comply with, the Code in connection with the performance of the Subcontract.

The Subconsultant must:

periodically monitor and assess its, and its officers', employees' and agents' compliance with the Code; and

on request from the Consultant's Representative, promptly provide information regarding:

the policies, frameworks or systems it has established to monitor and assess compliance with the Code; and

the Subconsultant's compliance with paragraph (a).

The Subconsultant must immediately notify the Consultant's Representative in writing upon becoming aware of any breach of paragraph (a). The notice must include a summary of the breach, the date that the breach occurred and details of the personnel involved.

Where the Consultant's Representative identifies a possible breach of paragraph (a), it may notify the Subconsultant in writing, and the Subconsultant must, within three days of receiving the notice, either:

where the Subconsultant considers a breach has not occurred - advise the Consultant's Representative that there has not been a breach and provide information supporting that determination; or

where the Subconsultant considers that a breach has occurred - notify the Consultant's Representative under paragraph (c) and otherwise comply with its obligations under this clause 16.16.

Notwithstanding paragraph (d), the Consultant's Representative may notify the Subconsultant in writing that it considers that the Subconsultant has breached paragraph (a), in which case the Subconsultant must notify the Consultant's Representative in writing under paragraph (c) and otherwise comply with its obligations under this clause 16.16.

Nothing in this clause 16.16 or the Code limits, reduces or derogates from the Subconsultant's other obligations under the Subcontract. The Consultant's rights under this clause 16.16 are in addition to and do not otherwise limit any other rights the Consultant may have under the Subcontract. The performance by the Subconsultant of its obligations under this clause 16.16 will be at no additional cost to the Consultant.

The Subconsultant acknowledges and agrees that the Subconsultant's compliance with the Code may be taken into account in any registration of interest process, tender process or similar procurement process in connection with any other Commonwealth project.

For the purposes of this clause 16.16, Code means the Commonwealth Supplier Code of Conduct dated 1 July 2024, available at https://www.finance.gov.au/government/procurement/commonwealth-supplier-code-conduct/commonwealth-supplier-code-conduct, as amended from time to time.

COMMERCIAL-IN-CONFIDENCE INFORMATION

Clause 17 does not apply unless the Subcontract Particulars state that it applies.

Subject to paragraph (b), the Consultant must keep confidential any information provided to the Consultant by the Subconsultant before or after the Award Date when:

a written request to keep specific information confidential and the justification for keeping such information confidential has been expressly made by the Subconsultant to the Consultant in its tender;

the Consultant agrees (in its absolute discretion) that such information is commercial-in-confidence information;

the Consultant’s Representative notifies the Subconsultant in writing that the Consultant (in its absolute discretion) agrees, including the terms of any agreement under subparagraph (ii); and

such information and the terms of any agreement are expressly specified in the Subcontract Particulars,

(Commercial-in-Confidence Information).

The Consultant's obligation in paragraph (a) does not apply if the Commercial-in-Confidence Information is:

disclosed by the Consultant to its legal or other advisers, or to its officers, employees, contractors or agents in order to comply with its obligations or to exercise its rights under or in connection with the Subcontract;

disclosed by the Consultant to its legal or other advisers, or to its officers, employees, contractors or agents in order to comply with the Consultant's management, reporting or auditing requirements under the Design Services Contract;

disclosed by the Consultant to any responsible Minister or any Ministerial adviser or assistant;

disclosed by the Consultant to any House or Committee of the Parliament of the Commonwealth of Australia;

disclosed to any Commonwealth department, agency or authority:

by virtue of or in connection with:

its functions, or statutory or portfolio responsibilities; or

the Design Services Contract; or

for any legitimate government purpose or process including policy development, research, compliance, regulatory and other non-commercial purposes;

authorised or required by law to be disclosed; or

in the public domain otherwise than due to a breach of paragraph (a).

INFORMATION SECURITY

DISP Membership

- The Subconsultant must:

at its cost have obtained as at the Award Date and thereafter maintain for the term of the Subcontract the level of DISP membership specified in the Subcontract Particulars in accordance with Control 16.1 of the DSPF; and

comply with any other direction or requirement of the Consultant's Representative in relation to the DISP.

Confidential Information and Information Security

The Subconsultant acknowledges and agrees that:

the Confidential Information is confidential to the Commonwealth and the Consultant and that any unauthorised use or disclosure of the Confidential Information may cause loss or damage to the Commonwealth and the Consultant; and

part of the Confidential Information may be Sensitive and Classified Information.

Except as expressly provided in this clause 18.2, the Subconsultant must:

hold the Confidential Information in strict confidence and must not disclose, use or deal with it or otherwise make it available to any person; and

ensure all Confidential Information is strictly kept secure and protected from all unauthorised access and use.

The Subconsultant may disclose Confidential Information where such disclosure is required by law provided that the Subconsultant:

only discloses such of the Confidential Information as is strictly required by law to be disclosed, including by taking all reasonable steps in consultation with the recipient (whether by agreed redaction or otherwise) to limit the Confidential Information which is disclosed;

where legally permitted to do so, immediately notifies the Consultant's Representative and the Consultant in writing of such requirement and provides such details as would enable the Consultant to independently seek to protect the confidentiality of the Confidential Information; and

ensures that any recipient is made aware of the confidential status of the Confidential Information and takes all reasonable steps to obtain confidentiality undertakings from the recipient.

Subject to paragraph (e)(ii)B, the Subconsultant may disclose Confidential Information to:

an employee, officer, agent, legal adviser or insurer of the Subconsultant who needs to know the Confidential Information to enable the Subconsultant to perform its obligations under the Subcontract; and

such other persons, provided the Consultant has obtained the prior written approval of the Consultant's Representative (including on such conditions as the Consultant's Representative may impose in its absolute discretion),

- provided that the Subconsultant must ensure that all such persons strictly comply with equivalent obligations as are imposed on the Subconsultant by this clause 18 in respect of all Confidential Information disclosed to them.

The Subconsultant must:

strictly comply with all:

Information Security Requirements, including as set out in Control 10 of the DSPF; and

additional information security or confidentiality requirements notified by the Consultant's Representative or the Consultant, including in respect of any Security or Confidentiality Incident; and

without limiting paragraph (d) or subparagraph (i), ensure:

that persons performing the roles specified in the Subcontract Particulars hold and maintain a security clearance at or above the level specified in the Subcontract Particulars; and

that no Sensitive and Classified Information is released to any third party, without the prior written approval of the originator through the Consultant's Representative (including on such conditions as the Consultant's Representative may impose in its absolute discretion).

Without limiting the Consultant's strict obligations under paragraph (e)(i), the security classification of the information and assets accessible to the Subconsultant in connection with the Subcontract is anticipated to be at or below the level specified in the Subcontract Particulars, provided that if the Subconsultant is required to access information and assets above the specified level, this will be deemed to be a change in Statutory Requirements for the purposes of clause 2.11.

Within such period as the Consultant's Representative or the Consultant may direct, the Subconsultant must, in accordance with the other terms of the direction, provide:

evidence of the Subconsultant's (including all persons who have been provided with or had access to Confidential Information) compliance with this clause 18; and

a statutory declaration in a form and from an authorised officer satisfactory to the Consultant (acting reasonably) in respect of the Subconsultant’s (including all persons who have been provided with or had access to Confidential Information) compliance with this clause 18.

Security or Confidentiality Incidents

- The Subconsultant must:

detect all actual or potential Security or Confidentiality Incidents;

immediately notify the Consultant's Representative and the Consultant if it becomes aware of any actual or potential Security or Confidentiality Incident;

take all steps necessary to prevent, end, avoid, mitigate or otherwise manage the adverse effect of any actual or potential Security or Confidentiality Incident; and

take all other steps as may be notified by the Consultant's Representative or the Consultant under clause 18.2(e)(i)B in respect of the Security or Confidentiality Incident or as necessary to comply with an Information Security Requirement.

Return and Retention of Confidential Information

Subject to paragraph (b), the Subconsultant must return to the Consultant or destroy all documents in its possession, power or control which contain any Confidential Information:

in accordance with the Information Security Requirements; and

without limiting subparagraph (i), where the Confidential Information is no longer required for the purposes of the Subcontract.

Subject to ongoing compliance with the other requirements of this clause 18 in respect of confidentiality and information security, the Subconsultant may retain Confidential Information in its records if retention is required to comply with the Information Security Requirements or any other Statutory Requirement, insurance obligation or otherwise with the prior written approval of the Consultant's Representative (including on such conditions as the Consultant's Representative may impose in its absolute discretion).

If the Subconsultant is aware that documents containing the Confidential Information are beyond its possession or control, then the Subconsultant must provide full particulars of the whereabouts of the documents containing the Confidential Information, and the identity of the person in whose custody or control they lie and procure compliance by such persons with paragraphs (a) and (b) as applicable.

Release and Indemnity

The Subconsultant:

must bear, and releases the Consultant in respect of all costs, expenses, losses, damages or liabilities suffered or incurred by the Subconsultant or any other person or entity arising out of or in connection with a Security or Confidentiality Incident or the exercise of any of the Consultant's Representative's or the Consultant's absolute discretions under clause 18; and

indemnifies the Consultant in respect of all costs, expenses, losses, damages or liabilities suffered or incurred by the Consultant arising out of or in connection with a Security or Confidentiality Incident.

STRATEGIC NOTICE EVENT

Subconsultant's Warranty on Award Date

The Subconsultant warrants that, on the Award Date, it is not aware of any Strategic Notice Event.

Subconsultant to Give Notice

If, at any time, the Subconsultant becomes aware of any Strategic Notice Event, the Subconsultant must, as soon as reasonably practicable, notify the DSC Contract Administrator and the Consultant's Representative, providing details, to the extent such details are known by or reasonably available to the Subconsultant, of:

the Strategic Notice Event, including:

whether the Subconsultant considers that it is a Material Change, Defence Strategic Interest Issue or a Significant Event;

the date or dates on or during which the Strategic Notice Event occurred and the date on which the Subconsultant became aware of the Strategic Notice Event; and

whether any of the Subconsultant's key people, other personnel engaged in connection with the Subcontract Services; and

the steps which the Subconsultant has taken (or will take) to prevent, end, avoid, mitigate, resolve or otherwise manage the risk of any adverse effect of the Strategic Notice Event on the interests of the Consultant or the Commonwealth.

Consultant Rights Upon Occurrence of Strategic Notice Event

- Without limiting any other right or remedy of the Consultant (under the Subcontract or otherwise at law or in equity), if:

the Subconsultant:

notifies the DSC Contract Administrator and the Consultant's Representative under clause 19.2; or

has given a false warranty in any respect under clause 19.1 or has failed to strictly comply with clause 19; or

the Consultant otherwise considers (in its absolute discretion) that there exists (or is likely to exist) a Strategic Notice Event,

the Consultant may (in its absolute discretion) and either itself, or through the Consultant's Representative, do any one or more of the following:

notify the Subconsultant that it is required to provide further information, documents or evidence in relation to, and otherwise clarify, the:

nature and extent of the Strategic Notice Event to the extent such information, documents or evidence are known or reasonably available to the Subconsultant; and

steps which the Subconsultant has taken (or will take) to prevent, end, avoid, mitigate, resolve or otherwise manage the risk of any adverse effect of the Strategic Notice Event on the interests of the Consultant and the Commonwealth,

within 3 business days of the request (or longer period agreed in writing by the Consultant);

regardless of whether or not the Subconsultant has received a notice under paragraph (c), notify the Subconsultant that the Subconsultant may continue to perform the Subcontract Services, whether with or without such conditions as the Consultant thinks fit (in its absolute discretion) including the Subconsultant preparing and implementing a Strategic Notice Event Remediation Plan in accordance with clause 19.4; and

regardless of whether or not the Consultant has notified the Subconsultant under paragraphs (c) or (d), take into account the occurrence of a Strategic Notice Event at any time, including when:

conducting performance reviews, providing a direction to remove a person from the Site or the Subcontract Services (including in accordance with clause 4.5), or exercising any rights of the Consultant in relation to access, audit or the treatment of documentation under or in connection with the Subcontract (including in accordance with clause 6.11);

deciding whether to exercise any rights in relation to termination or to omit parts of the Subcontract Services by Variation Order; and

determining whether to proceed with the Subconsultant to the Delivery Phase.

Strategic Notice Event Remediation Plan

If notified by the Consultant under clause 19.3(d), the Subconsultant must prepare and submit a draft Strategic Notice Event Remediation Plan to the Consultant's Representative for approval within 10 business days of the Consultant's notice (or longer period agreed in writing by the Consultant's Representative).

A draft Strategic Notice Event Remediation Plan prepared by the Subconsultant under paragraph (a) must include the following information:

how the Subconsultant will address the Strategic Notice Event to minimise the impact of the Strategic Notice Event on the Subcontract Services and the Works;

confirmation that the implementation of the Strategic Notice Event Remediation Plan will not in any way impact on the compliance by the Subconsultant with its other obligations under the Subcontract;

how the Subconsultant will seek to ensure that any events of a similar nature to the Strategic Notice Event do not occur again;

if the Strategic Notice Event involves a Material Change, how the Material Change will impact the Subconsultant's original agreement with the Consultant; and

any other matter reasonably requested by the Consultant.

The Consultant's Representative will review the draft Strategic Notice Event Remediation Plan and either approve it or provide the Subconsultant with the details of any changes that are required. The Subconsultant must make any changes reasonably requested by the Consultant's Representative and resubmit the draft Strategic Notice Event Remediation Plan to the Consultant's Representative within 5 business days of the request (or longer period agreed in writing by the Consultant's Representative). This paragraph (c) will apply to any resubmitted draft Strategic Notice Event Remediation Plan.

Without limiting its other obligations under the Subcontract, the Subconsultant must:

comply with each Strategic Notice Event Remediation Plan as approved by the Consultant's Representative; and

provide such reports and other information about the Subconsultant's progress in implementing the Strategic Notice Event Remediation Plan as may be reasonably requested by the Consultant's Representative.

Additional Obligations in respect of Known or Suspected Fraud or Corruption

- Without limiting the Subconsultant's other obligations under this clause 19, the Subconsultant must:

proactively:

take all necessary measures to prevent, detect and investigate any known or suspected Fraud or Corruption which is occurring or has occurred in connection with the Subcontract or the Subcontract Services (including all measures directed by the Consultant's Representative);

take all necessary corrective action to mitigate any loss or damage to the Consultant and the Commonwealth resulting from known or suspected Fraud or Corruption to the extent that the Fraud or Corruption was caused or contributed to by the Subconsultant or any of its officers, employees or agents and put the Consultant and the Commonwealth in the position it would have been in if the Fraud or Corruption had not occurred (including all corrective action directed by the Consultant's Representative); and

take all reasonable steps to ensure that any of its officers, employees or agents that report any known or suspected Fraud or Corruption which is occurring or has occurred in connection with the Subcontract or the Subcontract Services are protected from reprisals; and

provide all assistance reasonably required in respect of any investigation undertaken by the Consultant, the Commonwealth or any third party investigator appointed by either of them in respect of the known or suspected Fraud or Corruption.

Release

- The Subconsultant must bear, and releases the Consultant in respect of all costs, expenses, losses, damages or liabilities suffered or incurred by the Subconsultant or any other person or entity arising out of or in connection with the Strategic Notice Event or the exercise of any of the Consultant's Representative's or the Consultant’s absolute discretions under clause 19.

Subconsultant's Compliance

Nothing in this clause 19 requires the Subconsultant to act in any manner or disclose any information which would:

breach an obligation of confidentiality that existed prior to the date the Strategic Notice Event occurred, that is owed to an unrelated third party;

cause the Subconsultant to breach any law or regulation or contractual obligation regarding privacy or security (in Australia or outside of Australia);

have the effect of waiving legal professional privilege (or any equivalent privilege in Australia or outside of Australia) in relation to the information; or

breach the rules of a stock exchange or any similar body on which the Subconsultant, or any Related Body Corporate of the Subconsultant, is listed, which require the information to be first disclosed to the stock exchange or body. In this case, the Subconsultant must disclose the information to the Consultant's Representative promptly after disclosure is made to the stock exchange or body.

Notwithstanding any restriction that may apply in respect of specific information, such as that described in paragraph (a), the Subconsultant must use reasonable endeavours to make any disclosures and take reasonable steps to ensure that the overarching intent of this clause 19 is achieved.

FINANCIAL VIABILITY

The Subconsultant:

warrants that, on the Award Date and on the date of submitting each payment claim under clause 11.2, it has the financial viability necessary to perform the Subcontract Services, achieve Completion and otherwise meet its obligations under the Subcontract; and

acknowledges and agrees that the Consultant has:

entered into the Subcontract;

if applicable, made payments to the Subconsultant under clause 11.5; and

if applicable, proceeded to the Delivery Phase,

strictly on the basis of, and in reliance upon, the obligations and warranties set out in clause 20.

The Subconsultant must keep the Consultant’s Representative fully and regularly informed as to all financial viability matters which could adversely affect the Subconsultant's ability to perform the Subcontract Services, achieve Completion or otherwise meet its obligations under the Subcontract, including any potential or actual change in the Subconsultant’s financial viability.

The Consultant’s Representative may (in its absolute discretion) at any time request the Subconsultant to:

provide the Consultant’s Representative with a solvency statement in the form required by the Consultant with respect to the Subconsultant, properly completed and duly executed by the Subconsultant; and

ensure its Financial Representative is available to provide the Consultant’s Representative and any independent financial adviser engaged by the Consultant with financial information and documents (including internal monthly management accounts), answer questions, co-operate with and do everything necessary to assist the Consultant, the Consultant’s Representative and the independent financial adviser engaged by the Consultant for the purpose of demonstrating that the Subconsultant has the financial viability necessary to perform the Subcontract Services, achieve Completion and otherwise meet its obligations under the Subcontract.

If the Consultant considers (in its absolute discretion) that there could be or has been a change in the Subconsultant's financial viability which could adversely affect the Subconsultant's ability to perform the Subcontract Services, achieve Completion or otherwise meet its obligations under the Subcontract, the Consultant’s Representative may (in its absolute discretion) direct the Subconsultant to take such steps as the Consultant considers necessary to secure the performance of the Subcontract Services, Completion and the meeting of its obligations under the Subcontract, including requiring the Subconsultant to:

provide a deed of guarantee and undertaking in the form required by the Consultant;

provide a Subconsultant Deed of Covenant; or

provide collateral warranties in the form required by the Consultant.

The Subconsultant acknowledges and agrees that:

nothing in clause 20 will limit, reduce, or otherwise affect any of the rights of the Consultant under other provisions of the Subcontract or otherwise at law or in equity; and

clause 20 does not give the Subconsultant any rights.

ESTATE INFORMATION

Subconsultant Estate Information Obligations

The Subconsultant must:

carry out and fulfil all Subconsultant Estate Information Obligations;

fully co-operate with, provide information to and do all other things to assist, the Consultant and the Other Contractors to comply with their Estate Information obligations (including as they relate to the Work Health and Safety Legislation);

ensure that all Subconsultant Estate Information Obligations are carried out within any applicable timeframe prescribed by, or determined in accordance with, the Subcontract or the Defence Estate Information Management Requirements or as otherwise required by the Consultant's Representative; and

without limiting the foregoing if requested by the Consultant's Representative, provide Project Documents and such other documents, drawings, recordings or other information required for the occupation, use, operation and maintenance of the Works or each Stage (as defined in the Construction Contract) within the period specified by the Consultant's Representative in such request.

The Subconsultant warrants that all Estate Information assessed, created, managed, updated and recorded in accordance with this clause 21 will be:

prepared and completed in accordance with the requirements of the Subcontract; and

complete, fit for purpose and free from errors and omissions.

No Obligation to Review

The Consultant's Representative does not assume or owe any duty of care to the Subconsultant to review, or in reviewing, any Estate Information submitted by the Subconsultant for errors, omissions or compliance with the Subcontract.

No review of, comments upon, consent to or rejection of, or failure to review or comment upon or consent to or reject, any Estate Information prepared by the Subconsultant or any other direction by the Consultant's Representative about, or any other act or omission by the Consultant's Representative or otherwise by or on behalf of the Consultant or the Commonwealth in relation to, any Estate Information will:

relieve the Subconsultant from, or alter or affect, the Subconsultant's obligations under the Subcontract or otherwise at law or in equity; or

prejudice the Consultant's rights against the Subconsultant under the Subcontract or otherwise at law or in equity.

- SUBCONTRACT PARTICULARS

| CLAUSE 1 - GLOSSARY OF TERMS, INTERPRETATION AND MISCELLANEOUS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Completion - additional conditions precedent to Completion: (Clause 1.1) |  |  |  |  |  |
| Consultant: (Clause 1.1) |  |  |  |  |  |
| Consultant's Design Management Plan: (Clause 1.1) |  |  |  |  |  |
| Consultant's Environmental Management and Sustainability Plan: (Clause 1.1) |  |  |  |  |  |
| Consultant's Project Lifecycle and HOTO Plan: (Clause 1.1) |  |  |  |  |  |
| Consultant's Project Plans (additional): (Clause 1.1) |  |  |  |  |  |
| Consultant's Quality Plan: (Clause 1.1) |  |  |  |  |  |
| Consultant's Representative: (Clause 1.1) |  |  |  |  |  |
| Consultant's Site Management Plan: (Clause 1.1) |  |  |  |  |  |
| Consultant's Work Health and Safety Plan: (Clause 1.1) |  |  |  |  |  |
| Date for Completion (of a Milestone): (Clause 1.1) | Milestones |  | Date for Completion |  |  |
|  | [IF NO PHASES] |  |  |  |  |
|  | [IF TWO PHASES] |  |  |  |  |
|  | Planning Phase: |  |  |  |  |
|  | Delivery Phase: |  |  |  |  |
| Date for Delivery Phase Agreement: (Clause 1.1) | [IF CLAUSE 9 APPLIES, INSERT DATE FOR DELIVERY PHASE AGREEMENT. OTHERWISE, INSERT "NOT APPLICABLE"] |  |  |  |  |
| Defence Asbestos Register: (Clause 1.1) |  |  |  |  |  |
| Delivery Phase Fee Proposal: (Clause 1.1) | [WHERE CLAUSE 9 APPLIES, INSERT: "AS SET OUT IN ATTACHMENT 1 TO THESE SUBCONTRACT PARTICULARS", OTHERWISE INSERT "NOT APPLICABLE"] |  |  |  |  |
| Design Services Contract: (Clause 1.1) |  |  |  |  |  |
| DSC Contract Administrator: (Clause 1.1) |  |  |  |  |  |
| Environmental Management and Sustainability Plan (additional): (Clause 1.1) | [CONSULTANT TO INCLUDE (AMONG OTHER THINGS) ANY ADDITIONAL MATTERS ARISING FROM ITS SUPPLIER ENVIRONMENTAL SUSTAINABILITY PLAN UNDER THE DESIGN SERVICES CONTRACT] |  |  |  |  |
| Environmental Objectives (additional): (Clause 1.1) |  |  |  |  |  |
| Environmental Requirements (additional): (Clause 1.1) |  |  |  |  |  |
| Executive Negotiators: (Clause 1.1) | Consultant: Subconsultant: [To be inserted following selection of the successful Tenderer] |  |  |  |  |
| Fee: (Clause 1.1) | [IF NO PHASES] |  |  |  |  |
|  | Fee: |  |  | $[To be inserted following selection of the successful Tenderer] GST exclusive |  |
|  | [IF TWO PHASES] |  |  |  |  |
|  | Planning Phase Fee: |  |  | $[To be inserted following selection of the successful Tenderer] GST exclusive |  |
|  | Delivery Phase Fee: |  |  | As defined in clause 1.1 of the Conditions of Subcontract |  |
| Indicative Delivery Phase Fee: (Clause 1.1) | $[To be inserted following selection of the successful Tenderer] GST exclusive |  |  |  |  |
| Milestones: (Clause 1.1) | Milestone |  | Description |  |  |
|  | [IF NO PHASES] |  |  |  |  |
|  | [IF TWO PHASES] |  |  |  |  |
|  | Planning Phase: |  |  |  |  |
|  | Delivery Phase: |  |  |  |  |
| Pandemic Adjustment Event (additional): (Clause 1.1) |  |  |  |  |  |
| Preliminary Design Solution (if any): (Clause 1.1) |  |  |  |  |  |
| Project Plans (additional): (Clause 1.1) | [CONSULTANT TO INSERT ANY ADDITIONAL PLANS REQUIRED] |  |  |  |  |
| Quality Manager: (Clause 1.1) | [To be inserted following selection of the successful Tenderer] |  |  |  |  |
| Quality Objectives (additional): (Clause 1.1) |  |  |  |  |  |
| Quality Plan (additional): (Clause 1.1) |  |  |  |  |  |
| Regional Base Services Contractor: (Clause 1.1) |  |  |  |  |  |
| Schedule of Collateral Documents: (Clause 1.1) | - Payment Claim - Payment Statement - Expert Determination Agreement - Subconsultant Deed of Covenant - Subconsultant Design Certificate - Delivery Phase Agreement Minutes |  |  |  |  |
| Site: (Clause 1.1) |  |  |  |  |  |
| Site Management Plan (additional): (Clause 1.1) |  |  |  |  |  |
| Subconsultant: (Clause 1.1) | [To be inserted following selection of the successful Tenderer] |  |  |  |  |
| Subconsultant's Representative: (Clause 1.1) | [To be inserted following selection of the successful Tenderer] |  |  |  |  |
| Subcontract - other documents forming part of the Subcontract: (Clause 1.1) |  |  |  |  |  |
| WOL Objectives (additional): (Clause 1.1) |  |  |  |  |  |
| Work Health and Safety Plan (additional): (Clause 1.1) |  |  |  |  |  |
| Works: (Clause 1.1) |  |  |  |  |  |
| Governing law: (Clause 1.3(a)) |  |  |  |  |  |
| CLAUSE 2 - ROLE OF THE SUBCONSULTANT |  |  |  |  |  |
| Statutory Requirements with which the Subconsultant does not need to comply: (Clause 2.10(a)) |  |  |  |  |  |
| Approvals which the Subconsultant is to obtain: (Clause 2.10(b)) |  |  |  |  |  |
| Method of Work Plan for Airfield Activities and Operating Airfield: (Clause 2.15) | Clause 2.15 [DOES/DOES NOT] apply. (Clause 2.15 does not apply unless otherwise stated) |  |  |  |  |
| CLAUSE 3 - ROLE OF THE CONSULTANT |  |  |  |  |  |
| Other conditions precedent to Site access: (Clause 3.3(f)) |  |  |  |  |  |
| CLAUSE 4 - PERSONNEL |  |  |  |  |  |
| Subconsultant's Key People: (Clause 4.4(a)(i)) | Person |  | Position |  |  |
|  | [To be inserted following selection of the successful Tenderer] |  |  |  |  |
| CLAUSE 5 - INSURANCE |  |  |  |  |  |
| Insurance policies required to be effected by the Subconsultant: (Clause 5.1) | [CONSULTANT AND CONSULTANT'S REPRESENTATIVE TO CONSIDER AND SEEK ADVICE ON LEVELS AND LIMITS OF INSURANCES FROM THE CONSULTANT'S INSURANCE BROKER. WHERE THE CONSULTANT/CONSULTANT'S REPRESENTATIVE INTENDS TO INCLUDE INDICATIVE LEVELS OF INSURANCE, THE WORDS "[To be inserted following selection of the successful Tenderer, indicatively $[INSERT AMOUNT]]" AND THE RELEVANT AMOUNT SHOULD BE INCLUDED. WHERE AN INSURANCE IS NOT REQUIRED, OR THE RELEVANT PARTICULAR DOES NOT APPLY, INSERT "Not Applicable". APPROPRIATE ADVICE SHOULD BE SOUGHT WHERE THERE ARE QUESTIONS AS TO WHICH OF THE INSURANCES SPECIFIED BELOW ARE REQUIRED FOR A SPECIFIC PROJECT] Public Liability Insurance If written on an occurrence basis: Amount of Cover: $ for each and every occurrence for public liability claims If written on a claims made basis: Amount of Cover: $ per claim and $ in the aggregate |  |  |  |  |
|  | Workers Compensation Insurance Amount of Cover: Amount of Cover prescribed by Statutory Requirement in the State or Territory in which the Subcontract Services are performed or the Subconsultant’s employees perform work, are employed or normally reside |  |  |  |  |
|  | Employers' Liability Insurance Amount of Cover: The amount that an expert professional provider of the Subcontract Services would purchase, which must not be less than $ |  |  |  |  |
|  | Professional Indemnity Insurance Amount of Cover: $ per claim and $ in the aggregate |  |  |  |  |
|  | Other Insurances: (Clause 5.1(a)(v)) [CONSULTANT’S REPRESENTATIVE TO CONSIDER AND SEEK ADVICE ON OTHER SPECIFIC AND ADDITIONAL INSURANCES THAT MAY BE REQUIRED] |  |  |  |  |
| Insurance policies required to be effected by the Consultant: (Clause 5.2) |  |  |  |  |  |
| Run-off period for Public Liability Insurance if written on a claims made basis: (Clause 5.4(a)(ii)) | Where any part of the Subcontract Services are carried out in the Australian Capital Territory, New South Wales, Victoria, Tasmania, South Australia or the Northern Territory: 11 years. Otherwise: 7 years. |  |  |  |  |
| Run-off period for Professional Indemnity Insurance: (Clause 5.4(c)) | Where any part of the Subcontract Services are carried out in the Australian Capital Territory, New South Wales, Victoria, Tasmania, South Australia or the Northern Territory: 11 years. Otherwise: 7 years. |  |  |  |  |
| Maximum aggregate liability of the Subconsultant to the Consultant: (Clause 5.8) | $ [CONSULTANT TO CONSIDER APPROPRIATE AMOUNT BY REFERENCE TO A DETAILED RISK ANALYSIS OF THE SUBCONTRACT SERVICES AND THE PROJECT] |  |  |  |  |
| CLAUSE 6 - DESIGN AND DOCUMENTATION |  |  |  |  |  |
| Number of days for review: (Clause 6.3(a)(ii)) | days [CONSULTANT AND CONSULTANT'S REPRESENTATIVE TO CONSIDER SUFFICIENT LENGTH OF TIME TO ALLOW FOR REVIEW] |  |  |  |  |
| Number of copies of Design Documentation to be submitted by the Subconsultant to the Consultant's Representative: (Clause 6.5) |  |  |  |  |  |
| Design Documentation hard copy requirements: (Clause 6.5(a)) | Compatible with Autocad 14 To scale Printed in black ink on white or transparent ISO Standard Sheet (size A1, A3, A4 or as determined by the Consultant's Representative) |  |  |  |  |
| Design Documentation electronic copy requirements: (Clause 6.5(b)) | Compatible with Autocad 14 CD-ROM or as determined by the Consultant's Representative |  |  |  |  |
| Order of precedence of documents in the case of any ambiguity, discrepancy or inconsistency: (Clause 6.10(a)) | 1. Formal Agreement 2. Conditions of Subcontract 3. Special Conditions 4. Subcontract Particulars 5. Brief 6. Any other documents forming part of the Subcontract (as specified in the relevant item under clause 1.1 in these Subcontract Particulars) 7. Design Documentation (which has not been rejected under clause 6.3) 8. Project Plans |  |  |  |  |
| Number of days for sample review: (Clause 6.14(b)(ii)) | days |  |  |  |  |
| CLAUSE 7 - QUALITY |  |  |  |  |  |
| Number of days for submission of Project Plans: (Clause 7.4(a)(ii)A) | Design Management Plan: |  | days |  |  |
|  | Environmental Management and Sustainability Plan: |  | days |  |  |
|  | Estate Information Provision Plan: |  | days |  |  |
|  | Project Lifecycle and HOTO Plan: |  | days |  |  |
|  | Quality Plan: |  | days |  |  |
|  | Site Management Plan: |  | days |  |  |
|  | Work Health and Safety Plan: |  | days |  |  |
|  | [IF CLAUSE 2.15 DOES NOT APPLY, DELETE THIS ITEM] Method of Work Plan for Airfield Activities: |  | days |  |  |
|  | Other [SPECIFY]: |  | days |  |  |
| Number of days for review of Project Plans: (Clause 7.4(a)(ii)B) | Design Management Plan: |  | days |  |  |
|  | Environmental Management and Sustainability Plan: |  | days |  |  |
|  | Estate Information Provision Plan: |  | days |  |  |
|  | Project Lifecycle and HOTO Plan: |  | days |  |  |
|  | Quality Plan: |  | days |  |  |
|  | Site Management Plan: |  | days |  |  |
|  | Work Health and Safety Plan: |  | days |  |  |
|  | [IF CLAUSE 2.15 DOES NOT APPLY, DELETE THIS ITEM] Method of Work Plan for Airfield Activities: |  | days |  |  |
|  | Other [SPECIFY]: |  | days |  |  |
| CLAUSE 8 - TIME |  |  |  |  |  |
| Maximum intervals between program updates by Subconsultant: (Clause 8.2(b)(ii)) |  |  |  |  |  |
| Program format to be compatible with: (Clause 8.2(b)(iv)) | [PRIMAVERA SURETRAK/MICROSOFT PROJECT] or approved equivalent |  |  |  |  |
| CLAUSE 9 - PLANNING PHASE AND DELIVERY PHASE |  |  |  |  |  |
| Planning Phase and Delivery Phase: (Clause 9) | Clause 9 [DOES/DOES NOT] apply. (Clause 9 applies unless otherwise stated) |  |  |  |  |
| CLAUSE 11 - PAYMENT |  |  |  |  |  |
| Times for submission of payment claims by the Subconsultant to Consultant’s Representative: (Clause 11.2(a)) | Monthly on the [To be inserted following selection of the successful Tenderer] day of each month, but, where applicable, subject to the achievement of the applicable milestone in the Fee Payment Schedule |  |  |  |  |
| Email address for copy of tax invoice: (Clause 11.5(a)) |  |  |  |  |  |
| Number of business days for payment: (Clause 11.5(b)) | To the extent that the relevant part of the Subcontract Services is carried out in: - 1. Queensland, New South Wales or the Australian Capital Territory: 5; or - 2. any other State or Territory: 10. |  |  |  |  |
| Interest Rate: (Clause 11.9) | - In the case of damages - the Australian Taxation Office-sourced General Interest Charge Rate current at the due date for payment or such other rate nominated in writing from time to time by the Consultant's Representative. - In the case of late payments - the greater of: the rate in paragraph (1); and the rate of interest prescribed under any applicable Security of Payment Legislation. |  |  |  |  |
| Appointed Adjudicator/Prescribed Appointer/Authorised Nominating Authority: (Clause 11.14(d)) | To the extent that the relevant part of the Subcontract Services is carried out in: 1. the Northern Territory, the Resolution Institute of the Northern Territory Chapter; 2. Western Australia, the Resolution Institute of the Western Australian Chapter; 3. Victoria, any one of the following: (a) Resolution Institute, Victorian Chapter; (b) Building Adjudication Victoria Inc; or (c) Rialto Adjudications Pty Ltd; or 4. any other State or Territory (save for Queensland), the Resolution Institute of the Chapter in that State or Territory. |  |  |  |  |
| Facilities and infrastructure accounting (additional): (Clause 11.17(b)) |  |  |  |  |  |
| CLAUSE 12 - TERMINATION |  |  |  |  |  |
| Number of days to remedy breach: (Clauses 12.3(c) and 12.4(b)) | days |  |  |  |  |
| CLAUSE 13 - DISPUTE RESOLUTION |  |  |  |  |  |
| Directions to be the subject of an expert determination if disputed: (Clause 13.2) | Directions under clauses 2.11(c), 2.11(d), 2.13(a)(ii), 2.14, 8.4(b)(ii)B, 8.8, 10.3(b), 10.3(c), 11.4, 11.18(b), 12.8(a)(i), 16.3(e)(ii) and 16.3(e)(iii). |  |  |  |  |
| Industry expert who will conduct expert determinations: (Clause 13.3(a)(i)) |  |  |  |  |  |
| Nominating authority for industry expert: (Clause 13.3(a)(ii)) | (The Chair for the time being of the Resolution Institute unless otherwise specified) |  |  |  |  |
| CLAUSE 14 - NOTICES |  |  |  |  |  |
| Address and email address, for the giving or serving of notices, upon: (Clause 14.7(b)(i)) | Commonwealth: Address (not PO Box): Email address: Attention: DSC Contract Administrator: Address (not PO Box): Email address: Attention: Consultant: Address (not PO Box): Email address: Attention: Consultant's Representative: Address (not PO Box): Email address: Attention: Subconsultant: Address (not PO Box): [To be inserted following selection of the successful Tenderer] Email address: [To be inserted following selection of the successful Tenderer] Attention: [To be inserted following selection of the successful Tenderer] |  |  |  |  |
| CLAUSE 16 - GENERAL |  |  |  |  |  |
| Defence's Security Alert System level: (Clause 16.3(d)(i)) | ("Aware" if not otherwise specified) |  |  |  |  |
| Shadow Economy Procurement Connected Policy: (Clause 16.13) | Clause 16.13 [DOES/DOES NOT] apply. (Clause 16.13 applies unless otherwise stated) [CLAUSE 16.13 WILL APPLY WHERE THE SUBCONTRACT PRICE IS VALUED AT (OR ESTIMATED TO BE OVER) $4 MILLION (INCLUSIVE OF GST)] |  |  |  |  |
| CLAUSE 17 - COMMERCIAL-IN-CONFIDENCE INFORMATION |  |  |  |  |  |
| Commercial-in-Confidence Information: (Clause 17) | Clause 17 [does/does not] apply. [To be inserted following selection of the successful Tenderer] (Clause 17 does not apply unless otherwise stated) |  |  |  |  |
| Information which is Commercial-in-Confidence Information: (Clause 17) | Specific Information | Justification |  |  | Period of confidentiality |
|  | [To be inserted following selection of the successful Tenderer] | [To be inserted following selection of the successful Tenderer] |  |  | [To be inserted following selection of the successful Tenderer] |
| CLAUSE 18 - INFORMATION SECURITY - SENSITIVE AND CLASSIFIED INFORMATION |  |  |  |  |  |
| Sensitive and Classified Information: (Clause 18.1(a)) | DISP membership [IS/IS NOT] required. Where DISP membership is required: [REFER TO CONTROL 16.1 OF THE DSPF (AVAILABLE AT https://www.defence.gov.au/business-industry/industry-governance/defence-security-principles-framework) FOR GUIDANCE AS TO WHEN DISP MEMBERSHIP SHOULD BE REQUIRED AND THE RELEVANT LEVELS FOR EACH DOMAIN] |  |  |  |  |
|  | DISP Membership / Security Domain |  |  | Level |  |
|  | Governance |  |  | [INSERT LEVEL AND SPECIFIC DETAILS (AS REQUIRED) NOTING THAT, IN ACCORDANCE WITH CONTROL 16.1 OF THE DSPF, THIS MUST EQUAL THE HIGHEST LEVEL REQUIRED FOR THE OTHER THREE DOMAINS BELOW. INSERT "NOT APPLICABLE" IN THIS AND BELOW ROWS IF DISP MEMBERSHIP IS NOT REQUIRED] |  |
|  | Personnel Security |  |  | [INSERT LEVEL AND SPECIFIC DETAILS (AS REQUIRED)] |  |
|  | Physical Security |  |  | [INSERT LEVEL AND SPECIFIC DETAILS (AS REQUIRED)] |  |
|  | Information / Cyber Security |  |  | [INSERT LEVEL AND SPECIFIC DETAILS (AS REQUIRED)] |  |
| Minimum level of security clearance and roles required to hold such security clearance: (Clause 18.2(e)(ii)A) | Role |  |  | Minimum level of security clearance |  |
|  | [INSERT, HAVING REGARD TO THE DSPF] |  |  | [INSERT, HAVING REGARD TO THE DSPF AND TABLE 39 OF THE PROTECTIVE SECURITY POLICY FRAMEWORK GUIDELINES AVAILABLE AT https://www.protectivesecurity.gov.au/] |  |
| Anticipated highest security classification of information and assets: (Clause 18.2(f)) | [INSERT, HAVING REGARD TO THE DSPF, INCLUDING CONTROL 10.1] |  |  |  |  |

- Attachment 1 to the SUBContract Particulars - Delivery Phase Fee Proposal

[INSERT IF CLAUSE 9 OF THE CONDITIONS OF SUBCONTRACT APPLIES AND THERE ARE TWO PHASES. OTHERWISE, INSERT "NOT USED"]

Annexure 1 - Brief

Annexure 2 - SPECIAL CONDITIONS

[THE TENDER ADMINISTRATOR/CONSULTANT’S REPRESENTATIVE ARE TO REVIEW THIS LIST OF POTENTIAL SPECIAL CONDITIONS AND ADVISE WHICH ONES ARE REQUIRED FOR THE SUBCONTRACT. THE TENDER ADMINISTRATOR/CONSULTANT’S REPRESENTATIVE ARE ALSO REQUIRED TO IDENTIFY ANY AMENDMENTS TO THESE SPECIAL CONDITIONS OR ANY ADDITIONAL SPECIAL CONDITIONS WHICH MAY BE REQUIRED. NOTE THAT THERE ARE MORE EXTENSIVE SPECIAL CONDITIONS IN THE DESIGN SERVICES CONTRACT WHICH MAY BE OF RELEVANCE (WITH AMENDMENT) TO THE SUBCONTRACT]

- USE OF HAZARDOUS SUBSTANCES (INCLUDING HAZARDOUS CHEMICALS)

  - The Consultant

    - The Commonwealth and the Consultant seek to ensure that:

      - workers and other persons are not exposed to Hazardous Substances as a consequence of activities conducted on Commonwealth Premises and from work carried out as part of its business or undertaking, unless the Hazardous Substances are managed in accordance with subparagraph (ii); and

      - risks to health and safety concerning Hazardous Substances are managed in accordance with the WHS Legislation.

    - To the extent that the Consultant is legally required to do so, the Consultant will notify the Subconsultant of Hazardous Substances known to it to be within:

Commonwealth Premises relevant to the Subcontract Services; and

any other Commonwealth property (including plant and equipment) provided to the Subconsultant for the purposes of the Subcontract Services.

The Subconsultant

The Subconsultant acknowledges Hazardous Substances may be present within:

Commonwealth Premises relevant to the Subcontract Services; or

any other Commonwealth property (including plant and equipment) provided to the Subconsultant for the purposes of the Subcontract Services.

Without limiting paragraph (d) the Subconsultant must provide full details of each Hazardous Substance (including the proposed location and protective covering) proposed to be used in the Subcontract Services or incorporated into the Works to the Consultant’s Representative as soon as possible after the Award Date (and in any event no later than 30 days prior to the proposed Hazardous Substance being used in the Subcontract Services or incorporated into the Works).

Without limiting paragraph (b), the Subconsultant must:

prepare a register of each Hazardous Substance to be:

used in the Subcontract Services;

incorporated into the Works;

held or stored by the Subconsultant on Site; or

transported by the Subconsultant to or from the Site or in or through Commonwealth Premises;

(Hazardous Substance Register);

provide the Hazardous Substance Register to the Consultant’s Representative prior to the Subconsultant:

handling or storing the Hazardous Substance on Site; or

transporting the Hazardous Substance to or from the Site or in or through Commonwealth Premises;

provide the Consultant’s Representative with an updated Hazardous Substance Register:

on each occasion that it is updated by the Subconsultant; and

otherwise as requested by the Consultant’s Representative;

without limiting subparagraph (i), provide a Safety Data Sheet (SDS) in the form required by the Consultant for entry into the ChemAlert database for each Hazardous Substance to be:

used in the Subcontract Services; or

incorporated into the Works;

provide the SDS under subparagraph (iv) and any other information concerning the risks and hazards associated with the Hazardous Substance to the Consultant’s Representative prior to the Hazardous Substance being used in the Subcontract Services or incorporated into the Works;

provide the Consultant’s Representative any updated SDS from the manufacturer, importer or supplier of each relevant Hazardous Substance:

on each occasion an updated SDS is provided by the manufacturer, importer or supplier of the relevant Hazardous Substance; and

otherwise as requested by the Consultant’s Representative;

without limiting subparagraphs (i) - (iv) prepare information in the form required by the Consultant in accordance with the WHS Legislation (including any applicable information regarding use, handling, storage, locations, maximum storage quantities and volumes) for entry into the ChemAlert database for each Hazardous Substance to be:

used in the Subcontract Services;

incorporated into the Works; or

used, handled or stored on Commonwealth Premises,

(ChemAlert Information);

provide the ChemAlert Information prepared under subparagraph (vii) to the Consultant’s Representative:

in its reports under clause 4.7 of the Conditions of Subcontract; and

otherwise as requested by the Consultant’s Representative;

update the ChemAlert Information and provide the updated ChemAlert Information to the Consultant’s Representative:

in its reports under clause 4.7 of the Conditions of Subcontract; and

otherwise as requested by the Consultant’s Representative; and

do all things necessary to assist the Consultant’s Representative to enter the SDS, ChemAlert Information and all other information into the ChemAlert database.

The Subconsultant must not use, handle or store a Hazardous Substance which falls within one or more of the categories of Hazardous Chemical described in clause 1.3(d) in connection with the Subcontract Services or the Works, without the prior written consent of the Consultant’s Representative.

Without limiting paragraph (b), in its request for consent under paragraph (d), the Subconsultant must provide:

details of the Hazardous Substance and the relevant category under clause 1.3(d);

details of the purpose, use, handling or storage of each Hazardous Substance which falls within one or more of the categories of Hazardous Chemical described in clause 1.3(d); and

for each Hazardous Substance which falls within one or more of the following categories:

clause 1.3(d)(i) or 1.3(d)(ii), a copy of all Approvals for use, handling or storage;

clause 1.3(d)(v) or 1.3(d)(vii), details of how the health of workers using, handling or storing such Hazardous Chemical will be monitored in accordance with WHS Legislation; and

clause 1.3(d)(vi), a copy of:

all notices given to a relevant regulator; and

all licences required to be held by the Subconsultant,

- in relation to use, storage or handling.

Without limiting clause 6.15 of the Conditions of Subcontract or any other provision of the Subcontract, the Subconsultant must:

comply with any applicable Code of Practice;

ensure that all documentation (including all Design Documentation and other Project Documents) concerning Hazardous Substances (including in relation to assembly, maintenance and operation) identifies the nature of the hazard and risk (including those risks which may remain after Completion (as defined in the Construction Contract) and after the end of the last Defects Liability Period (as defined in the Construction Contract));

ensure that all goods incorporated into the Works comply with WHS Legislation and any Statutory Requirements relating to Hazardous Substances;

ensure that all Hazardous Substances used in the Subcontract Services or used in (or incorporated into) the Works are correctly labelled and packaged in accordance with WHS Legislation and Statutory Requirements;

notify the Consultant’s Representative within 14 days of becoming aware of any non-hazardous substance which could be substituted for the Hazardous Substance without significant detriment to the performance of the Subcontract Services or the Works; and

be able to demonstrate compliance with this paragraph (f) at the request of the Consultant’s Representative.

Definitions

For the purposes of clause 1:

Code of Practice means a code of practice approved in accordance with the WHS Legislation.

Commonwealth Premises means any of the following that is owned or occupied by the Commonwealth:

an area of land or any other place (whether or not it is enclosed or built on);

a building or other structure; or

a vehicle, vessel or aircraft.

Dangerous Goods has the meaning given in the Australian Code for the Transport of Dangerous Goods by Road and Rail, as amended from time to time.

Hazardous Chemical has the meaning given in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth) and includes:

prohibited carcinogen, as defined in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth);

restricted carcinogen, as defined in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth);

hazardous chemicals the use of which is restricted under regulation 382 of the Work Health and Safety Regulations 2011 (Cth), including polychlorinated biphenyls;

Schedule 11 Hazardous Chemicals;

hazardous chemicals listed in Table 14.1 of Schedule 14 of the Work Health and Safety Regulations 2011(Cth);

Schedule 15 Chemical; and

lead as defined in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth).

Hazardous Substances means Ozone Depleting Substances, Synthetic Greenhouse Gases, Hazardous Chemicals or Dangerous Goods.

Ozone Depleting Substance means any substance identified as having ozone depleting potential in the Ozone Protection and Synthetic Greenhouse Gas Management Act 1989 (Cth) or any regulations made under that Act.

Schedule 11 Hazardous Chemical has the meaning given in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth).

Schedule 15 Chemical has the meaning given in subregulation 5(1) of the Work Health and Safety Regulations 2011 (Cth).

Synthetic Greenhouse Gas means any gas identified as a Synthetic Greenhouse Gas in the Ozone Protection and Synthetic Greenhouse Gas Management Act 1989 (Cth) or in any regulations made under that Act.

SITE RESTRICTIONS

The Site based Subcontract Services must be executed subject to the following restrictions:

[INSERT DESCRIPTION OF RESTRICTIONS].

REQUESTS FOR INFORMATION

Without limiting the Conditions of Subcontract, the Subcontract Services include responding to Requests for Information (Request for Information Subcontract Services). All documentation provided as part of the Request for Information Subcontract Services will be deemed to form part of the Design Documentation.

Without limiting the Conditions of Subcontract, the Subconsultant must:

perform the Request for Information Subcontract Services so as to ensure that the Request for Information Subcontract Services fully address each Request for Information, reduce the need for further Requests for Information and minimise the Commonwealth’s exposure to delay and extra costs under the Construction Contract to the maximum extent possible;

submit (or resubmit) the Design Documentation prepared as Request for Information Subcontract Services to the Consultant’s Representative in accordance with clause 6 of the Conditions of Subcontract;

perform the Request for Information Subcontract Services within the time required by the Consultant’s Representative, including so as to ensure that the Consultant’s Representative can issue the Design Documentation prepared by the Subconsultant in response to each Request for Information so as to minimise the Commonwealth’s exposure to delay and extra costs under the Construction Contract; and

for the purposes of performing the Request for Information Subcontract Services, ensure that its personnel and other resources have appropriate availability, qualifications, experience, ability and expertise.

For the purposes of clause 3 of the Special Conditions, Request for Information means any request made by a consultant or contractor to the Commonwealth or the Consultant requesting further information, instruction, guidance, advice or opinion (including in respect of the resolution of ambiguities, discrepancies or inconsistencies in the Design Documentation) or otherwise in respect of the Design Documentation.

CIVIL LIABILITY ACT (WESTERN AUSTRALIA)

In clause 13.18 of the Conditions of Subcontract, insert the following sentence at the end of the paragraph:

Further, all of the provisions comprising Part 1F of the Civil Liability Act 2002 (WA) are hereby expressly excluded from application to the Subcontract.

ADJUSTMENT OF TABLE OF VARIATION RATES AND PRICES

The Fee is not subject to rise and fall.

All rates and prices in the Table of Variation Rates and Prices are to be adjusted (using the formula set out below) annually on the anniversary of the Award Date.

The following formula shall be used to calculate the rise and fall of the Table of Variation Rates and Prices:

| Pn = Po x | In |
| --- | --- |
|  | Io |

Where:

Pn = the revised rate or price applying from the most recent annual anniversary of the Award Date.

Po = the rate or price applying at the Award Date.

In = the latest of the preceding March, June, September or December Price Revision Index published prior to the annual anniversary of the Award Date.

Io = the latest of the preceding March, June, September or December Price Revision Index published prior to the Award Date.

Price Revision Index = is the index set out below

| Description | Table | Group |
| --- | --- | --- |
| ABS Publication 6345.0 Labour Price Index | Table 5 | Private - Construction Index |

CHILD SAFETY

[THIS CLAUSE IS TO BE USED IN CIRCUMSTANCES WHERE THE SUBCONSULTANT AND ITS OFFICERS, EMPLOYEES, AGENTS, CONSULTANTS OR VOLUNTEERS WILL OR MAY INTERACT WITH CHILDREN DURING THE TERM OF THE SUBCONTRACT IN AN INCIDENTAL WAY. FOR EXAMPLE, IF THE SUBCONSULTANT IS CARRYING OUT ACTIVITIES THAT MAY BE PROVIDED ON A SCHOOL’S PREMISES EVEN WHERE INTERACTING WITH CHILDREN IS NOT A PART OF THE SUBCONTRACT SERVICES]

- If any part of the activities carried out by the Subconsultant under the Subcontract (including the Subcontract Services) involves the Subconsultant employing or engaging a person (whether as an officer, employee, agent, consultant or volunteer) that is required by State or Territory law to have a working with children check to undertake such activities or any part of such activities, the Subconsultant agrees:

without limiting its other obligations under the Subcontract, to comply with all State, Territory or Commonwealth law relating to the employment or engagement of people who work or volunteer with children in relation to such activities, including mandatory reporting and working with children checks however described; and

if requested, provide the Commonwealth at the Subconsultant’s cost, a statement of compliance with this clause, in such form as may be specified by the Commonwealth.

PRELIMINARY DESIGN SOLUTION

Without limiting the Subconsultant's obligations elsewhere in the Subcontract, the Subconsultant acknowledges and agrees that:

prior to the Award Date, [IT HAS/THE CONSULTANT’S OTHER DESIGN CONSULTANTS HAVE] prepared the Preliminary Design Solution;

it bears all risks howsoever they may arise as a result of the use by it of the Preliminary Design Solution;

the use of the Preliminary Design Solution by the Subconsultant does not affect any of its warranties or other obligations under the Subcontract or entitle it to make any Claim against the Consultant, arising out of, or in any way in connection with, such use;

if the Works are designed in accordance with the Preliminary Design Solution (as may be developed in accordance with the Subcontract), the Works will comply with the requirements of the Brief and satisfy all other requirements of the Subcontract; and

it must design the Works in accordance with the Preliminary Design Solution (as may be developed in accordance with the Subcontract), except to the extent where a Variation the subject of a direction by the Consultant's Representative necessitates a consequential change to the Preliminary Design Solution in which case the Subconsultant must notify the Consultant's Representative of such change.

EARLY CONTRACTOR INVOLVEMENT

[IF THE CONSULTANT HAS BEEN ENGAGED BY THE COMMONWEALTH UNDER THE DESIGN SERVICES CONTRACT ON THE BASIS OF AN APPROVED PROJECT DELIVERY METHODOLOGY INVOLVING ECI DELIVERY, THE CONSULTANT AND CONSULTANT'S REPRESENTATIVE SHOULD CONSIDER WHETHER A SPECIAL CONDITION IS REQUIRED TO INCLUDE THOSE ECI RELATED SERVICES UNDER THIS SUBCONTRACT]

JOINT AND SEVERAL LIABILITY

[THIS CLAUSE IS ONLY TO BE USED WHERE THE SUBCONSULTANT IS COMPRISED OF A JOINT VENTURE]

- The Subconsultant acknowledges and agrees:

that the joint and several liability of each entity comprising the Subconsultant, and the Subconsultant's obligations under this Subcontract, will not be qualified or otherwise limited by any matter whatsoever including as a result of, and notwithstanding, the operation of any provision in any joint venture or other agreement between the entities comprising the Subconsultant entered into for the purposes of tendering for or performing the Subcontract Services or otherwise in connection with this Subcontract; and

that the Consultant has entered into this Subcontract in reliance upon the Subconsultant's acknowledgement and agreement in paragraph (a).

PAYMENT TIMES PROCUREMENT CONNECTED POLICY

- [IF THE PAYMENT TIMES PROCUREMENT CONNECTED POLICY APPLIES TO THE DESIGN SERVICES CONTRACT, THE CONSULTANT SHOULD OBTAIN ITS OWN ADVICE IN RELATION TO THIS SPECIAL CONDITION AND ENSURE THAT IT IS SUITABLE FOR COMPLIANCE WITH ITS RELEVANT OBLIGATIONS]

This PT PCP Subcontract

- [THIS CLAUSE IS TO BE USED IN CIRCUMSTANCES WHERE THE SUBCONTRACT IS A PT PCP SUBCONTRACT (AS DEFINED IN THE DESIGN SERVICES CONTRACT) AND THE CONSULTANT SHOULD ADAPT IT AS REQUIRED TO COMPLY WITH THE REQUIREMENTS SET OUT IN THE DESIGN SERVICES CONTRACT AND BE OTHERWISE CONSISTENT WITH THE PAYMENT TIMES PROCUREMENT CONNECTED POLICY.  IF THIS SUBCONTRACT IS A REPORTING ENTITY SUBCONTRACT, THIS CLAUSE SHOULD BE PRESERVED, AND THE ADDITIONAL TEXT IN PARAGRAPH (A) SHOULD BE INCLUDED]

The Payment Times Procurement Connected Policy [applies/does not apply] to this Subcontract.  [IF THIS SUBCONTRACT IS NOT A PT PCP SUBCONTRACT, INCLUDE: Paragraphs (b) to (f) of this clause 10.1 of the Special Conditions will not apply when the Payment Times Procurement Connected Policy does not apply to this Subcontract.]

Notwithstanding clause 11.5 of the Conditions of Subcontract (and the corresponding Subcontract Particular), the Consultant will pay the Subconsultant:

subject to paragraph (c), within 20 days after the acknowledgement of the satisfactory delivery of the goods or services and receipt of a Correctly Rendered Invoice. If this period ends on a day that is not a business day, payment is due on the next business day; and

subject paragraph (d), for payments made by the Consultant after the payment is due, the unpaid amounts plus interest on the unpaid amount calculated in accordance with paragraphs (d) and (e);

Paragraph (b)(i) does not limit any obligation to comply with applicable Statutory Requirements that provide a shorter payment period than the period specified in paragraph (b)(i).

The Consultant is not required to pay any interest in accordance with paragraph (b)(ii) if either:

      - the Commonwealth has failed to pay the Consultant in accordance with the timeframes and requirements under the Design Services Contract; or

      - the amount of interest payable is less than $100 (GST inclusive).

Interest payable under paragraph (b)(ii):

      - will be simple interest calculated in respect of each day from the day after the amount was due and payable, up to and including the day that the Consultant effects payment; and

      - will be paid at the Australian Taxation Office-sourced General Interest Charge Rate current at the due date for payment.

The Subconsultant may make a complaint to the PT PCP Policy Team or to the Commonwealth in accordance with the Payment Times Procurement Connected Policy if there has been a non-compliance with the requirements of paragraph (b).

Downstream Reporting Entity Subcontract

- [THIS CLAUSE IS TO BE USED IN CIRCUMSTANCES WHERE THE SUBCONTRACT IS A REPORTING ENTITY SUBCONTRACT (AS DEFINED IN THE DESIGN SERVICES CONTRACT) AND THE CONSULTANT SHOULD ADAPT IT AS REQUIRED TO COMPLY WITH THE REQUIREMENTS SET OUT IN THE DESIGN SERVICES CONTRACT AND BE OTHERWISE CONSISTENT WITH THE PAYMENT TIMES PROCUREMENT CONNECTED POLICY]

    - If the Subconsultant enters into a PT PCP Subcontract, it must include provisions equivalent to those in clause 10.1(a) to (f) of the Special Conditions and state that the Payment Times Procurement Connected Policy applies to that PT PCP Subcontract.

    - If the Subconsultant enters into a Reporting Entity Subcontract, then that Reporting Entity Subcontract must include:

      - provisions equivalent to those in clause 10.1(a) to (f) of the Special Conditions and state that the Payment Times Procurement Connected Policy applies to that Reporting Entity Subcontract; and

      - obligations equivalent to this paragraph (b) (such that the obligations in this paragraph (b) are to continue to be flowed down the supply chain to all Reporting Entity Subcontractors).

Definitions

    - For the purposes of clause 10 of the Special Conditions:

      - Correctly Rendered Invoice means an invoice which is:

rendered in accordance with all of the requirements of the Subcontract; and

for amounts that are correctly calculated and due for payment and payable under the Subcontract.

Payment Times Procurement Connected Policy or PT PCP means the Payment Times Procurement Connected Policy available at https://treasury.gov.au/publication/p2021-183909, as amended from time to time.

PT PCP Policy Team means the relevant Minister, department or authority that administers or otherwise deals with the Payment Times Procurement Connected Policy on the relevant day.

PT PCP Subcontract means a subcontract between a Reporting Entity (having the meaning in the Payment Times Reporting Act 2020 (Cth), as updated from time to time), and another party (Other Party) where:

the subcontract is, wholly or in part, for the provision of goods or services for the purposes of the Subcontract;

both parties are carrying on business in Australia; and

the component of the subcontract for the provision of goods or services for the purposes of the Subcontract has a total value of less than, or is reasonably estimated to not exceed, $1,000,000 (GST inclusive) during the period of the subcontract, not including any options, extensions, renewals or other mechanisms that may be executed over the life of the subcontract (but including work or official orders entered into that are valued at up to $1,000,000 (GST inclusive) under standing offer or panel arrangements),

- but does not include the following subcontracts:

subcontracts entered into prior to the Reporting Entities' tender response for the Services;

subcontracts which contain standard terms and conditions put forward by the Other Party and which cannot reasonably be negotiated by the Reporting Entity; or

subcontracts for the purposes of:

procuring and consuming goods or services overseas; or

procuring real property, including leases and licences.

Reporting Entity Subcontract means a subcontract between the Subconsultant and another party to provide goods or services directly or indirectly to the Subconsultant for the purposes of the Subcontract where the value of such goods or services are estimated to exceed $4,000,000 (GST inclusive), and Reporting Entity Subcontractor has a corresponding meaning.

Annexure 3 - FEE PAYMENT SCHEDULE

| Payment milestone name | Payment milestone description | Amount (GST exclusive) |
| --- | --- | --- |
| Planning Phase: |  |  |
| [EG. 50% Schematic Design Report] | [EG. Each of the following has been achieved by the Subconsultant: - Design Documentation comprising the 50% Schematic Design Report (the required content of which is set out in section [INSERT] of the Brief) has been submitted to, and not rejected by, the Consultant's Representative in accordance with clause 6.3 of the Conditions of Subcontract; and - each of the other activities to be undertaken as described in section [INSERT] of the Brief has been completed in accordance with the requirements set out in the Brief.] | $[To be inserted following selection of successful Tenderer] |
| [INSERT] | [INSERT] | $[To be inserted following selection of successful Tenderer] |
| [INSERT] | [INSERT] | $[To be inserted following selection of successful Tenderer] |
| Delivery Phase: |  |  |
| [INSERT] | [INSERT] | $[To be inserted following selection of successful Tenderer] |
| [E.G. Performance of the Subcontract Services in respect of the Project in each relevant month in accordance with the Subcontract] | [E.G. Completion of all the Subcontract Services the Subconsultant is required to perform in the relevant month in accordance with the Subcontract.] | [E.G. The Subcontract value of the Subcontract Services performed by the Subconsultant in accordance with the Subcontract in each relevant month, provided that the balance of the Fee remaining once the Subconsultant has achieved all payment milestones up to and including the payment milestone [E.G. "COMPLETION UNDER THE CONSTRUCTION CONTRACT"] is not less than [INSERT RELEVANT PERCENTAGE I.E. 20% OF THE SUBCCONSULTANT'S DELIVERY PHASE FEE]] |
| [E.G. Completion under the Construction Contract] | [E.G. A notice of completion has been issued in respect of the last Stage of the Works under the Construction Contract.] | [E.G. $[To be inserted following selection of successful Tenderer]] |
| [INSERT] | [INSERT] | $[To be inserted following selection of successful Tenderer] |

Annexure 4 - TABLE OF VARIATION RATES AND PRICES