CONTRACT SUMMARY Work Breakdown Structure

Purose

This Annex sets out the Contract Summary Work Breakdown Structure (CSWBS) and associated CSWBS dictionary at Table 1.  The CSWBS defines the highest level decomposition of the Contract scope, and the Contract Work Breakdown Structure (CWBS) is derived from it.

Note to drafters:  Before releasing an RFT, drafters should review the list of CSWBS elements in the second column and amend the set of elements to ensure that the full scope of the Contract is properly identified.  For example:

Delete any of the deliverable Services (CSWBS 1.01 to 1.05) not required under the draft Contract (under SOW clauses 4 to 8).

Ensure that the associated CSWBS Dictionary definitions below are consistent with the scope of the required Services, as defined in the selected and tailored DSDs.

If Workstreams are incorporated into the Contract, it may be necessary to align the CSWBS definitions with the respective Workstreams.

Drafters should be aware that the CSWBS forms the highest-level breakdown of the pricing for Core Services, as set out in the ‘menu’ worksheet of the Support Pricing Work.

Table 1 - CSWBS and Associated Dictionary

| CSWBS ID | CSWBS Element | Definition |
| --- | --- | --- |
| 1.01 | Operating Support | This element includes the provision of the Operating Support Services required to achieve the Contract Outcomes, requirements and objectives, including the management efforts that are specific to the provision of those Services. This element includes all work required to satisfy the Operating Support provisions of the SOW and DSDs, including within the Approved plan(s) specific to the provision of Operating Support Services. Includes any Operating Support efforts required to support activities under other CSWBS Elements (eg, development of plans and reports and participation in Contract reviews). This element includes all of the Support Resources and any other goods and services specifically required for the provision of Operating Support Services, with the exception of those Support Resources or other goods or services that are addressed though other CSWBS Elements (eg, common resources not specific to Operating Support). This element excludes the support of the Support Resources. These activities are covered under other CSWBS Elements (eg, Maintenance of Operating Support equipment is covered under Maintenance Support, provision of Non-RIs for Operating Support equipment is covered under Supply Support, and personnel management for Operating Support personnel is covered under Support Services Management). |
| 1.02 | Engineering Support | This element includes the provision of the Engineering Services required to achieve the Contract Outcomes, requirements and objectives, including the management efforts that are specific to the provision of those Services. This element includes all work required to satisfy the Engineering Support provisions of the SOW and DSDs, including within the Approved plan(s) specific to the provision of Engineering Services. Includes any Engineering Support efforts required to support activities under other CSWBS Elements (eg, development of plans and reports and participation in Contract reviews). This element includes all of the Support Resources and any other goods and services specifically required for the provision of Engineering Services, with the exception of those Support Resources or other goods or services that are addressed though other CSWBS Elements (eg, common resources not specific to Engineering Support). This element excludes the support of the Support Resources. These activities are covered under other CSWBS Elements (eg, Maintenance of Engineering equipment is covered under Maintenance Support, provision of Non-RIs for Engineering equipment is covered under Supply Support, and personnel management for Engineering personnel is covered under Support Services Management). |
| 1.03 | Maintenance Support | This element includes the provision of the Maintenance Services required to achieve the Contract Outcomes, requirements and objectives, including the management efforts that are specific to the provision of those Services. This element includes all work required to satisfy the Maintenance Support provisions of the SOW and DSDs, including within the Approved plan(s) specific to the provision of Maintenance Services. Includes any Maintenance Support efforts required to support activities under other CSWBS Elements (eg, development of plans and reports and participation in Contract reviews). This element includes all of the Support Resources and any other goods and services specifically required for the provision of Maintenance Services, with the exception of those Support Resources or other goods or services that are addressed though other CSWBS Elements (eg, common resources not specific to Maintenance Support). Except in relation to Maintenance, this CWBS Element excludes the support of the Support Resources. These activities are covered under other CSWBS Elements (eg, Engineering support for Maintenance equipment (eg, S&TE) is covered under Engineering Support, provision of Non-RIs for Maintenance equipment is covered under Supply Support, and personnel management for Maintenance personnel is covered under Support Services Management). |
| 1.04 | Supply Support | This element includes the provision of the Supply Services required to achieve the Contract Outcomes, requirements and objectives, including the management efforts that are specific to the provision of those Services. This element includes the costs for the procurement of RIs, Non-RIs, Consumables and Packaging required by other CSWBS Elements, particularly Operating Support, Engineering Support, Maintenance Support and Training Support. This element includes all work required to satisfy the Supply Support provisions of the SOW and DSDs, including within the Approved plan(s) specific to the provision of Supply Services. Includes any Supply Support efforts required to support activities under other CSWBS Elements (eg, development of plans and reports and participation in Contract reviews). This element includes all of the Support Resources and any other goods and services specifically required for the provision of Supply Services, with the exception of those Support Resources or other goods or services that are addressed though other CSWBS Elements (eg, common resources not specific to Supply Support). This element excludes the support of the Support Resources. These activities are covered under other CSWBS Elements (eg, Maintenance of Supply equipment (eg, materials handling equipment) is covered under Maintenance Support and personnel management for Supply personnel is covered under Support Services Management). |
| 1.05 | Training Support | This element includes the provision of the Training Services required to achieve the Contract Outcomes, requirements and objectives, including the management efforts that are specific to the provision of those Services. Includes all work required to satisfy the Training Support provisions of the SOW and DSDs, including within the Approved plan(s) specific to the provision of Training Services. Includes any Training Support efforts required to support activities under other CSWBS Elements (eg, development of plans and reports and participation in Contract reviews). This element includes all of the Support Resources and any other goods and services specifically required for the provision of Training Services, with the exception of those Support Resources or other goods or services that are addressed though other CSWBS Elements (eg, common resources not specific to Training Support). This element excludes the support of the Support Resources. These activities are covered under other CSWBS Elements (eg, Maintenance of Training Equipment is covered under Maintenance Support, provision of Non-RIs for Training Equipment is covered under Supply Support, and personnel management for Training personnel is covered under Support Services Management). |
| 1.06 | Support Resources | This element includes the physical resources and work for the provision, management and support of Support Resources, which are not covered under other CSWBS Elements. For example, this element may include training of contractor personnel, provision of Technical Data Services, provision and support of common-use facilities, and provision, support and updating of Information and Communications Technology (ICT) systems. |
| 1.07 | Support Services Management | This element includes the business and administrative planning, organising, directing, co-ordinating, controlling, reporting and approval actions designated to accomplish Contract Outcomes, requirements and objectives, which are not included within the scope of the CSWBS Elements for the SSCCs. This element includes contract management and administration; cost, schedule and performance management; Defect claims administration; contract data management; vendor liaison; GFM management, Subcontract management; risk management; Life Cycle Cost; Ramp Up; Phase Out; AIC and Technical Data and Software rights management. This element includes work performed to satisfy the requirements of: SOW clause 2, General Requirements; SOW clause 3, Support Services Management; SOW clause 10, Australian Industry Capability; SOW clause 11, Quality Management; SOW clause 12, Health, Safety and Environment; and SOW clause 13, Capability Innovations and Efficiencies; and the work necessary for compliance with the COC. |