DATA ITEM DESCRIPTION

DID NUMBER:	DID-SSM-CWBS-V5.3

TITLE:	Contract Work Breakdown Structure (CWBS)

DESCRIPTION and intended use

The Contract Work Breakdown Structure (CWBS) is the Contractor’s extension of the Contract Summary Work Breakdown Structure (CSWBS), decomposing the scope of the Recurring Services to provide the framework for Contract planning, management and status reporting, and for estimating costs, schedule and programmatic achievements at completion.

The Contractor uses the CWBS to:

define the work effort necessary to successfully achieve the objectives of the Contract;

assist with estimating the cost, schedule and resource requirements for the Contract; and

ensure that there is a clean structure for the organisation and management of the Contract and that there are clear accountabilities for Contract outcomes.

The Commonwealth uses the CWBS to:

gain visibility into the Contractor’s planning;

gain assurance that the Contractor understands the full scope of work (particularly in the context of clause 1.8 of the COC (‘Contracted Requirement’)) and has appropriately incorporated this work into its execution plan for the Contract;

understand and evaluate the Contractor’s approach to meeting the requirements of the Contract;

assist with understanding and evaluating any proposed changes to the scope of work that may occur during the Term; and

as a source of input to planning performed by the Commonwealth Representative.

INTER-RELATIONSHIPS

The CWBS is subordinate to the Support Services Management Plan (SSMP).

The CWBS is related to, and shall be consistent with, the Support Services Master Schedule (SSMS), where such a data item is required under the Contract.

The CWBS inter-relates with the price breakdown at Attachment B, providing the basis against which the Price and Payment Schedules for Recurring Services Fees are derived.

APPLICABLE DOCUMENTS

The following documents form a part of this DID to the extent specified herein:

| Nil |  |
| --- | --- |

Preparation Instructions

Generic Format and Content

The data item shall comply with the general format, content and preparation instructions contained in the CDRL clause entitled ‘General Requirements for Data Items’.

The CSWBS shall form the basis for preparation of the CWBS by the Contractor.

Specific Content

General

The CWBS shall comprise a Work Breakdown Structure (WBS) index, a WBS graphic (optional), a WBS dictionary, and a Responsibility Assignment Matrix (RAM).

The CWBS shall be derived from the CSWBS in a manner consistent with the example CWBS provided at Annex B to this DID as the basis for the CWBS.

WBS Index

Note:  The WBS index is an indentured list of WBS elements and sub-elements, starting with a single level 1 element (the Contract), incorporating the high-level WBS element structure which is invoked contractually (the CSWBS), and the lower-level elements of the Contractor’s WBS necessary to provide an appropriate framework throughout the Contract for product and service definition and control.

The CWBS shall include a WBS index delivered in a tool that has built-in functionality (such as Microsoft Excel), so that it can be reviewed at any level of expansion.

The WBS index shall be derived from the WBS dictionary and each record in the WBS index shall include:

WBS element number;

WBS element title; and

WBS element revision date and revision number.

WBS Graphic

Note:  The WBS graphic is optional, but if provided, may be limited to the higher levels of the CWBS breakdown (eg, the first three levels).

The CWBS may include a WBS graphic, which contains the same information as the WBS index, but shown in a graphical form, usually a tree structure.

WBS Dictionary

Note:  The WBS dictionary is effectively the statement of work for each WBS element, and provides the collection of supporting information to fully define each WBS element, including scope, activities, products, specifications, entry and exit criteria, etc.

The CWBS shall include a WBS dictionary using the WBS dictionary template at Annex A.

Responsibility Assignment Matrix

The CWBS shall include a RAM as a standalone element of the CWBS, which provides a mapping from the responsible manager identified in the CWBS to the associated CWBS elements so that the set of CWBS elements allocated to each responsible manager is clearly identified.

Annex:

- WBS Dictionary Template

- Example Contract Work Breakdown Structure

WBS DICTIONARY TEMPLATE

- INTRODUCTION

The CWBS dictionary shall include at least the information identified in Table 1.

Note:  The CWBS may include additional columns and information, as required by the Contractor’s internal processes.

Table 1 - CWBS Dictionary Template

| CWBS Element Number | CWBS Element Level | CWBS Element Title | CWBS Element Description | Inclusions | Exclusions | Responsible Manager | Entry Criteria (including inputs / dependencies) | Exit Criteria (including outputs) | Performance Measures | SOW / COC Cross-references | Lower-level CWBS Elements (next Level only) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| a. | b. | c. | d. | e. | f. | g. | h. | i. | j. | k. | l. |

Notes for Table 1:

CWBS Element Number. The number allocated to the CWBS Element.  The entire Contract is Level 1, while Level 2 is defined by the CSWBS.

CWBS Element Level. The level in the CWBS at which the CWBS Element resides.

CWBS Element Title.	A short title that provides a summary of the scope of the CWBS Element.

CWBS Element Description. A description of the scope of the CWBS Element, including a statement of the required work and, if a product, a reference to the applicable specification (eg, title and number).

Inclusions. The identification of any specific scope inclusions, which may not be evident from the CWBS Element Description and which help to clarify the scope of the CWBS Element (eg, the identification of all significant deliverables to be provided through the CWBS Element).

Exclusions. The identification of any specific scope exclusions, which may not be evident from the CWBS Element Description and which help to clarify the scope of the CWBS Element.  Do not include generic statements, such as “Everything provided under all other CWBS Elements”.  The CSWBS Dictionary provides examples of the types of exclusions that would be appropriate here.

Responsible Manager.  The management position responsible for managing the scope of work under the CWBS Element and satisfying the associated exit criteria.

Entry Criteria (including inputs / dependencies).  The criteria that enable the work under the CWBS Element to commence.  Often, these will be exit criteria from other, related CWBS Elements, but may also include inputs to be provided by the Commonwealth or Associated Parties.

Exit Criteria (including outputs).  The measurable and verifiable completion requirements for the CWBS Element, which help with identifying when the work under the CWBS Element is complete.  Examples include approval of a document, release of preliminary drawings, delivery of a working subsystem, or satisfactory completion of a test program.

Performance Measures.  The objective measures of performance that satisfy information needs required to assess achievement and to identify problems and risks associated with the CWBS Element.  Not all CWBS Elements will have performance measures (eg, level-of-effort CWBS Elements).  Performance measures should only be identified at the leaf nodes of the CWBS.

SOW / COC Cross-references.  The specific clauses in the SOW (and, if applicable, the COC) that are addressed through the CWBS Element, noting that many SOW clauses may have applicability to more than one CWBS Element.  All SOW clauses are to be identified in the CWBS.  SOW cross-references should only be identified at the leaf nodes of the CWBS.

Lower-level CWBS Elements (next Level only).  The next lower-level CWBS Elements (if applicable).

EXAMPLE CONTRACT WORK BREAKDOwN STRUCTURE FOR RECURRING SERVICES

Note:  The following example CWBS for Recurring Services has been developed to illustrate how a product-oriented CWBS can be derived from the CSWBS at Attachment M to the Contract, where a deliverable service is categorised as a form of product.

- Contract (Support) Recurring Services

  - Operating Support

    - Mission System 1 Operations (for when the Contractor is operating MS1)

    - Mission System 2 Operations (for when the Contractor is operating MS2)

    - Help Desk Services

    - […other Operating Support Services…]

    - Operating Support Management

  - Engineering Support

    - Mission System 1 Engineering Services (only those specific to MS1)

    - Mission System 2 Engineering Services (only those specific to MS2)

    - Repairable Item Engineering Services

    - Configuration Management (if not covered under the items above)

    - Software Support

    - […other Engineering Services…]

    - Engineering Management

  - Maintenance Support

Note:  If there is only one Mission System type, it may be preferable to lift the Level 4 elements up to Level 3 to avoid having too many levels in the CWBS.

    - Mission System 1 (eg, Ship) Maintenance

      - MS1 Intermediate Docking

      - MS1 Mid Cycle Docking

      - MS1 Full Cycle Docking

      - MS1 Repairable Item Group 1 (eg, Propulsion System) Maintenance

      - MS1 Repairable Item Group 1 (eg, Combat System) Maintenance

      - Support to MS1 Organic Maintenance

    - Mission System 2 (eg, Aircraft) Maintenance

      - MS2 R3 Servicing

      - MS2 R4 Servicing

      - MS2 R5 Servicing

      - MS2 Repairable Item Group 1 (eg, Engines) Maintenance

      - MS2 Repairable Item Group 2 (eg, Avionics) Maintenance

      - Support to MS2 Operational Maintenance

    - Mission System 3 (eg, Distributed Communications System) Maintenance

      - MS3 Site 1 Maintenance

      - MS3 Site 2 Maintenance

      - MS3 Site 3 Maintenance

      - MS3 Repairable Item Maintenance

    - Mission System 4 (eg, Information and Communication Technology (ICT) System) Maintenance

      - System Administration

      - MS4 Deeper Maintenance

      - Support to MS4 Operational Maintenance

    - Repairable Item (RI) Maintenance

      - RI Group 1 Maintenance

      - RI Group 2 Maintenance

      - RI Group 3 Maintenance

    - […other Maintenance Services…]

    - Maintenance Management

  - Supply Support

    - General Supply Services

    - Warehousing Services (ie, for when the Contractor is providing Warehousing Services to the Commonwealth)

    - Mission System 1 Non-RI Procurement

    - Mission System 2 Non-RI Procurement

    - Repairable Item Group 1 (eg, MS1 RIs) Non-RI Procurement

    - Repairable Item Group 2 (eg, Support and Test Equipment (S&TE)) Non-RI Procurement

    - Repairable Item Group 3 (eg, Training Equipment) Non-RI Procurement

    - Fuel and Other Consumables Procurement

    - […other Supply Services…]

    - Supply Management

  - Training Support

Note:  The following Level 3 and 4 breakdown for the first two elements could equally be reversed, depending upon the nature and scope of the required Training program.

    - Training Course 1

      - Training Delivery and Administration

      - Training Materials Upkeep

    - Training Course 2

      - Training Delivery and Administration

      - Training Materials Upkeep

    - Training Management

  - Support Resources

Note:  This CWBS Element could be broken down into the respective Support Resources, but there is often limited work associated with a number of the Support Resources, so this approach has not been adopted and the following generic breakdown has been provided instead.

    - […Support Resource Work 1…]

    - […Support Resource Work 2…]

  - Support Services Management

Note:  The following breakdown is illustrative only (more so than for the other CWBS Elements), and this element should be derived based on the Contractor’s own corporate processes.

    - Support Services Planning, Monitoring and Control, Reviews and Reporting

    - Technical Data and Software Rights Management

    - Security Management

    - Quality Management

    - Health, Safety and Environment

    - Australian Industry Capability