ASDEFCON (Complex Materiel) Volume 1

Version 4.2

Statement of Work Tailoring Guide

Release:  April 2026

Authority

This Guide does not create procurement policy.  This guide may refer to mandatory procurement policies that are applicable to the ASDEFCON (Complex Materiel) Volume 1 template.  Any mandatory procurement guidance referred to in this guide is sourced from appropriate legislation and mandatory Commonwealth and Defence policy.

Note to Defence Staff and External Agencies

Defence staff and external agencies intending to use the associated Australian Standard for Defence Contracting (ASDEFCON) Statement of Work (SOW) templates will need to tailor the templates to their specific procurement requirements, and should seek appropriate professional guidance as required.

Disclaimer

The information in this publication is provided by Defence for the purpose of disseminating guidance to staff.  While every effort has been made to ensure that this publication is accurate and up-to-date, any user should exercise independent skill and judgment before relying on it.  Further, this publication is not a substitute for independent professional advice and users external to Defence should obtain appropriate advice relevant to their particular circumstances.

Defence does not make any representation or warranty about the accuracy, reliability, currency or completeness of any material contained in this publication and nothing in this publication should be considered as a representation by the Commonwealth.  In publishing this information, Defence do not warrant that the information will be used in any particular procurement process.  Defence are not liable for any loss resulting from any action taken or reliance made on any information or material in this publication (including, without limitation, third party information).

Copyright

Commonwealth of Australia 2026

With the exception of the Commonwealth Coat of Arms, this publication is licensed under a Creative Commons Attribution-NonCommercial 4.0 International licence.

This publication should be attributed as the ‘ASDEFCON (Complex Materiel) Volume 1 SOW Tailoring Guide’.

Use of the Coat of Arms

The terms under which the Coat of Arms can be used are detailed on the Commonwealth Coat of Arms website.

Feedback

Feedback and suggestions should be sent to: ASDEFCONSOW.Support@defence.gov.au

Amendment Record

| Version | Release Date | Description of Amendments |
| --- | --- | --- |
| 3.0 | October 2020 | First release as a dedicated guide for the ASDEFCON (Complex Materiel) Volume 1 SOW template (previous guides were combined). |
| 4.0 | April 2023 | Updated for V4.0 of the template and inclusion of the enhanced AIC framework |
| 4.2 | April 2026 | Updated for V4.2 of the template |

Table of Contents

page

Using the Template and SOW Tailoring Guide	v

Purpose and Scope.	v

Further Help	v

Definitions, Acronyms and Abbreviations	v

Referenced Documents	vi

Application of ASDEFCON (Complex Materiel) Volume 1	vi

Providing Advice to Tenderers	vii

About the Conditions of Tender	vii

About the Conditions of Contract	vii

About the SOW	vii

Tailoring the Draft Statement of Work	viii

Recommended SOW Tailoring and Development Approach	viii

Template and SOW Tailoring Guide User Tips	viii

Word Processing Tips	ix

1.	SCOPE	1

1.1	Purpose	1

1.2	Background – For Information Only	1

2.	GENERAL REQUIREMENTS	2

2.1	Scope of Work	2

2.2	Delivery of Supplies	2

2.3	Deliverable Data Items	3

3.	PROJECT MANAGEMENT	4

3.1	Contractor's Project Management Arrangements	4

3.2	Contract Status Reports	4

3.3	Progress Meetings	5

3.4	Extraordinary Meetings	5

3.5	Maintenance of Contractual Documents	6

3.6	Defence Security Compliance	6

3.7	Stocktaking of Contractor Managed Commonwealth Assets	7

3.8	Australian Industry Capability	7

4.	ENGINEERING	9

4.1	Interface Design	9

4.2	Site Installation	10

4.3	System Safety	11

4.4	System Security	13

4.5	Additional Engineering and Design Information	13

5.	INTEGRATED LOGISTICS SUPPORT	15

5.1	Implementation of Support Resources	15

5.2	Training	15

5.3	Codification Data	16

5.4	Disposal Requirements	16

6.	VERIFICATION AND VALIDATION	18

6.1	Final Inspection and Test	18

6.2	Test Readiness Reviews	20

7.	QUALITY MANAGEMENT PROGRAM	21

7.1	Contractor Quality Management Responsibilities	21

7.2	Non-Conforming Supplies	22

8.	HEALTH SAFETY AND ENVIRONMENT	23

8.1	Problematic Substances and Problematic Sources	23

8.2	Environmental Management	24

8.3	Work Health and Safety	25

8.4	Incident Reporting and Remediation	26

Annex A – Specifications	28

Annex B – Contract Data Items	28

Annex C – Problematic Substances and Problematic Sources	28

Annex D – Known Hazards at Commonwealth Premises	29

Using the Template and SOW Tailoring Guide

Purpose and Scope.

The Australian Standard for Defence Contracting (ASDEFCON) template, ASDEFCON (Complex Materiel) Volume 1 is intended for low risk, complex procurements; primarily for off-the-shelf items of materiel but which may involve:

minimal design and development (eg, selection of standard product options) and/or low-level integration not requiring any Commonwealth oversight of that process; and/or

installation of the Supplies onto Defence equipment or into Defence facilities.

The purpose of this Statement of Work (SOW) Tailoring Guide (’Tailoring Guide’) is to provide drafters with guidance for selecting optional components (eg, clauses and annexes) and for tailoring the template for individual program needs.

The scope of this Tailoring Guide covers the main body of the SOW while providing some guidance to other elements of the template (eg, SOW Annexes and Data Item Descriptions) where necessary.  Drafters should also refer to the ‘notes to drafters’ embedded within the template.  The SOW templates and this Tailoring Guide should be read and used together.

Further Help

In addition to this Tailoring Guide, further advice regarding ASDEFCON (Complex Materiel) Volume 1 may be sought from:

your Commercial Delivery Branch representative, within Commercial Division; and

Commercial Policy Systems and Practice Branch, ASDEFCON help desks:

ASDEFCON SOW Policy: asdefconsow.support@defence.gov.au

ASDEFCON and Contracting Initiatives: procurement.ASDEFCON@defence.gov.au

Definitions, Acronyms and Abbreviations

Capitalised terms, acronyms and abbreviations used herein have the meanings given in the Glossary at Attachment G to the ASDEFCON (Complex Materiel) Volume 1 conditions of contract (COC).

The table below lists those acronyms and abbreviations that are frequently used in this Tailoring Guide and that may be in addition to those listed in the Glossary.

| Abbreviation / Acronym | Description |
| --- | --- |
| AIC | Australian Industry Capability |
| CASG | Capability Acquisition and Sustainment Group |
| COC | - conditions of contract |
| COT | conditions of tender |
| COTS | Commercial Off-The-Shelf |
| DID | Data Item Description |
| DPN | - Defence Protected Network |
| E&T | Engineering and Technical |
| ENG | - Engineering |
| FI&T | Final Inspection and Test |
| HSE | Health Safety and Environment |
| IP | Intellectual Property |
| ML | Materiel Logistics |
| MOTS | Military Off-The-Shelf |
| PM | Project Management |
| PSM | Product Support Manual |
| RFT | - Request for Tender |
| STANAG | Standardisation Agreement |
| TDR | Tender Data Requirement |
| WHS | Work Health and Safety |

The table below lists definitions used in this Tailoring Guide that are in addition to those in the Glossary.

| Term | Definition |
| --- | --- |
| Commercial Off-The-Shelf | Systems, hardware or software that already exist, have been developed for commercial application and to commercial standards, are in use with one or more customers for an equivalent purpose, and require no change or minimal change. |
| Military Off-The-Shelf | Systems, hardware or software that already exist, have been developed and produced to military standards and specifications, are in service with one or more other customers for an equivalent purpose, and require no change or minimal change. |

Referenced Documents

Documents referenced in the SOW Tailoring Guide and the ASDEFCON (Complex Materiel) Volume 1 templates are listed under Attachment F of the COC.  The table below lists those additional referenced documents used in this Tailoring Guide.

| Reference | Description |
| --- | --- |
|  | ASDEFCON (Complex Materiel) Volume 1 template |
|  | ASDEFCON (Complex Materiel) Volume 2 SOW Tailoring Guide |
|  | ASDEFCON (Complex Materiel) Volume 2 template |
| CTSTG | ASDEFCON Contract Template Selection and Tailoring Guide |
| CASG Manual (PM) 002 | Project Management in Defence (PMM) |
| CASG-2-Policy (E&T) 12-8-001 | System Safety Engineering |
| CASG-2-Manual (E&T) 12-5-001 | Verification and Validation (V&V) |
| CASG-2-Framework (E&T) 12-5-001 | Verification and Validation (V&V) and Test and Evaluation (T&E) in the One Defence Capability System (ODCS) |
| DPIP 2019 | Defence Policy for Industry Participation 2019 |

Application of ASDEFCON (Complex Materiel) Volume 1

The ASDEFCON (Complex Materiel) Volume 1 template is applicable to low-risk complex procurements.  These are primarily off-the-shelf (COTS or MOTS) acquisitions but may involve some design and development (eg, selection of standard options or some customisation), including to enable integration with other systems, so long as the risk is so low that the Commonwealth has no need for oversight of the design and development process.  Basic installation, safety, security, test, and training activities are included as options within this template and, as a result, the template is often used instead of a simple purchase order for various types of equipment.

In comparison with ASDEFCON (Complex Materiel) Volume 2, this template does not include Systems Engineering, Support System design, or Configuration Management, but it does include a clause to address a minimal set of engineering requirements, relating to interface design, site installation, safety and security.  The ASDEFCON (Complex Materiel) Volume 1 template has minimal governance and assurance mechanisms, not even including a Project Management Plan, which is commensurate with the low level of risk.  The template includes ‘pay on delivery’ as the payment method, whereas the larger templates include a payment by Milestone regime that enable some payments before the actual delivery.

Note that if any significant design, development, integration, certification and / or installation activity is required as part of the procurement, it will be necessary to use the ASDEFCON (Complex Materiel) Volume 2 template.  Other factors that may contribute to selecting the ASDEFCON (Complex Materiel) Volume 2 template include requirements for Government Furnished Material (GFM) or for work in Government Furnished Facilities (GFF), and other higher-complexity contracts where greater oversight of the technical program and further mechanisms to ensure accountability are required.

The low complexity of the ASDEFCON (Complex Materiel) Volume 1 template makes it suitable for relatively lower value procurements; hence, the template does not include all procurement-connected policies that may be applicable to higher value procurements.  If higher value, off-the-shelf / low complexity procurements are required, the template can be used if the additional provisions are incorporated, with appropriate commercial and subject matter guidance.  Drafters should refer to the ASDEFCON Contract Selection and Tailoring Guide for a summary of procurement-connected policies that may be applicable to an individual contract, and for further information.

Providing Advice to Tenderers

Drafters should provide tenderers with information that will allow them to submit viable and competitive tenders.  Insufficient information may result in a poor understanding of the required scope of work and deliverables, increasing risk and likely increasing tendered prices as a result.

Noting that tenderers need to identify all of the Support Resources required for the primary equipment, within a fixed-price, drafters need to provide sufficient supporting information with the Request For Tender (RFT) to enable tenderers to accurately estimate those requirements.  Where installation, test, and training will be required, drafters also need to describe Commonwealth expectations (eg, the extent of testing anticipated, such as simple functional checks versus fully detailed demonstrations).

The draft contract and RFT should be developed consistent with the applicable higher-delegate submission, or Project Execution Strategy if part of a larger program.

About the Conditions of Tender

The conditions of tender (COT), including Tender Data Requirements (TDRs) that are annexes to Attachment A to the COT, contain commercial and technical requirements to be addressed by tenderers.

Some TDRs seek information about the tenderers ability to provide the Supplies, if they became the Contractor under any resultant Contract.  Other TDRs require SOW-related input; for example, using the lists of required Supplies and planned work to structure a draft price and delivery schedule.

In general, the SOW (including the specifications in Annex A) should be developed before the TDRs are tailored, so that the TDRs can be tailored to reflect the requirements of the completed SOW.

Under ASDEFCON (Complex Materiel) Volume 1, tenderers may be requested to provide sample Supplies for tender evaluation purposes (see COT clause 3.1).  Example Supplies may be inspected, used to demonstrate functions and, in some cases, used in field tests or other user evaluation.  Any trial / user evaluation activity should consider Work Health and Safety (WHS), Training, Intellectual Property (IP) access, maintenance and possible damage to the example Supplies, which may require separate lease / loan agreements.  For the winning tender, information from these activities may be used to update the Specifications at SOW Annex A prior to the Effective Date.

About the Conditions of Contract

The conditions of contract (COC) contain the commercial provisions for the Contract and associated conditions, such as compliance with Defence and government policies and legal obligations.

When developing the SOW, drafters need to be aware that some COC clauses are related to, and often need to be tailored consistently with, the SOW.  The ‘related clauses’ identified against each SOW clause in this Tailoring Guide indicate the most relevant of the related COC clauses.

About the SOW

The SOW (including Specifications) defines the Supplies to be provided and the related scope of work that the Contractor will need to undertake to deliver and have them accepted.  Under an ASDEFCON (Complex Materiel) Volume 1 contract, work is defined by:

the clauses that form the main body of the SOW;

the Annexes to the SOW, including specifications of the Supplies (specifications do not describe the work but they define scope by the outputs to be produced from work);

if included, the Approved Final Inspection and Test Plan; and

any other internal plans or schedules that the Contractor may develop to perform the required work, which expand upon the SOW and other requirements.

These documents may also refer to recognised standards, technical manuals, and quality management systems to define work processes and procedural level instructions.

Tailoring the Draft Statement of Work

The template includes clauses that are annotated as Core or Optional clauses.

Core clauses are always included in the draft Contract (for the scale of contracts covered by the template); however, these may contain optional subclauses.

Optional clauses may or may not be needed depending upon an individual contract’s requirements.  An optional clause means that it is unlikely to be included in some contracts that use this template.  In other circumstances these clauses could be mandatory, such as when required to address regulatory requirements.  As a convention, optional clauses that are not required are deleted but replaced with the words ‘Not used’, in order to preserve any cross-references to subsequent clauses.

Clauses may be tailorable or non-tailorable.  This SOW Tailoring Guide indicates if a clause must be tailored, may be tailored, or is non-tailorable.  A clause may be non-tailorable because it was established by an external authority (eg, data item Approval clauses negotiated by Defence and industry executives).

Core and Optional clauses are annotated within the template for level one and level two headings, and in this SOW Tailoring Guide.  Drafters should tidy up the template and remove annotations (eg, ‘Option A’, ‘Core’ and notes to drafters) before the draft Contract is released to tenderers.

Wherever possible, the form of the SOW template should be adhered to, bespoke tailoring should be kept to a minimum and changes limited to only those areas that are necessary to address specific requirements of the procurement.  Changing clauses risks creating inconsistencies and may cause unintended consequences in the resulting contract.  However, some tailoring is unavoidable, and contracts must be customised to the specific goods and services required, and the circumstances of the procurement.  When tailoring, clauses should only be added, modified or deleted consistent with the advice provided in this Tailoring Guide, or after seeking advice from the relevant specialist.

Recommended SOW Tailoring and Development Approach

The following are the very broad steps leading to RFT development.

Step 1.	 Confirm the objectives and boundaries for the draft Contract based on the relevant procurement strategy.  Essentially, determine what is in and what is not in scope.

Step 2.  Identify and scope the required materiel, including the operational equipment (eg, ‘mission systems’) and Support Resources (eg, Technical Data will be required even if the details are not yet known).  This refers to the specifications for the materiel to be supplied, to be included at Annex A.

Step 3.  Tailoring the SOW.  Define work requirements for the contract in the SOW.  This begins by tailoring the technical clauses for Engineering, ILS, V&V and QM.  Drafters should then tailor the project management clauses and enabling SOW clauses (eg, general requirements) and confirm that the Data Item Descriptions (DIDs) to be used are identified (in Annex B).  Finally, clause 8 and Annexes (C and D) should be tailored for WHS requirements, depending on the activity on Commonwealth premises.

Step 4.	 Review and refine the COC and other attachments.

Step 5.	 Prepare the COT, Tender Data Requirements (TDRs) (ie COT annexes) and RFT documentation pack for release to industry.

Template and SOW Tailoring Guide User Tips

The notes to drafters within the template are intended to guide drafters on which clauses should be used in various circumstances.  Notes to tenderers provide guidance for both drafters and tenderers.  Notes may also refer to reference documents and whom to consult for further information.

Drafters should read the SOW template and Tailoring Guide well before the date the draft Contract is required, particularly as input from stakeholders may take time to obtain.

Drafters may need to access referenced documents in order to undertake tailoring.  In some cases, these documents will also be required by tenderers and will need to be made accessible for the RFT.

The following steps are suggested when addressing a relevant section or clauses within the SOW:

- determine the Supplies and the related services (eg, Training) required;

read the relevant clause and refer to this Tailoring Guide for additional information;

understand what the clause asks the Contractor to do, and its relevance to the Contract;

review any related DIDs to ascertain any flow-on effects (eg, work in accordance with plans);

select the relevant clauses that best describe what is required from the Contractor; and

ensure that related DIDs and/or annexes are referenced from the selected clause.

After reading the guidance, drafters may remain uncertain if a particular optional clause in the template is applicable to their requirements and advice from subject matter experts should be sought as required.

Word Processing Tips

All of current the ASDEFCON templates use styles from a Microsoft Word® document template called ‘ASDEFCON Styles V1.1.dotm’.  The styles can be easily applied by using buttons created by another template called ‘ASDEFCON Toolbar V1.1.dotm’.  Both templates are available for download from the ASDEFCON templates website, along with instructions for installation.  Once installed, the ASDEFCON styles and tools will appear on an additional ribbon in Microsoft Word®.  Refer to the ASDEFCON Toolbar and Styles 2015 User Guide for details.

Adding clauses and notes needs to be done with care to avoid inadvertent changes to the styles and to ensure that built-in numbering continues to function correctly.  The tips that follow will assist drafters in working with the documents:

When tailoring, do not delete headings at heading level 1 or 2.  If a clause is not required, retain the heading and mark it 'Not used'.  This preserves cross-references between different parts of the template particularly between the COC and SOW.

If possible, additional clauses at heading level 3 should be inserted after standard template clauses to avoid cross-referencing errors between documents.    Note that cross-references between clauses within a single document are inserted as cross-reference fields – use ‘Ctrl + click’ to follow a link or click on the link and press F9 to update.

Avoid using ‘formatting’ to change the look or numbering of a clause.  Use the ASDEFCON ribbons to apply pre-defined styles.  There are style sets for the COT/COC, Attachments, SOW and tables.  The SOW style set can be applied from the ‘SOW group’ on the ASDEFCON ribbon, Use the  (Change Ribbon Settings) button to reconfigure the ribbon groups.

If additional styles are required (eg, for headers and footers), open the ‘Styles and Formatting’ task pane (click the  (styles) button or select from the menu: Home tab > Styles and the ‘expand’ button in the bottom right hand corner).  Highlight or click into the applicable clause and then select the required style from the ‘Styles’ list.  SOW specific styles all begin with ‘SOW’.  DIDs also use the SOW styles.

When pasting text from another document, paste as 'Unformatted text' (‘Right Click > Keep Text Only’).  This avoids unwanted styles in the source text corrupting the styles and numbering within the document.  Once pasted, use the format painter or apply the ASDEFCON styles from the ASDEFCON ribbon.

If the clause numbering associated with a style in the document appears corrupted or the indenting is not right, here are a few options to try:

Reapply the style as described above, which should correct any formatting inadvertently applied to the style.

Save the file and close Word, then reopen the file.  This seems to fix clauses where clause indentation has changed.

On the ASDEFCON ribbon, click on the  (Attach ASDEFCON) button, which will reapply the styles from the template to the current document.

If changes were saved to the styles template (a dialog box would have prompted the user to save the changes to the template) save all documents and re-install a clean copy of the toolbar and styles template.  Reopen the document and then reapply the styles, as described above.

Optional clauses appear in a box (actually a table).  In the ASDEFCON ribbon click the  button to remove the table, otherwise use ‘convert to text’ from the ‘Table Tools - Layout’ menu.

ASDEFCON (COMPLEX MATERIEL) VOLUME 1
STATEMENT OF WORK – Tailoring Guidance

SCOPE

Purpose

Status:	Core

Purpose:	To define the purpose of the Statement of Work (SOW).

Guidance:	Clause 1.1 is a concise and generic statement for the purpose of the SOW.  It should not require amendment; however, drafters may amend the clause for additional context (eg, “…under this Contract to acquire [name of equipment]”).  Otherwise, clause 1.1 may be included in the RFT without alteration.

Related Clauses:	SOW Annex A

Background – For Information Only

Status:	Optional.  Included if tenderers / Contractor require an understanding of background information to give context of Contract requirements.

Purpose:	To provide background information, including broader project activities that may be useful and important to the Contractor.

Guidance:	This clause may provide a brief overview of the background to the project, including broad objectives, but only where this is relevant to the Contractor’s work.  This clause should only be included if there will be a benefit of having this information in the Contract.  If the background information is only useful for the tender then it may be provided another way (eg, annexed to the covering letter to the RFT).

Background information that can help to contextualise the SOW might include:

details of earlier and/or related projects/policies/systems, for example:

the new equipment is replacing system XYZ and installation will be restricted to one site at a time as old equipment is removed;

the new equipment will be required to interface with system ABC – interface specifications for ABC are included at Annex X;

the new equipment needs to be prepared for transport and for use in a timely manner, to enable transport by air and G-Wagon – refer to the specification for deployment requirements and size constraints; or

the Supplies will be supported in-service by an existing platform-level support contract that will be amended to provide support services for the first Supplies delivered under this Contract; or

details of the environment that the system is to operate in (reference to a more detailed description would be required).

As this clause is not intended to be contractual in nature ‘shall’ statements should not be used.  Care should also be taken to ensure that this clause does not conflict with information in other elements of the Contract, including the Specifications.

The description in this clause should be concise, with information to ‘set the scene’ but not include excessive amounts of information – if more detail is required, this could be included in an SOW annex or separately in an RFT information pack.

When beneficial, drafters should develop an appropriate and concise background clause.  Otherwise, drafters should annotate the heading as ‘Not used’, delete the notes and delete draft clause below the heading.

Related Clauses:	Nil.

GENERAL REQUIREMENTS

Scope of Work

Status:	Core

Purpose:	To define the Contractor's overall scope of work under the Contract.

Guidance:	This clause is to provide a high-level description the overall scope of work under the Contract, covering such activities as manage, construct, test, deliver, install and commission equipment, and conduct Training, as applicable.

Drafters should ensure that this clause covers the scope of activities required under the Contract.  This clause also calls up the Specification, at SOW Annex A, to specify the requirements for the Supplies.  Refer to Annex A of the template for guidance.

Drafters may add to clause 2.1 where that will help to clarify the scope of work.  For example, where the Commonwealth will be performing related activities that will affect the scope of work (eg, in regards to installations), further description may help to clarify the boundary between Commonwealth and Contractor responsibilities.

Notwithstanding the need to identify these boundaries, there are legal and commercial issues with including Commonwealth work in a contract, and guidance should be sought from the applicable Commercial Delivery Branch, Commercial Division.  An example clause is:

“The Commonwealth shall:

- provide all of the utilities within facilities where the installation of equipment is required, including mains power and data cabling; and

- coordinate Defence Personnel required to undergo Training at the places and times agreed between the parties.”

In addition to Commonwealth work, there may be aspects of related work that are explicitly excluded from the Contract’s scope.  An example clause is:

“The Contractor is not required to:

- provide representation during field testing activities being managed by the Commonwealth;

- modify any element of infrastructure outside the walls of building XYZ at Naval Establishment ….”

Clause 2.1.2 calls up the Specifications at Annex A and should not be altered.

Drafters may revise clause 2.1 to improve the definition of scope, as described above.

Related Clauses:	Clause 1.6 of the COC, Contracted Requirement

Annex A, Specification

Delivery of Supplies

Status:	Core

Purpose:	To require the Contractor to package Supplies, and to mark and label the packaging appropriately, for the nature of the Supplies.

Policy:	DEF(AUST)1000C, Australian Defence Force Packaging Standard

WHS Legislation

Guidance:	This clause specifies requirements for packaging, and the labelling and markings on Packaging, for Supplies delivered under the Contract.  This should not be confused with packaging that is a Supply, such as a special-to-type packaging container that is listed in the Price and Delivery Schedule as a specific item of Supply.  The clause interacts with numerous clauses in the COC (see Related Clauses) relating to care, custody, liability, taxes, duties, customs, and export approvals (as specific packaging and documentation may be required).  This clause provides for the work associated with packaging and delivery, whereas the liabilities for Supplies and customs duties are covered in the COC.

In keeping with the ASDEFCON principle of using Contractor processes when appropriate, DEF(AUST)1000C has not been mandated but is identified as a guide.  The note to drafters highlights that this clause is not intended to include exhaustive marking requirements; however, some requirements from DEF(AUST)1000C may be included, such as barcoding – refer to ASDEFCON (Complex Materiel) Volume 2 SOW clause 2.2 for an example.  Additional requirements should be included if specific WHS and other regulations apply (eg, for explosive ordnance).

Under the COC and Attachment B, the Contractor is responsible for delivering Supplies to the designated point(s) of delivery, in a serviceable condition and by the due date, while meeting all other costs and Contract requirements.  As such, mandating a packaging standard has potential to conflict with the Contractor’s responsibilities.  Of note, for items of Packaging that are Supplies, the Defence packaging standard should be included in the Specification.

In some instances, when acquiring good from overseas, it can be beneficial to include an additional Annex to the SOW to detail specific requirements for import of goods into Australia.  In particular, overseas suppliers may not be familiar with Australia’s quarantine regulations and untreated timber crates or other ‘vegetable matter’ used in packaging, or labelling requirement for Dangerous Goods.  A summary with links to appropriate guidance and regulations can help to avoid problems during delivery.

Drafters should determine if additional clauses are required for legislative / regulatory requirements.  If not, then clause 2.2 may be included in the RFT without alteration.

Related Clauses:	Clause 3.4 of the COC, Authorisations, which relates to export approvals.

Clause 3.5 of the COC, Imported Supplies and Customs Entry

Clause 6 of the COC, Delivery, Acceptance and Ownership

Clause 7.5 of the COC, Taxes and Duties

Attachment B, Price and Delivery Schedule

SOW clause 8.1, Problematic Substances and Problematic Sources

Deliverable Data Items

Status:	Core (mostly non-tailorable)

Purpose:	To define the framework and management requirements for deliverable data items.

Guidance:	This clause does not require tailoring.  For some projects with tight schedules it may be appropriate to reduce the default Commonwealth action period in clause 2.3.2.  However, delays in Approving data items may lead to claims for postponement in accordance with clause 2.3.6.  Therefore, drafters should consider the workload for data item Approval, any requirement to action several data items at once, and the need to seek specialist advice, before reducing the action period in this clause.

Clause 2.3.4 outlines reasons why the Commonwealth may decide not to Approve a data item.  This clause was developed through consultation with industry representatives to address concerns with prior Approval practices, and to ensure that non-Approval was only for substantive reasons.  The agreed criteria in this clause are the full range of possible substantive reasons and these are non-tailorable.

Clause 2.3.11 requires the Contractor to acknowledge that a delay in the delivery of data items may lead to a delay in the Commonwealth actioning those data items.

If appropriate, the 20 Working Day default Commonwealth action period may be amended; otherwise, clause 2.3.4 should be included in the RFT without alteration.

Related Clauses:	Annex B lists the data items and DIDs for the Contract.

PROJECT MANAGEMENT

Contractor's Project Management Arrangements

Status:	Core

Purpose:	To require the Contractor to nominate a Project Manager.

Guidance:	The objective of this clause is to ensure that a specific person, with appropriate authority, is assigned the responsibility to manage the Contract.  The Contractor’s Project Manager is often the Contractor Representative, as specified in the Details Schedule at the front of the COC.

No tailoring of this clause is required.

Further Reading:	CASG Manual (PM) 002 - Project Management in Defence

Contract Status Reports

Status:	Optional.  Included when the Contract is of sufficient duration and complexity.

Purpose:	To require the Contractor to submit regular status reports.

Guidance:	The Contract Status Report (CSR) provides a mechanism for the Commonwealth to monitor Contractor progress, particularly if the succession of activities in the Price and Delivery Schedule does not provide sufficient visibility of progress during the Contract.

Drafters will need to consider the expected duration and complexity of the Contract and determine if CSRs will be required and, if so, how often.  If the Supplies are ‘off-the-shelf’ and delivered within three or four months from the Effective Date, CSRs may not be or necessary.  However, if the Contract will continue for more than a few months, with installation at different sites or other work to be monitored, then CSRs can be of significant value in tracking progress.

If CSRs are not required, the heading can be marked as ‘Not used’ and the clauses below the heading can be deleted.

DID-PM-STAT-CSR-1 specifies the requirements for a CSR.  A CSR may comprise of two parts; the core ‘Contract Status’, and an Australian Industry Capability (AIC) Report for when an AIC program is applicable to the Contract.  Reporting for AIC is conditional on AIC clauses being included in the Contract, hence there should be no need to tailor the DID even if an AIC program is not required.  In this respect, the DID is considered to be ‘self-tailoring’.

The clause has three options, intended to work with or without progress meetings and with or without AIC Reports.  These are:

Option A: intended for lower risk contracts when CSRs are required without the need for a progress meeting to follow each CSR.  This option may be used if an AIC program is required but the contract is short term and there is only one CSR, which includes an AIC Report.

Option B: intended for lower value contracts with longer duration with several installation activities, or some other reason whereby each CSR is to be followed by a progress meeting.  This option could be used for higher value contracts with an AIC program; however, as AIC may be reviewed less frequently than regular progress meetings option C would be better.

Option C: intended for contracts of a longer duration with an AIC program.  The option allows Part A of the CSR to be delivered more frequently than Part B, the AIC Report; for example, ‘Contract Status’ is required every two or three months but the AIC Report is only required every six months.

If Option A is included, drafter’s are to insert the reporting period into clause 3.2.2.  For Options B and C drafters insert the number of days before the progress meeting for delivery of the CSR.  Note that 10 Working Days matches the delivery of agenda for progress meetings under clause 3.3.3.

Option C allows the AIC Report to be delivered less frequently by stating that Part B is only required with every second, third or fourth delivery of Part A.  The remainder of clause 3.2 may be included in the RFT without alteration.

Related Clauses:	SOW clause 2.3, Deliverable Data Items

SOW clause 3.3, Progress Meetings

SOW clause 3.8, Australian Industry Capability

DID-PM-STAT-CSR-1 specifies requirements for the CSR.

Progress Meetings

Status:	Optional.

Purpose:	To require the conduct of regular progress meetings in order to monitor the Contract.

Guidance:	Progress meetings allow the Commonwealth to meet with the Contractor to discuss the progress made under the Contract.  Progress meetings can be informed by CSRs delivered prior to each meeting, but this is not mandatory.  If progress meetings are not required, then heading clause 3.3 may be marked as ‘Not used’ and the clauses below the heading can be deleted.

Including this clause will add the cost of regular meetings to the cost of the Contract.  Note that clause 3.4, Extraordinary Meetings, is a core clause and so, if progress meetings are not included in the Contract, extraordinary meetings can be used to discuss any significant problems or issues that arise.  Accordingly, clause 3.3 should only be included when the expected duration of the Contract, and complexity (eg, through installations), creates a need for regular progress meetings.

If Progress Meetings are included, the interval for these meetings should be inserted into clause 3.3.1.  The delivery of CSRs under clause 3.2 should be coordinated to precede each progress meeting as CSR topics will generally set the agenda that is delivered under clause 3.3.3 (ie, the agenda is often delivered with the CSR).

Clause 3.3.5 details general administrative requirements for progress meetings.  This includes a sentence allowing for virtual meetings / video-conferencing for efficiency.  If video-conferencing will be unsuitable, this sentence may be deleted.

Clause 3.3.6 defines the requirements for minutes from the progress meetings.

If progress meetings are required, then drafters should insert the interval into clause 3.3.1, otherwise the remainder of clause 3.3 may be included in the RFT without alteration.

Related Clauses:	SOW clause 3.2, Contract Status Reports

SOW clause 3.4, Extraordinary Meetings

Extraordinary Meetings

Status:	Core

Purpose:	To establish the process for the conduct of extraordinary meetings.

Guidance:	In general, an extraordinary meeting is not scheduled in the Contract but may be called by either the Commonwealth or the Contractor if required.  This clause details the responsibilities of each party for an extraordinary meeting.  When agreeing to the location for an Extraordinary Meeting, the nature of the issue to be discussed, the requirements for associated information, and Contractor and Commonwealth travel budgets should be considered.

Within ASDEFCON (Complex Materiel) Volume 1, administrative arrangements for Extraordinary Meetings are also used to define the administrative arrangements for specific review meetings, including Training Readiness Reviews, Facilities Preparedness Reviews, and Test Readiness Reviews, as applicable.

Clause 3.4 is to be included in the RFT without alteration.

Related Clauses:	SOW clause 3.3, Progress Meetings

SOW clause 4.2, Site Installation

SOW clause 5.2, Training

SOW clause 6.2, Test Readiness Review

Maintenance of Contractual Documents

Status:	Core

Purpose:	To require the Contractor to apply strict configuration control to Contract documents.

Guidance:	There is always a need to be able to produce an up-to-date, readable version of ‘today’s Contract’.  There is also a need to be able to produce a clean, readable version of the Contract from any previous time.

There have been a number of instances where it has not been possible to produce a copy of the required version of a Contract because the approach to Contract amendment was inadequate.  Attaching contract change notices to the original contract is inadequate as later changes can unknowingly affect previous changes.

It should be noted that a requirement for the Contractor to maintain contractual documents does not remove the need for the Commonwealth to do the same.

Clause 3.5 is to be included in the RFT without alteration.

Related Clauses:	Clause 11.1 of the COC, Change to the Contract

Defence Security Compliance

Status:	Optional.

Purpose:	To require the Contractor to undertake the work necessary to achieve compliance with clause 11.8 of the COC, Defence Security.

Guidance:	This clause is required if work under the Contract requires access to security classified information and/or equipment.

The security requirements of the Contract are specified in clause 11.8 of the COC.  Clause 3.6 of the SOW requires the Contractor to undertake all of the work needed to comply with clause 11.8 of the COC (eg, including obtaining security clearances and providing secure storage facilities, as applicable).  The clause helps to ensure that all work under the Contract, which needs to be priced, is included in the SOW.

This clause does not address the security characteristics associated with the equipment being procured, which is addressed through clause 4.4 of the SOW.

Related policy is included the Defence Security Principles Framework (DSPF).

If required, clause 3.6 is to be included in the RFT without alteration.  Otherwise, the clause can be deleted and the heading annotated with ‘Not used’.

Related Clauses:	TDR C-13 requires each tenderer to provide details of their facility and ICT system security accreditation.

Clause 11.8 of the COC, Defence Security

SOW clause 4.4, System Security

Stocktaking of Contractor Managed Commonwealth Assets

Status:	Core

Purpose:	To require the Contractor to undertake the necessary stocktaking and accounting of Contractor Managed Commonwealth Assets (CMCA).

Guidance:	This clause is applicable to all contracts, including those with no GFM, which is the usual case for this template.  The clause requires stocktaking of any assets owned by the Commonwealth and held by the Contractor, such as Supplies paid for but not yet delivered, or found to be defective and returned for repair.  CMCA is defined in the Glossary at Attachment G.

To manage the CMCA, clause 3.7 requires the Contractor to institute, maintain, and apply a system for the accounting for, and control, handling, preservation, protection, and maintenance (as applicable) of, the CMCA.

The clause requires the Contractor to deliver quarterly stocktake reports for Commonwealth Approval.  The items subject to stocktake must be advised by the Commonwealth.  This data item has no DID to define it as a notice may be sufficient, but delivery needs to be compliant with clause 2.3 and clause 3.7.

The relevant policy document for stocktaking is the Defence Stocktaking Manual.

Clause 3.7 is to be included in the RFT without alteration.

Related Clauses:	Clause 2.3, Deliverable Data Items

Australian Industry Capability

Status:	Optional.

Purpose:	To require the Contractor to perform the work required for an Australian Industry Capability (AIC) program.

Guidance:	This clause is required if the Contract is required to implement an AIC program, in accordance with Defence policies.

In accordance with the 2019 Defence Policy for Industry Participation (2019 DPIP), contracts valued at $4 million or more, inclusive of GST, are required to implement an AIC program, unless otherwise exempt in accordance with the 2019 DPIP.

As the ASDEFCON (Complex Materiel) Volume 1 template is for the procurement of Supplies that are (or almost) off-the-shelf, the nature and scope of the AIC program and the participation by Australian Industry will largely be determined by source selection.  Under contract, the SOW requires implementation of the resulting AIC program, and associated reporting.

If the Contract Price is expected to be $20 million or more (inclusive of GST and the Contract is not exempt), then the 2019 DPIP requires an AIC Plan be developed and delivered to the Commonwealth.  If applicable, use the optional clauses below to replace SOW clause 3.8.1.  An AIC Plan includes an AIC Schedule, hence corresponding changes are required in Attachment G, COC clause 4, and TDR E-1.

DIDs for AIC Plans in larger acquisition templates are not suitable for use with ASDEFCON (Complex Materiel) Volume 1, hence a new DID (“DID-PM-AIC-AICP-1”) will need to be developed and listed in SOW Annex B.  For assistance, seek advice from AIC Program Support and Assurance (aic.delivery@defence.gov.au).

Reporting for the AIC program is only viable if a contract lasts long enough to have reporting, and clause 3.2, for the CSR, would also be included.  There are three options for reporting under clause 3.2.  If a CSR is to be delivered every six months, then Option A or B may be appropriate.  If a CSR is delivered more frequently, then Option C allows AIC reporting to only be required every six months, or at some other interval.  As the scope of the AIC program and expenditure is largely determined by tender selection, there is unlikely to be a need for more frequent reporting.

If an AIC program is required, clause 3.8 is to be included.  If the Contract will be of long enough duration, then an appropriate reporting option should be selected under clause 3.2.

If an AIC program is not required, the clauses below the heading can be deleted and the heading annotated with ‘Not used’.

Related Clauses:	Clause 4 of the COC, Australian Industry Capability

Clause 3.2, Contract Status Reports

Attachment G, Australian Industry Capability

TDR E-1, Australian Industry Capability

Optional Clauses:

The Contractor shall develop an Australian Industry Capability (AIC) Plan (AICP) that complies with the requirements of DID-PM-AIC-AICP-1 and clause 2.3.

Within [...INSERT PERIOD, EG, '10'...] Working Days following the Effective Date, the Contractor shall deliver the AICP to the Commonwealth Representative for Approval.

The Contractor shall review the accuracy of the AICP, and update the AICP if necessary, at intervals of no greater than [...INSERT NUMBER OF MONTHS, EG six...] months in accordance with clauses 2.3.9 and 2.3.10.

The Contractor shall manage and conduct the AIC program in accordance with the Approved AICP, this clause 3.8, and clause 4 of the COC.

ENGINEERING

Interface Design

Status:	Optional

Purpose:	To require the Contractor to develop design documentation for relatively low complexity interfaces between the Supplies and existing Commonwealth-owned equipment.

Guidance:	Clause 4.1 can be included when the Commonwealth needs visibility of interfaces to be designed and developed to enable Supplies to be integrated into, or to otherwise interface with, existing equipment.  For example, this clause may allow for the integration of a new radio into a vehicle when the interface design is primarily for mounting brackets and some electrical wiring; however, the Commonwealth wants the opportunity to review the design before Approving that the installation work proceed.  The clause may also be used for developing simple ICT interfaces.  If this requirement is not applicable to the draft Contract, the heading can be annotated as ‘not used’ and the clauses below the heading can be deleted.

Due to the limited scope of this template (eg, no formal system reviews), such interface design must be relatively low in technical complexity, as described above; otherwise, the ASDEFCON (Complex Materiel) Volume 2 template should be used.

The clause begins with a Contractor acknowledgement of the Commonwealth’s need to view the design documentation for the proposed interface(s).  These interface(s) should be identified in the Specifications and drafters must determine if the Commonwealth needs to provide Technical Data for the existing equipment to enable the Contractor to develop the interface(s).  If the existing equipment is commercially available (or otherwise known to the Contractor), this may not be necessary; however, for Defence-specific equipment the applicable interface specifications and/or other design documents may need to be provided as appendices to the Specification, or otherwise made available to tenderers and the Contractor.

Clause 4.1.2 is intended to capture the Contractor’s work effort involved in the design and development of the interface(s).  The designs are delivered to the Commonwealth under clause 4.1.3 in preparation for an Equipment Installation Readiness Review (EIRR).  An EIRR could be held prior to the installation of Supplies onto an item of Commonwealth equipment or into a facility under clause 4.2.

Work under clause 4.1.2 can interact with the system safety and system security programs under clauses 4.3 and 4.4 respectively, and with potential additional engineering requirements under clause 4.5.

Note that the ASDEFCON (Complex Materiel) Volume 1 template does not have milestones like other ASDEFCON templates.  However, the design documentation can be included in the Price and Delivery Schedule with a ‘delivery date’ prior to the EIRR.  Either the comments can be used to identify that the payment for design documentation is subject to a completion of the EIRR (as defined by clause 4.1.5), or a separate line and price can be added for the EIRR itself.  Drafters should consult with their commercial advisor when including the EIRR as a ‘milestone’.

Clause 4.1.4 is optional, and should be included when the Commonwealth will need to provide interface specifications and/or other designs data, as discussed above.

Clause 4.1.5 describes the EIRR both in terms of its purpose and requirements for successful completion.  The EIRR is undertaken as an extraordinary meeting in accordance with clause 3.4.  The outcomes of the EIRR are important in defining the schedule and other obligations that will be placed on the parties to enable installation (eg, the Commonwealth needing to provide host equipment or access to facilities) – preparation for this is identified in clause 4.1.6.

Clauses 4.1.7 to 4.1.9 apply to the performance of the implementation work.  If installation involves Commonwealth facilities, then clause 4.2 will also apply.

If this clause is included, appropriate requirements need to be included in the Specification, and drafters should consider whether interface specifications and/or other design documents need to be provided (and whether to include optional clause 4.1.4).  The timing for delivery prior to an EIRR may also be amended if required.  Aside from those changes, clause 4.1 should be suitable for inclusion without further amendment.  Coordination is also required in the Price and Delivery Schedule to create an ‘effective milestone’ for the conduct of the EIRR.

Related Clauses:	All other clauses under SOW clause 4.

Price and Delivery Schedule (for relevant Milestones)

SOW clause 3.4, Extraordinary Meetings

SOW Annex A, Specifications, to specify the interfaces to be developed.

Further Reading:	TBD

Site Installation

Status:	Optional

Purpose:	To require the Contractor to plan for and to undertake the installation of Supplies at Commonwealth facilities.

Guidance:	Clause 4.2 should be included if Supplies need to be installed into Commonwealth facilities.  Aside from defining the physical design of interfaces (as per clause 4.1), installation into Commonwealth facilities requires co-ordination with Security and Estate Group (SEG) and, when applicable, Defence Digital Group (DDG).  If site installation is not applicable to the draft Contract, the heading can be annotated as ‘not used’ and the clauses below the heading can be deleted.

Clause 4.2.1 requires the Contractor to acknowledge the scope of installation work by identifying each Commonwealth facility where equipment installation is required, and the type of equipment (eg, operational equipment or Support and Test Equipment (S&TE)) involved.

Clause 4.2.2 builds on clause 4.2.1 by referring to more detailed information required to prepare for and to perform the installation work.  As described, this additional information is to be included in a new Annex to the SOW, which would likely contain floor plans, electrical plans, air conditioning (ie, ducting) plans, and so on, appropriate to the type of equipment to be installed.  This information is included as an Annex to enable the tenderers to understand the required scope of installation work and to be able to provide a firm price for this work.  If this is not practical due to, for example, a lack of detailed drawings at the time of tendering, drafters could consider adopting an approach similar to the one set out in clause 4.1.1 and/or incorporating one or more site visits into the SOW, including during the tender period.

Clause 4.2.3 identifies and requires that the Contractor acknowledge that certain conditions and restrictions apply to installations in Commonwealth facilities, and that the Commonwealth is depending upon the Contractor’s information, provided in a Facilities Requirements Analysis Report (FRAR), for the installation to proceed.  Clause 4.2.4 then defines the minimum contents of a FRAR; no DID is used in this instance, however, drafters may refer to DID-ILS-FAC-FRAR (from ASDEFCON (Strategic Materiel)) if considering more detail for this clause.

Due to potentially long lead times, clause 4.2.5 requires the FRAR to be delivered shortly after the ED.  Drafters need to consider a suitable timeframe, and if additional time (and clauses) are required to enable the Contractor to conduct a site survey of applicable Commonwealth facilities, in order to prepare the FRAR.

Clause 4.2.6 requires the Contractor to develop a Site Installation Plan (SIP), which identifies and schedules the required installation activities, including the necessary resources and related Commonwealth actions.  The content requirements for the SIP are included in a clause rather than a DID; however, drafters may refer to DID-ENG-MGT-SIP (from ASDEFCON (Strategic Materiel)) if considering more detail for this clause.  Note that the content of the SIP may depend on any changes to facilities by the Commonwealth (SEG and possibly DDG) in response to the Approved FRAR.

Clauses 4.2.8 and 4.2.9 provide an option to conduct a Facilities Preparedness Review (FACPR) to confirm that any pre-requisite building work has been done, and that the facilities are ‘prepared’ for the installation.  Depending on the inclusion of a FACPR, the SIP under clause 4.2.6 can be scheduled for delivery before the FACPR or the first site installation.

A FACPR can be appropriate for more complex installations.  Note that, if installation is required at multiple bases, and/or several sites at a base, then the clauses can be modified for a FACPR to be held before the first site installation at each base.  In preparation for the FACPR, the Commonwealth will need to plan the co-ordination activities required to enable installation, such as arranging for Contractor access with Base Security, preparing for the disconnection of power and/or water, and advising resident units of any expected disruptions.  Administratively, the FACRR is conducted as an extraordinary meeting in accordance with clause 3.4.

Clause 4.2.10 requires the Contractor to perform the site installation(s) in accordance with the Approved SIP, while clauses 4.2.11 and 4.2.12 clarify and acknowledge the responsibilities of both parties in regards to work and providing materials.

Clauses 4.2.11 and 4.2.12 identify common requirements for the installation, while the options included at clauses 4.2.13 to 4.2.15 identify preparatory and change management processes specific to DDG (eg, if interfacing with the DPN) or when those DDG requirements do not apply.  Depending on the full scope of installation work, both Option A and Option B could be required.

Completion of installation work can be identified as events in the Price and Delivery Schedule in order to effect payment (ie, like milestones).  For example, clause 4.2.14 identifies that an installation will enable site-specific FI&T, allowing the cost of installation work to be tied to that Acceptance.  Alternatively, an earlier separate payment could be connected to the completion of a Test Readiness Review for that facility, if applicable (see clause 6.2), or some other defined event.

Clauses 4.2.16 to 4.2.18 define the obligations of both parties in regards to site access by authorised personnel, the need for visitor escorts, and co-ordination with Commonwealth / Defence units normally operating in the facilities affected by the site installation activities.

Clause 4.2 requires drafters to identify the facilities, add details in a new Annex to the SOW (or alternative approach as set out above), and select from the optional clauses.  While tailoring and additional clauses may be required, the draft clauses provide a framework for defining the installation work.

Drafters should also note that if the Contractor is to conduct work on Commonwealth Premises, several optional clauses under clause 8, Health Safety and Environment, must be included and drafters will need to identify work area hazards in Annex D.

Related Clauses:	All other clauses under SOW clause 4.

SOW clause 3.4, Extraordinary Meetings

SOW clause 6.2, Test Readiness Review

SOW clause 8, Health Safety and Environment, includes optional clauses that must be included if the Contractor is to work on Commonwealth Premises.

SOW Annex D, Known Hazards at Commonwealth Premises

Further Reading:	DID-ILS-FAC-FRAR and DID-ENG-MGT-SIP from ASDEFCON (Strategic Materiel).

System Safety

Status:	Optional

Purpose:	To require the Contractor to implement the core elements of a system safety program applicable to the introduction of new equipment to Defence.

Guidance:	Clause 4.3 should be included if the Contract will introduce new equipment to Defence, in order to provide assurance of the safety in the design of the new Supplies (in contrast to the WHS obligations for Contract-related work under clause 8.3).  This clause would not be required if procuring additional items of existing equipment, when the Commonwealth already has all of the relevant system safety information, or when the Commonwealth has access to that information by other means.  If this requirement is not applicable to the draft Contract, the heading can be annotated as ‘not used’ and the clauses below the heading can be deleted.

Clause 4.3.1 has the effect of addressing the work required to comply with the COC and WHS Legislation for system safety or ‘design safety’.  In principle, the work is required to comply with WHS Legislation (even without the clause); however, the clause emphasises this obligation to tenderers and especially overseas suppliers.

Clause 4.3.2 requires the Contractor to review the Technical Data to be provided, such as operator and maintenance manuals, to ensure that it is suitable for WHS purposes for the operation and support of the Supplies.  Technical Data should advise suitably qualified personnel of relevant WHS hazards and associated risks in order for them to take the necessary precautions.  While this information is linked to compliance with WHS legislation, as the note above the clause identifies, this is most relevant for imported items where the Technical Data may have been prepared under regulations that differ from (ie, are less prescriptive than) WHS Legislation.  This clause could be removed and replaced with ‘not used’ if it is determined during tender evaluation or negotiations that all Technical Data will meet the standards required by WHS Legislation.

Clause 4.3.3 again captures work that is otherwise required by the COC and WHS Legislation; however, the clause ensures that the delivery of new safety information is co-ordinated with the delivery of Supplies being offered for Acceptance.

The approach under clause 4.3.3 is significantly different to ASDEFCON (Complex Materiel) Volume 2, which requires the Contractor to prepare a Safety Case Report (SCR) or Materiel Safety Assessment (MSA).  Under clause 4.3.3, if the Supplies require, or if the Supplies will be added to a system that requires, a SCR or MSA, the preparation of those documents would be undertaken by the Commonwealth or another contractor (eg, that manages an SCR for a high-level system) using the information provided through this clause 4.3.3.

Clause 4.3.4 applies if items of Supplies require ‘registration of design’, which can be considered as a specific kind of ‘safety information’ required by clause 4.3.3, but additional requirements apply.  Registration of design applies to ‘medium and high risk plant’ (eg, forklifts and cranes) in accordance with Part 5.3 of the Work Health and Safety Regulations 2012 (Cth).  If medium or high risk plant is required, it can be beneficial to include a requirement to this effect in the Specifications (especially if there may be overseas suppliers).  If it is known that Supplies will not include medium or high risk plant, or this is confirmed during negotiations, clause 4.3.4 could be replaced with ‘not used’.

Design registration is usually performed by a State or Territory WHS regulator but may be performed by the Commonwealth regulator (Comcare).  For example, compliance of an imported motor vehicle is usually assessed by a state regulator; however, if this is not practical because the item is military equipment (eg, a boiler on a Navy ship), design registration may be performed by Comcare.  For more information regarding design registration, refer to CASsafe.

Note that for equipment that already has registration of design, confirming that a compliant data plate is attached (or nearby) should be confirmed as part of a FI&T activity, or otherwise by a routine inspection prior to Acceptance.

If clause 4.3 is included, it should be reviewed and amended as required, but in many cases it can be included without amendment.  If details are known about the origin of the Supplies and Technical Data, then some clauses may not be necessary and could be deleted (eg, if confirmed during negotiations).

Related Clauses:	All other clauses under SOW clause 4.

COC clause 12.4, Work Health and Safety

SOW clause 8, Health Safety and Environment

Further Reading:	DID-ENG-SOL-MSA from ASDEFCON (Complex Materiel) Volume 2.

CASG-2-Policy (E&T) 12-8-001, System Safety Engineering

Part 5.3 and Section 743 of the WHS Regulations 2012 (Cth)

SafetyMan

System Security

Status:	Optional

Purpose:	To require the Contractor to implement the core elements of a system security program applicable to the introduction of new equipment to Defence.

Guidance:	Clause 4.4 should be included if new equipment or Software will be introduced to Defence, and it is necessary to assess and confirm the security characteristics of these Supplies.  This clause may not be required for additional procurements of existing equipment, if the Commonwealth already has the required information, or when the Commonwealth has access to the required information through other means.  If this requirement is not applicable to the draft Contract, the heading can be annotated as ‘not used’ and the clauses below the heading can be deleted.

Clauses 4.4.1 and 4.4.2 require the Contractor to analyse the Cyber Security-related characteristics of Information and Communications Technology (ICT) Equipment, Operational Technology (OT) Equipment and Software that form part of the Supplies, and then prepare the Cyber Security Assessment Information (CSAI).  There can be challenges with ensuring that the scope is clear enough for tenderers to provide a sound response to this requirement.  The note to tenderers above clause 4.4.1 is intended to provide a reasonable basis for each tenderer to provide a response, and then for the parties to finalise the exact scope during negotiations.

For background information, drafters should refer to the SOW Tailoring Guides for ASDEFCON (Strategic Materiel) and ASDEFCON (Complex Materiel) Volume 2, in regard to SOW clause 4.6.7.  For contracts using this template (unlike the larger templates), the CSAI obtained is to be used by Commonwealth personnel to prepare the plans and procedures required to obtain, or update, a ‘security authorisation’.

Clauses 4.4.3 and 4.4.4 provide two options for the delivery of the CSAI, either as a specific data item deliverable required to be delivered at a specific time (specified using Option A) or as part of the ‘Technical Data package’ included as Supplies and scheduled for delivery in the Price and Delivery Schedule (Option B).  Note that both options could be included (with minor amendment) to enable an initial CSAI to be delivered under Option A, for stakeholder review, and a final version delivered with the Technical Data package under Option B.

If this clause in included for the collection of CSAI, drafters need to decide whether to use clause 4.4.1 to identify the specific equipment to be analysed, or use another security-appropriate means.  Drafters should also determine the preferred approach for scheduling the delivery of the CSAI.

Related Clauses:	All other clauses under SOW clause 4.

Further Reading:	SOW Tailoring Guides for ASDEFCON (Strategic Materiel) and ASDEFCON (Complex Materiel) Volume 2, regarding SOW clause 4.6.7.

Additional Engineering and Design Information

Status:	Optional

Purpose:	To require the Contractor to provide additional design or engineering information that may be required to enable the Supplies to be introduced into service.

Guidance:	By default this clause is not used; however, it has been included as a placeholder for the purpose of obtaining additional system design and/or engineering information necessary for the Commonwealth to introduce new equipment into service.  If there are no additional requirements, then the clause can be deleted.

An example of additional information that may be required is an Equipment Certification to Access Radiofrequency Spectrum (ECARS) form, for products that use the radiofrequency spectrum for their operation.  An ECARS form could be requested using DID-ENG-SOL-ECARS from the ASDEFCON (Strategic Materiel) template, and clauses similar to those used in clauses 4.4.2 to 4.4.4.

Another example may be to obtain information for items of ‘Controlled Radiation Sources’ under the Australian Radiation Protection and Nuclear Safety Act 1998 (Cth) (called Problematic Sources in ASDEFCON).  Plans may need to be prepared and approved for these items to be added to the Defence Source Licence.  For further detail, refer to the Defence Radiation Safety Manual.

Use of this clause is not limited to the above two examples.  If required, drafters will need to develop this clause (and include a DID if necessary) to suit the requirement.

Related Clauses:	All other clauses under SOW clause 4.

Further Reading:	Refer to the Specialty Engineering clauses in ASDEFCON (Complex Materiel) Volume 2.

INTEGRATED LOGISTICS SUPPORT

Implementation of Support Resources

Status:	Optional

Purpose:	To identify the work effort required by the Contractor to deliver and install, as applicable, Support Resources.

Guidance:	This clause is included to acknowledge the work effort involved in the delivery and installation of Support Resources (‘implementation’).

The clause may not be required when all Support Resources are only required ‘to be delivered’.  However, it can be useful to ensure that installation (eg, of S&TE or Training Equipment) is included in the contract scope and tendered price, if installation is not included in ‘per unit’ pricing.  This can help to avoid additional costs being identified during negotiations, or unexpected costs arising under Contract.

Note also that this clause may not be required if installation is more significant and included under clause 4.2, Site Installation.

If this requirement is not applicable to the draft Contract, the heading can be annotated as ‘not used’ and the clauses below the heading can be deleted.

Related Clauses:	Attachment B of the COC, Price and Delivery Schedule.

SOW clause 4.2, Site Installation

Further Reading:	Nil

Training

Status:	Optional

Purpose:	To require the Contractor to conduct a Training Readiness Review (TNGRR), prior to the conduct of Training courses delivered to Defence Personnel.

Guidance:	This clause is to be included if the Contractor will be providing Training under the proposed Contract and/or the scope of Training is significant enough to require a formal meeting to co-ordinate resources for the commencement of Training.

The clause includes two options.  Firstly, for a TNGRR, and then for Contractor-delivered Training courses.  A TNGRR may be held before Contractor-delivered Training, or to ensure that the Commonwealth is prepared for in-house Training using Training Material and any Training Equipment delivered as Supplies (ie, a TNGRR can be required with or without Contractor-delivered courses).  Contractor-delivered Training could also be delivered with or without a prior TNGRR, depending on the amount of co-ordination required before delivery

The objective of a TNGRR is to enable the Commonwealth and the Contractor to review Training Materials, Training Equipment, and facilities (eg, classrooms), and to confirm that all necessary elements (including personnel) are ready for Training to commence.  Note that the Commonwealth needs an opportunity prior to a TNGRR to review Training Materials and to confirm the delivery and installation of Training Equipment, if applicable (even if temporary at the Contractor's facility).

The Price and Delivery Schedule may include lines for pricing the delivery of Training Materials, conduct of the TNGRR, and/or the actual delivery of Training courses.  The TNGRR can be used as a step that leads to Acceptance of the Training ‘solution’ as a whole.  The TNGRR determines if the delivery of a Training course is ready to proceed, while Acceptance generally occurs after that Training has been delivered.

Clause 5.2.1 requires the TNGRR to be held while clause 5.2.2 identifies the typical scope and that, administratively, a TNGRR is conducted as an Extraordinary Meeting in accordance with clause 3.4.

The second set of optional clauses can be used to provide information that is needed to scope (and tender for) Contractor-delivered Training courses.  The clauses present a minimal amount of information that needs to be further developed by the drafter.  Annex D to the ASDEFCON (Support Short) SOW can be used as a guide for additional information that could be included, depending on the circumstances.

Note that Training programs are not developed by contracts using the ASDEFCON (Complex Materiel) Volume 1 template.  The review of related Training Materials is primarily to confirm the suitability of existing / adapted course materials.

If no Training is to be delivered under the Contract, this clause may be deleted and replaced with ‘Not used’.

If Training is required but implementation is low risk a TNGRR (first option) may not be required,  If included, this set of optional clauses does not require tailoring.

If the Contractor is to deliver Training courses, include and tailor the second set of optional clauses.

Related Clauses:	Attachment B of the COC, Price and Delivery Schedule, may have Training related entries, including for the conduct of the TNGRR.

SOW clause 3.4, Extraordinary Meetings

Further Reading:	Defence Learning Manual

Codification Data

Status:	Optional

Purpose:	To require the Contractor to deliver, for Commonwealth Approval, Codification Data for all items of Supply (other than Technical Data).

Guidance:	Product Support Manual (PSM) Chapter 15, Introduction to Codification and Cataloguing, describes Codification requirements.

If all of the Supplies are known to be MOTS or other off-the-shelf items, unmodified and already codified, the applicable NATO Stock Number will be included in the item identification for provisioning purposes, and no codification action would be required.

ASDEFCON templates, the PSM identifies the requirements to be able to comply with Defence’s obligations to the NATO Standardisation Agreement (Appendix 1 to STANAG 4177).

Clause 5.3.1 specifies that Codification Data is to be compliant with DID-ILS-TDATA-CDATA.  This DID does not require tailoring.

Note that within participating countries, the preference is to have items codified in the country of origin.  Additionally, subcontractor / suppliers may not wish to provide sensitive Codification Data via a prime Contractor.  Hence, clause 5.3 allows the Commonwealth to agree to other solutions, such as a supplier providing Codification Data directly to an NCB in Australia or other country of origin.

When included, this clause does not require tailoring and should not be altered without the agreement of the National Codification Bureau.  If the Supplies will not require Codification, this clause may be deleted and the heading annotated with ‘Not used’.

Related Clauses:	DID-ILS-TDATA-CDATA defines the requirements for Codification Data.

SOW clause 2.3, Deliverable Data Items

Further Reading:	Product Support Manual

Disposal Requirements

Status:	Core

Purpose:	To require the Contractor to develop and deliver a Disposal Requirements Report for Commonwealth Approval.

Guidance:	Tenderers are requested to provide Disposal information in their tenders.  This requirement in the SOW is to obtain a more detailed report.  The information to be reported is intended for in-service use.

The Defence Disposal policy is Product Support Manual (PSM) Chapter 12, Defence Disposal Policy.

The report need only address Supplies that have ‘special’ or non-routine Disposal requirements, such as those items containing hazardous materials (eg, heavy metals) or Ozone Depleting Substances, subject to international controls or agreements regarding resale, having significant reclamation value, or with security requirements, safety issues, or particular legislated constraints.

Relevant safety management authorities should be consulted as early as possible regarding the requirements for disposal of identified hazardous chemicals.  Within the Defence Enterprise Resources Planning Solution (ERP) items containing Hazardous Chemicals may be identified as ‘Problematic Items Of Supplies’.

There is no specific format or content for the report, other than the examples of special disposal requirements listed and the general requirements for deliverable data items in clause 2.3.  If specific content is required a DID may be developed and added to Annex B and the references from this clause, for example: “… a Disposal Requirements Report that complies with the requirements of DID-ILS-XXX-XXX”.  Otherwise, clause 5.3 may be included in the RFT without alteration.

Related Clauses:	SOW clause 2.3, Deliverable Data Items

SOW clause 4.3, System Safety

SOW clause 8.1, Problematic Substances and Problematic Sources.

TDR D-3 (clause 3 of Annex D to Attachment A of the COT) requires each tenderer to provide details of Supplies that have special disposal requirements.

Further Reading:	Refer to the further reading section under clause 8.1, Problematic Substances and Problematic Sources.

VERIFICATION AND VALIDATION

Status:	Optional

Purpose:	To provide assurance as to the suitability of Supplies offered for Acceptance.

Guidance:	As identified the notes to drafters above clauses 6 and 7, these clauses must be tailored together to define the approach to assurance regarding the quality and suitability of the Supplies.  These clauses allow for the following three options:

1.	Quality assured through a certified QMS controlling Contractor processes, or

2.	Quality assured through both a certified QMS and Final Inspection and Test (FI&T) of the Supplies, or

3.	Quality assured through FI&T of the Supplies.

If option 2 or 3 is selected, for FI&T, then clause 6.1 is required and clause 6.2 is optional.  If option 1 is selected, both clauses 6.1 and 6.2 are not used.  Drafters should note that information that may be collected under clause 4 that is relevant to Verification and Acceptance of the Supplies, in particular clause 4.3, System Safety and clause 4.4, System Security.

Clause 6 allows for a formal process of Verification, which can be coordinated with installation if applicable, and enables a planned test regime to be witnessed by, and involve, Defence.  Without this clause, items delivered to the Commonwealth for Acceptance would still be inspected and may be rejected if found to be defective.

This template only includes Verification.  However, for consistency across templates, the terminology ‘Verification and Validation’ is used.

If a Verification program and this clause are not required, the heading of clause 6 should be annotated with ‘Not used’, and the subclauses may be deleted.  When included, refer to guidance for clauses 6.1 and 6.2.

Related Clauses:	SOW clause 7, Quality Management Program

COC clause 6.2, Acceptance

Final Inspection and Test

Status:	Optional

Purpose:	To require the Contractor to develop, for Commonwealth Approval, a FI&T Plan (FI&TP) and to conduct Verification in accordance with the Approved FI&TP.

Guidance:	FI&T should be included in the draft SOW when the complexity of the Supplies, or the installation, requires Verification activities to gain assurance as to the suitability and Quality of the Supplies, before Acceptance.  As noted above, assurance may be obtained fully through FI&T, or in combination with the Quality Management requirements in clause 7.

As for all Verification activities, FI&T is undertaken to address the risk that Supplies may not meet the requirements of the Contract, and performing FI&T will confirm suitability or the extent to which the Supplies fall short of expectations.  For example, it would be unusual to conduct FI&T of Commercial Off-The-Shelf electronic equipment such as a computer or a monitor, or additional quantities of spares for a system that was procured under a previous contract (and Accepted Supplies are covered by the Defect provisions in the COC).

The Contractor uses the FI&TP to document the planning arrangements for the FI&T activities, to Verify that the Supplies satisfy the requirements of the Contract, including the Specifications at SOW Annex A.

The Commonwealth uses the FI&TP to determine if the FI&T activities will be adequate to provide assurances of the conformance and quality of the Supplies, and to plan and prepare for any Commonwealth involvement in the FI&T activities (eg, Defence user participation).

If FI&T is required, tenderers may be asked to provide a draft FI&TP, comprising a draft of the general section and a summary of the procedures sections of the FI&TP, in accordance with DID-V&V-MGT-FI&TP and subject to any tailoring of Annex D to Attachment A of the COT.  The draft plan will be considered during tender evaluation and may be updated during negotiations.  Clause 6.1 requires the FI&TP to be updated and submitted for Approval under the Contract, and clause 6.1.2 should be amended to include the delivery date.

If a draft FI&TP was not requested in the tender, but is required under the Contract, drafters should remove the word ‘further’ from clause 6.1.2.

DID-V&V-MGT-FI&TP describes the FI&TP requirements.  It does not require tailoring.  The FI&TP is to include a description of the FI&T Procedures to be used to Verify each of the Supplies.  For example, installation drawings may be inspected and checked against the physical installation; or a pump may be tested for flow rates under specified conditions.  Test procedures are defined in step-by-step, to ensure that test activities are repeatable, if required.  The specification at Annex A may include FI&T specification requirements.

Clause 6.1.3 creates the obligation on the Contractor to apply the Approved FI&TP.  Clause 6.1.4 requires the Contractor to review and if necessary update the FI&TP for Commonwealth Approval, prior to the conduct of FI&T activities.  This is especially useful in longer Contracts and/or if details for each installation need to be updated.

Clauses 6.1.5 to 6.1.8 require the Contractor to invite the Commonwealth Representative to witness all FI&T activities, and not to conduct the FI&T activities unless the Commonwealth witness attends, unless otherwise agreed in writing by the Commonwealth Representative.  These clauses do not require tailoring.

Clauses 6.1.9 and 6.1.10 require the Contractor to prepare and deliver a FI&T Report after each FI&T activity, for Commonwealth Approval.  Reports are prepared in accordance with the Approved FI&TP.  These clauses do not require tailoring.

Clause 6.1.11 requires the Contractor to apply sampling procedures in accordance with an agreed sampling standard.  Two suitable standards are included in the clause; however, If the Contractor proposes an alternative standard the Commonwealth Representative should seek advice from subject matter experts before agreement.  Agreement would be via Approval of the FI&TP, which would describe how sampling is conducted using the alternate standard.  Clause 6.1.11 need not be tailored, even if a separate sampling standard is agreed.  If sampling is not applicable, as there is only one item being supplied or all items will be tested, clause 6.1.11 may be deleted.

The optional clause 6.1.12 should be included if any calibrated test equipment is required to be used to perform testing.

Drafters should include clause 6.1 when FI&T is to be included for assurance purposes (and when option 2 or 3 is selected in clause 7).  Drafters should tailor clauses 6.1.2 and 6.1.4 as required, and include optional clauses 6.1.11 and 6.1.12 when applicable.

Related Clauses:	COC clause 6.2, Acceptance

SOW clause 2.3, Deliverable Data Items

SOW clause 7, Quality Management Program

DID-V&V-MGT-FI&TP defines requirements for the FI&TP.

TDR D-4 (clause 4 of Annex D to Attachment A of the COT), Final Inspection and Test Plan

Further Reading:	CASG-2-Manual (E&T) 12-5-001 Verification and Validation (V&V)

CASG-2-Framework (E&T) 12-5-001 Verification and Validation (V&V) Test and Evaluation (T&E) One Defence Capability System (ODCS)

Test Readiness Reviews

Status:	Optional

Purpose:	To require a Test Readiness Review (TRR) to be conducted prior to commencing a formal FI&T activity, to ensure that all parties are prepared.

Guidance:	To be included when the scope and complexity of FI&T activities, including the need to coordinate different parties, warrants the inclusion of formal TRR meetings.  If clause 6.1 is not used, then this clause 6.2 will also not be used.  If clause 6.2 is included, the FI&TP should describe when and how TRRs will be conducted.  For example, if there are two separate FI&T phases at two separate Defence bases, there may be a TRRs for each base.

The purpose of a TRR is to confirm the completeness of the FI&T Procedures (within the FI&TP), and to ensure that the relevant Supplies and any addition resources required are ready for the FI&T activity.

Clause 6.2.1 requires the TRR to be held, outlines the typical scope of a TRR, and identifies that the TRR will be conducted as an Extraordinary Meeting in accordance with clause 3.4.  Clause 6.2.2 simply requires that the FI&T activities (ie, clause 6.1) not go ahead until the TRR has been held and any issues have been resolved.

If required, drafters may add an additional clause identifying the sets of FI&T activities or the numbers and locations of TRRs expected by the Commonwealth, noting that clause 6.2.1 requires a TRR before each FI&T activity.

Drafters are to consider whether the TRR(s) is/are required.  If not required the clause may be deleted and the heading clause annotated with ‘Not used’.  If included, the clauses do not require tailoring but additional detail may be provided if multiple TRRs are expected.

Related Clauses:	SOW clause 3.4, Extraordinary Meetings

SOW clause 6.1, Final Inspection and Test

Further Reading:	ASDEFCON (Strategic Materiel) MSR Checklist, MSR-CHECKLIST-TRR

QUALITY MANAGEMENT PROGRAM

Contractor Quality Management Responsibilities

Status:	Optional

Purpose:	To increase confidence that the Supplies will meet Contract requirements, through effective management of Quality by the Contractor.

Guidance:	The ISO 9000 series of Quality Management standards used in Defence contracts are commercial standards.  The risk-based application of these standards is consistent with Commonwealth Procurement Rules and Defence policy.

As described in the note to drafters, and in guidance for clause 6 above, ASDEFCON (Complex Materiel) Volume 1 has three options for Quality Assurance:

1.	Quality assured by following a certified QMS, or

2.	Quality assured by following a certified QMS and undertaking FI&T, or

3.	Quality assured by undertaking FI&T only.

The note to drafters at the start of clause 7 is comprehensive in explaining these three options.  If option 1 or 2 is selected then clause 7.1 is included in the draft SOW.

A certified QMS assists the Contractor in maintaining quality of work and gives the Commonwealth a high degree of assurance that adequate quality-management practices are in place.  Without a QMS, management of processes can be unstructured and the quality of outcomes can sometimes be sacrificed in the interests of cost and schedule, with no visibility to the Commonwealth.  In higher-risk Contracts, this would be unacceptable.

Requiring a certified QMS may not be necessary for some ASDEFCON (Complex Materiel) Volume 1 contracts with low risk or for low-criticality Supplies, such as for items that are in production in an established environment and where normal, commercial production quality standard is suitable (ie, Quality systems most likely exist, for multiple customers and there is no need for the Commonwealth to review or audit them).  Note that requiring a Contractor to obtain certification for an existing QMS will not change the quality of a product that has already been manufactured and is pending delivery when the Contract is signed (noting that clause 7.1.5 allows the Commonwealth to access the QMS that ‘was used’.)  Likewise, if the Contractor is an importer of required off-the-shelf Supplies, certifying their QMS will not change the production process.  Hence, the option to assure quality through FI&T (ie, Verification) alone might be suitable in such cases.  This avoids third-party certification costs and permits more suppliers to tender.

Considerations include the value in, or essentiality of, ensuring that a certified QMS will be applied to the production of the Supplies, and whether the Commonwealth wants to audit and have direct visibility of any such QMS.  Drafters should be aware of the potentially high cost to a Contractor of attaining QMS Certification just for one contract; a cost that may be passed on to the Commonwealth.

Drafters should be aware that the ADF regulatory / assurance authorities may dictate requirements for a quality system to be used in relation to production, and should ensure that the selected optional clauses accord with any such regulatory / assurance requirements.

Clauses 7.1.1 to 7.1.3 specify the requirements for a certified QMS, applicable to the contract scope, and that the QMS is to be applied.  Clause 7.1.4 includes Subcontractors within the quality management regime for the Contract.

If the Supplies have potential to be manufactured before the Effective Date, clause 7.1.5 facilitates access to the Certified QMS that was applied.  If Supplies were manufactured prior to the Effective Date, and there was no certified QMS at that time, those Supplies may deserve particular attention during FI&T.

Clause 7.1.6 covers the Contractor’s efforts associated with facilitating the Commonwealth’s quality-related Audit and Surveillance activities.  Contract terms for Commonwealth access are included at clause 11.6 of the draft COC.

Clause 7.1.7 entitles the Commonwealth Representative to require the Contractor to correct quality system, process, and product non-conformances, within the period specified in a notice.

The subclauses within clause 7.1 should not be amended without appropriate policy advice.  Changes may result in the inappropriate application of standards, or a reduction in the Commonwealth’s rights.

Drafters need to select the method for ensuring the quality of the Supplies under the Contract, considering both the Quality Management and V&V clause.  If Option 1 or 2 (as described in the note to drafters) is selected, clause 7.1 may be included in the RFT without alteration.

Related Clauses:	TDR D-5 (clause 5 of Annex D to Attachment A of the COT) requests tenderers to provide information relating to their QMS.

SOW clause 6.1, Final Inspection and Test

COC clause 11.6, Commonwealth Access

Further Reading:	Product Support Manual (PSM) Chapter 7, Defence Supplier Quality Assurance

AS/NZS ISO 9001, Quality Management Systems – Requirements

Non-Conforming Supplies

Status:	Core

Purpose:	To define the contractual obligations and mechanism for seeking Commonwealth Representative Approval for the use of non-conforming materials or work in the Supplies.

Guidance:	Requirements for the control of non-conforming Supplies should always be included in contracts in order to increase the probability that Supplies received conform to quality requirements, and are free of reworked or repaired components that do not have Commonwealth Representative Approval.  Accordingly, clause 7.2 is core.

This clause provides the mechanism by which the Contractor is to apply to the Commonwealth Representative Approval of non-conforming work or materials in the Supplies.  The Defence mechanism for processing these applications, and providing written Approval, is through the use of an Application for a Deviation (AFD), as a Form SG002 or a suitable equivalent agreed by the Commonwealth.

ASDEFCON (Complex Materiel) Volume 1 has a simplified clause for managing AFDs.  If a more detailed procedure for managing AFDs is required, then drafters should refer to ASDEFCON (Complex Materiel) Volume 2.  In some instances, it may be appropriate to transfer this more detailed process; however, for off-the-shelf solutions that should not be necessary.

Clause 7.2 should not be amended without policy advice from appropriate Defence QA adviser.  Changes may result in an inappropriate application of standards or a reduction in the Commonwealth’s rights.

Related Clauses:	COC clause 6.2, Acceptance

SOW clause 2.3, Deliverable Data Items

DID-PM-MGT-AFD defines the format and contents of an Application for a Deviation.

Further Reading:	Product Support Manual (PSM) Chapter 7, Defence Supplier Quality Assurance

HEALTH SAFETY AND ENVIRONMENT

Problematic Substances and Problematic Sources

Status:	Core

Purpose:	To define the requirements for the management of Problematic Substances and Problematic Sources.

Guidance:	Tenderers are to identify specific Problematic Substances and Problematic Sources in the Supplies, in response to TDR D-2 (ie, COT Attachment A, Annex D, clause 2).  At the ED, the Approved list of Problematic Substances and Problematic Sources is included at SOW Annex C.  Annex C lists the Approved Problematic Substances and Problematic Sources that form part of the Supplies.  For Problematic Substances and Problematic Sources that are to be brought onto Commonwealth Premises for the purposes of installation or test, if applicable (ie, and in addition to Supplies), Commonwealth Representative Approval is also required.

Note that the ASDEFCON (Complex Materiel) Volume 1 template does not require details of Problematic Substances or Problematic Sources that the Contractor uses on their own premises (eg, used in manufacturing but not present in the Supplies).

Clause 8.1.1, Problematic Substances

Clause 8.1.1.1 is a core clause and states that the Contractor is not to deliver Supplies that contain or emit a Problematic Substance, which may affect the health or safety of persons who may be exposed to the Problematic Substance, unless the Commonwealth Approves both the Problematic Substance and it’s use.  Approved Problematic Substances are listed in Annex C.  Problematic Substances that are not listed in Annex C by the ED but which become Approved during the Contract, will require a contract change proposal to amend Annex C.  If Commonwealth personnel discover another Problematic Substance (ie, not identified in Annex C) in or emitted by the Supplies, which may affect health or safety during an activity referred to in clause 12.4.9 (a) to (c) of the COC, the Commonwealth can notify the Contractor and require the Contractor to comply with the requirements of clause 8.1.1.1 (ie, requiring a change to the Supplies or a request for Approval).

Clauses 8.1.1.2 and 8.1.1.3 are optional but should be included in the SOW if the Contract will involve work on Commonwealth Premises, such as for installation, FI&T and/or Training.  The Contractor is required to seek Approval from the Commonwealth if a Problematic Substance is to be brought onto Commonwealth Premises (other than those as part of the Supplies) by itself or its Subcontractors.  If not Approved, the Contractor is not to bring that Problematic Substance onto Commonwealth Premises.

Clause 8.1.1.3 requires the Contractor to notify the Commonwealth Representative of the maximum quantities of Approved Problematic Substance(s) to be brought onto Commonwealth Premises, before doing so.  This allows the Commonwealth time to confirm suitability and update the Defence ChemAlert database, if required.

Approval of a Problematic Substance requires a Safety Data Sheet (SDS) to be provided to the Commonwealth.  Under clause 8.1.1.4 this applies to both a Problematic Substance included in Supplies or Approved to bring onto Commonwealth Premises.  Delivery of the SDS is not required if the Contractor can identify that SDS within the ChemAlert database (which Defence holds a copy of).   DID-PM-HSE-SDS defines the requirements of a SDS.

Clause 8.1.2, Problematic Sources

Clause 8.1.2 is an optional clause that is included if the Contractor may need to use a Problematic Source on Commonwealth Premises, such as for installation or FI&T.  Such instances are rare.  Note that Problematic Sources in the Supplies were to be identified in the tender response and included in Annex C prior to ED (or may have been specified by the Commonwealth), hence, this clause only applies to Problematic Sources that the Contractor needs to use on Commonwealth Premises.

When the clause is included, details of the Problematic Source and its use need to be Approved by the Commonwealth Representative.  The Commonwealth Representative should confirm that the Contractor is licenced for use of the Problematic Source (refer COC clause 3.4, Authorisations), or is covered by a Defence source licence, and that it will be used in accordance with applicable safe work procedures.  If there is no likelihood of a Problematic Source being used by the Contractor on Commonwealth Premises, then the clause can be replaced with ‘Not used’.  If the need for the clause is unclear, the clause may be included in the RFT with the ‘Note to tenderers’.

Optional clause 8.1.2.2 should be included if the Commonwealth may provide an item containing a Problematic Source to the Contractor.  In this case the Problematic Source should be licenced by Defence and Defence must provide the Contractor with safety-related information in accordance with CASsafe and the WHS Act.

Drafters should review clause 8.1 and include the optional clauses and any notes to tenderers as indicated above.

Related Clauses:	TDR D-2, Problematic Substances and Problematic Sources in the Supplies

COC clause 3.4, Authorisations

COC clause 12.4, Work Health and Safety

SOW clause 2.3, Deliverable Data Items

SOW clause 8.4, Incident Reporting and Remediation

Annex C, Problematic Substances and Problematic Sources in Supplies

DID-PM-HSE-SDS defines requirements for Safety Data Sheets.

Further Reading:	Work Health and Safety Regulations 2012 (Cth)

Defence Radiation Safety Manual (DRSM)

Defence Safety Manual (SafetyMan)

Schedules 1 and 4 of the Ozone Protection and Synthetic Greenhouse Gas Management Act 1989

Code of practice: Preparation of Safety Data Sheets for Hazardous Chemicals:

https://www.safeworkaustralia.gov.au/safety-topic/hazards/chemicals/safety-data-sheets

https://www.safeworkaustralia.gov.au/doc/model-code-practice-preparation-safety-data-sheets-hazardous-chemicals

Australian Code for the Transport of Dangerous Goods by Road and Rail (National Transport Commission) (ADG Code):

https://www.ntc.gov.au/codes-and-guidelines/australian-dangerous-goods-code

Classifying Chemicals and the Globally Harmonized System of Classification and Labelling of Chemicals (GHS), Seventh Revised Edition (United Nations, 2023):

https://www.safeworkaustralia.gov.au/safety-topic/hazards/chemicals/classifying-chemicals

Environmental Management

Status:	Optional

Purpose:	Clause 8.2.1 is included to capture any work effort associated with compliance with COC clause 12.5, Environmental Obligations.

Guidance:	Contractors are obliged to comply with relevant legislation, including environmental legislation (see clause 12.5 of the COC).  Environmental management requirements will often not be required in the SOW when all work will be undertaken at the Contractor’s facilities, aside from deliveries, in which case the clauses below the heading can be deleted and heading clause annotated with ‘Not used’.

Note that environmental compliance requirements and characteristics of the Supplies should be identified in the specifications.

SOW clause 8.2 in the template is intended to apply a minimal approach to environmental management when work will be required on Commonwealth Premises, such as for installation and FI&T activities.  At clause 8.2.2 drafters should insert reference(s) to the Environmental Management Plan for the applicable Commonwealth Premises, or a site specific plan, procedures, or other relevant documents.  These documents should be made available to the tenderers and Contractor, often as GFI.

If there will be GFE that contains Ozone Depleting Substances (ODSs) or Synthetic Greenhouse Gases (SGGs) or if there are other specific requirements, drafters should add to the list of referenced plans and procedures as appropriate.

Drafters are to determine if there is a need to address environmental management for work on bases, and if more significant issues are applicable.  If required, the clauses should be seen as a starting point for identifying applicable reference documents and for further development when required.

Related Clauses:	COC clause 12.5, Environmental Obligations

Further Reading:	Environment Protection and Biodiversity Conservation Act 1999 (Cth)

Other environmental legislation, such as the Hazardous Waste (Regulation of Exports and Imports) Act 1989 (Cth) and Ozone Protection and Synthetic Greenhouse Gas Management Act 1989 (Cth)

CASG-2-Manual (E&T) 12-8-001 Materiel Systems Environmental Management

Work Health and Safety

Status:	Core (with options)

Purpose:	To require the Contractor to manage WHS and to enable the Commonwealth to discharge its duties under the WHS Legislation.

Guidance:	Under the WHS Legislation, the Commonwealth bears a duty to ensure the health and safety of workers engaged, or caused to be engaged, by the Commonwealth, or whose work activities are influenced or directed by the Commonwealth.  This duty includes responsibilities for Contractor and Subcontractor Personnel and, as a result, clause 8.3 is a core clause.

Clause 8.3.1 is included to capture any work effort associated with compliance with COC clause 12.4.  Clause 8.3.1 is core for all Contracts.

The first set of optional clauses, clauses 8.3.2 and 8.3.3, are included in the Contract if the Contractor or Subcontractors will perform work on Commonwealth Premises.  This may be required for the installation of equipment, the delivery of Training, and/or for FI&T.  Clause 8.3.2 requires that the Contractor, if requested by the Commonwealth Representative, provide evidence of the Authorisations, risk assessments and planning needed to undertake the work on Commonwealth Premises.  Authorisations are required under COC clause 3.4.

Clause 8.3.3 requires Contractor and Subcontractor Personnel to attend safety-related briefings for the Commonwealth Premises where work will be performed.  Briefings may be provided by the Commonwealth or a third party (eg, base security) when arranged by the Commonwealth.  If no briefings are required, then the clause may be deleted and replaced with ‘Not used’.

The second set of optional clauses, clauses 8.3.4 to 8.3.6, is to be included when work will be conducted on Commonwealth Premises and there is a need to inform Contractor and/or Subcontractor staff of hazards in the vicinity of where the work will be conducted.  When these clauses are included in the SOW, Annex D, Known Hazards at Commonwealth Premises, must also be included to list the hazards to which workers may be exposed.  This would include when Contractor / Subcontractor staff would be expected to undertake a safety risk assessment or require additional resources (eg, personal protective equipment) in relation to a hazard.  For example, for work near high voltage electricity, information about no-go zones would be appropriate to include in Annex D.  Further, any equipment to be mounted on a wall in a building that contains asbestos sheeting should be identified as this requires special safety precautions.  When required, these clauses can be included without change, but Annex D requires development and supporting documentation to be provided (eg, safety hazard reports).  Refer to the Annex D guidance below and notes to drafters within Annex D for further information.

Drafters should review clause 8.3 as indicated above and include the two sets of optional clauses and Annex D as required.

Related Clauses:	COC clause 3.4, Authorisations

COC clause 12.4, Work Health and Safety

SOW clause 8.4, Incident Reporting and Remediation

Annex D, Known Hazards at Commonwealth Premises

Further Reading:	Defence Safety Manual (SafetyMan)

CASG WHS Management System (CASsafe)

WHS Legislation

Codes of practice approved under section 274 of the Work Health and Safety Act 2011 (Cth)

Incident Reporting and Remediation

Status:	Core

Purpose:	To outline the processes for how the parties can assist each other to comply with mandatory reporting requirements under the WHS Legislation.

Guidance:	This clause creates obligations on both parties to meet the incident notification requirements of the WHS Legislation.

Clause 8.4 defines the reporting requirements for Notifiable Incidents.  Notifiable Incidents are defined in WHS Legislation (via the Glossary) to mean the death of a person, a serious injury or illness of a person, or a dangerous incident (eg, a near miss).  Under the WHS Legislation, these incidents must be reported to the applicable WHS regulator.  The regulator may subsequently undertake investigations and issue directives in relation to the Notifiable Incident.

Under the WHS Legislation, Defence must report Notifiable Incidents to Comcare.  The Contractor and Subcontractors must report Notifiable Incidents to their respective regulators, which in most cases will be a State or Territory regulator but for corporations licensed under the Safety Rehabilitation and Compensation Act 1988 (Cth) (non-Commonwealth licensees), this will also be Comcare.  Clause 8.4 requires the Contractor and Subcontractors also inform the Commonwealth of applicable Notifiable Incidents as the Commonwealth must notify Comcare.  Applicable Notifiable Incidents, reportable by the Commonwealth to Comcare, will include all those involving Commonwealth Personnel or on Commonwealth Premises, and other notifiable incidents that arise out of the conduct of Defence’s business or undertaking (eg, if the Commonwealth specified a procedure that was being used at the time of the incident).  Clause 8.4 requires that the Commonwealth be provided with copies of notice(s) or other documentation issued by the relevant Commonwealth, State or Territory regulator to the Contractor or Subcontractor.

For all Notifiable Incidents involving Commonwealth Premises, Commonwealth Personnel and Commonwealth-specified procedures (including within Australia and overseas), clauses 8.4.1 and 8.4.2 instigate a reporting process in accordance with the SafetyMan, which requires completion of an incident report (Form AE527) which may include use of the Sentinel Event Kiosk hosted on the DPN.

In addition to the notification required under clause 8.4.1, the Commonwealth is to receive details of all notices and other formal communications (for Notifiable Incidents) between the Contractor and Subcontractors and their regulator(s), in accordance with clause 12.4 of the COC.  This is included through clause 8.4.3.

Clause 8.4.4 is a ‘reciprocal’ obligation on the Commonwealth to support the Contractor by informing the Contractor of Notifiable Incidents that the Contractor must report to their regulator (eg, for Contractor Personnel when visiting Commonwealth Premises).  This obligation includes providing the Contractor with details from the Commonwealth’s notice to Comcare.

Clause 8.4 is to be included in the RFT without alteration.

Related Clauses:	COC clause 12.4, Work Health and Safety

SOW clause 8.3, Work Health and Safety

Further Reading:	WHS Legislation

SafetyMan

WHS029 Guide to Work Health and Safety Incident Notification (Comcare)

Annex A – Specifications

The Annex A template includes a significant amount of embedded guidance that is not repeated here.

Under ASDEFCON (Complex Materiel) Volume 1, the Commonwealth determines the form of the required solution, rather than the tenderers developing a solution in response to a Function and Performance Specification (FPS).

Further reading includes:

- CASG Procedure (ENG) 12-3-005, Developing Function and Performance Specifications; and

- CASG Handbook (ENG) 12-3-004, Capability Definition Documents (Lite) Guide.

The references (above) are designed for more complex procurements that require an FPS; however, it provides useful background reading.  However, the handbook is closer to the scale of ‘requirements engineering’ applicable to the ASDEFCON (Complex Materiel) Volume 1 template.  Other references are included in guidance in Annex A.

Annex B – Contract Data Items

The note to drafters in Annex B provides guidance when read in conjunction with the guidance for each SOW clause that calls up a DID.

Annex C – Problematic Substances and Problematic Sources

Annex C lists the Approved Problematic Substances and Problematic Sources within the Supplies.  This list is developed from the successful tenderer’s response to TDR D-2 and should be populated before the Effective Date.  As ASDEFCON (Complex Materiel) Volume 1 is used to procure off-the-shelf items, any subsequent changes should be minimal, if required at all.

If the Commonwealth is aware of Problematic Substances that will be in the Supplies, because they are included in the specification (eg, a specified type of fuel) or all products available in the market use them, then these may be listed in draft Annex C prior to releasing the RFT.  This can save time and effort for both tenderers and the Commonwealth.

If additional Problematic Substances are identified and Approved after the Effective Date, these will be added via a contract change proposal.

The template does not include draft tables; however, as a guide they should include:

- for Problematic Substances:

identification details sufficient to identify the applicable SDS;

identification of the component that contains the Problematic Substance (eg, reference / part number, manufacturer, NSN); and

its purpose; and

for Problematic Sources:

identification details for the substance or apparatus;

the applicable radiation class;

identification of the component that is or contains the Problematic Source (eg, reference / part number, manufacturer, NSN); and

its purpose.

Annex D – Known Hazards at Commonwealth Premises

Annex D lists the known hazards to health and safety located on Commonwealth Premises at the location and in the nearby vicinity of where work will be performed under the Contract.  The aim of Annex D is to provide sufficient information to tenderers, and subsequently the Contractor, about the relevant health and safety hazards so that the Contractor can assess the risks and ensure that appropriate actions (eg, briefings, obtaining personal protective equipment) and safe work methods can be followed.

Annex D contains detailed guidance for development, notes to drafters, and includes examples in the draft tables.  Refer to the guidance for clauses 8.3.4 to 8.3.6 for further information.

https://creativecommons.org/licenses/by/4.0/

https://www.pmc.gov.au/government/commonwealth-coat-arms

The term ‘Approved’ is defined in the Glossary with reference to SOW clause 2.3.