CONTRACT SUMMARY WORK BREAKDOWN STRUCTURE

PURPOSE

This Annex sets out the Contract Summary Work Breakdown Structure (CSWBS) and associated CSWBS dictionary at Table 1.  The CSWBS defines the highest level decomposition of the Contract scope, and the Contract Work Breakdown Structure (CWBS) is derived from it.

Note: While particular CSWBS elements have the same title as particular SOW clauses (eg, Systems Engineering), the scope of the CSWBS elements differs from the scope of work identified under the identically-titled SOW clause.  This outcome occurs because the SOW clause includes requirements that can apply at any level of the decomposition of the Mission System(s) and/or Support System and, therefore, the associated work is included under the Mission System(s) and Support System CSWBS elements.

Note to drafters: Before releasing an RFT, drafters should review the list of CSWBS elements in the second column and amend the set of elements to ensure that the full scope of the Contract is properly identified.  For example:

if there are two or more different types of Mission System, drafters should insert each different type of Mission System as a separate level 2 element before the Support System element;

for other major deliverables (eg, facilities, a system integration laboratory, or a complex training simulator (eg, aircraft or bridge simulator)), drafters should confirm where in the hierarchy these items should naturally sit and either insert new CSWBS elements at level 2 or include them in the CSWBS definitions so that they will be properly identified at the lower levels in each tenderer’s CWBS; and

if platform integration and/or site installation are not Contract requirements, drafters should delete this level 2 element.

Drafters should also review the definitions for each of the CSWBS elements and update or modify them to suit the requirements of the draft Contract.  Drafters should not make arbitrary changes to the wording below, and if there are no substantive changes required to align with the overall scope of the draft Contract, the definitions should not be amended.

Table 1 - CSWBS and Associated Dictionary

| CSWBS Id | CSWBS Element | Definition |
| --- | --- | --- |
| 1.01 | Mission System | This element includes the standalone system or major end item used to accomplish the primary mission of the defence materiel item. This element includes all the segments, subsystems, and Software / hardware items that comprise the Mission System as well as all design, development, integration, assembly, test and checkout, and technical and management activities associated with the individual segments, subsystems and hardware / Software items. This element also includes the design, development, integration, assembly, test and checkout associated with the overall Mission System. When an overall system or system-of-systems comprises several Mission Systems being supplied under the Contract, each will be listed separately at level 2. |
| 1.02 | Support System | This element includes all of the physical support deliverables being generated under the Contract, including any effort associated with the acquisition of, and/or the design, development and production of, those physical deliverables. This element includes the effort associated with delivery, installation, integration, and check out of the physical support deliverables. This element includes the acquisition, design, development and production of any logistics resources associated with those physical deliverables (ie, the logistics resources required for the support of Support System elements such as Facilities, S&TE, etc). This element also includes any support services (eg, maintenance and supply) required under the Contract before any associated Contract (Support) comes into operation. |
| 1.03 | Platform / Site Integration and Installation | This element includes the effort involved in providing technical and engineering services to the platform manufacturer or integrator and/or the Commonwealth and Associated Parties for the platforms and sites during the installation and integration of the Mission System(s) into the host platform or site location. |
| 1.04 | Project Management | This element includes the business and administrative planning, organising, directing, co-ordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware / software elements and are not included in Systems Engineering, ILS or V&V. This element includes cost, schedule, performance measurement management, quality management, Defect administration, contract management, data management, vendor liaison, subcontract management, risk management, IV&V activities, life cycle cost, Contract activities for transition to operational service, Australian Industry Capability, and Technical Data and Software rights management. |
| 1.05 | Systems Engineering | This element includes the technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. This element includes the effort to define the system and the integrated planning and control of the technical program efforts of design engineering, specialty engineering, production engineering, configuration management, interface management and requirements management. This element also includes the effort to transform an operational need or statement of deficiency into a description of system requirements and a preferred system configuration / architecture. This element excludes the acquisition of, and/or the design, development, integration and production of, specific Mission System subsystems and components (both hardware and software). These activities are covered under the Mission System(s) CSWBS element(s). |
| 1.06 | Integrated Logistic Support | This element includes the overall planning, directing, and controlling of the ILS function. This element includes the effort associated with the logistics-analysis processes, the outcome of which result in the identification of the logistics resources (both range and scale) required to support both the Mission System and the Support System. This element excludes the acquisition of, and/or the design, development, integration and production of, specific Support System Components (eg, S&TE, Facilities, Software Support Environment, Training Equipment and Materials, etc). These activities are covered under the Support System CSWBS element. This element also excludes the acquisition, design, development, integration and production of the logistics resources required for the support of the individual Support System elements themselves, which are also covered under the Support System CSWBS element. |
| 1.07 | Verification and Validation | This element includes V&V management and infrastructure for the Mission System(s) and the Support System as well as the actual V&V for all phases of the Contract. This element includes processes that demonstrate that the engineering design and development process is complete, demonstrate that the design risks have been minimised, demonstrate that the system will meet specifications and determine whether the engineering design is supportable (practical, maintainable, safe, etc) for operational use. This element includes such tests as system demonstration, flight tests, sea trials, mobility demonstrations, stability tests, qualification operational test and evaluation, etc, and support thereto, required to prove the operational capability of the deliverable system. This element also includes logistics testing efforts to evaluate the achievement of Supportability goals and the adequacy of the Support System (eg, deliverable maintenance tools, test equipment, technical publications, maintenance instructions, personnel skills and training requirements, and Software support facility / environment elements). |