DATA ITEM DESCRIPTION

DID NAME:	DID-PM-DEF-CMS-2-V5.3

TITLE:	Contract Master Schedule

DESCRIPTION and intended use

The Contract Master Schedule (CMS) is the schedule model that describes the Contractor’s planned sequence of tasks/activities, milestones and decision points to enable the objectives of the Contract to be met.  Additionally, the CMS defines the current schedule status, comparing the current schedule with the contracted schedule (ie, the Delivery Schedule).  The CMS also compares the current schedule status with any applicable baseline schedule.

The Contractor uses the CMS, including or supplemented by subordinate schedules, to:

plan the tasks/activities and sequencing of those tasks/activities to achieve the requirements of the Contract, including the tasks/activities required to be performed by the Commonwealth and/or Associated Parties that interact with the Contractor’s tasks/activities;

provide schedule direction and status to the management team responsible for conduct of the work; and

forecast outcomes and resourcing requirements.

The Commonwealth uses the CMS to:

achieve assurance that the Contractor can meet its contractual obligations, including in relation to those tasks/activities required to be performed by the Commonwealth and/or Associated Parties that interact with the Contractor’s tasks/activities;

gain visibility into the Contractor’s planning;

understand and evaluate the Contractor’s approach to meeting the requirements of the Contract;

assist with monitoring the progress of the Contractor in meeting the requirements of the Contract; and

as a source of input into planning performed by the Commonwealth Representative.

For the purposes of ensuring a common understanding of schedule-related terminology, including as used in this DID, Annex A to this DID contains a list of terms that are applicable to the development and management of a schedule.

INTER-RELATIONSHIPS

The CMS inter-relates with the following data items, where these data items are required under the Contract:

Project Management Plan (PMP);

Contract Work Breakdown Structure (CWBS); and

Contract Status Report (CSR).

APPLICABLE DOCUMENTS

The following documents form a part of this DID to the extent specified herein:

| Nil. |  |
| --- | --- |

Preparation Instructions

Generic Format and Content

The data item shall comply with the general format, content and preparation instructions contained in the CDRL clause entitled ‘General Requirements for Data Items’.

The CMS shall be the primary schedule for the Contract, and all other schedules shall be subordinate to the CMS.

The CMS shall be capable of being displayed in a variety of formats, including:

a Gantt chart;

a listing of all tasks/activities, together with their planned and actual start and completion dates;

a listing of milestones (including Milestones in the Contract), together with their original baseline, current baseline, forecast and actual dates;

a breakdown of the Contract work into CWBS elements; and

a spreadsheet view that details the task/activity coding and associated attributes specified in the schedule model.

The CMS shall be capable of being displayed at the following levels:

Summary Level:  The Summary Level of the CMS shall provide a graphical display of Contract tasks/activities, key events, and milestones at Level 3 of the CWBS; and

Detailed Level:  The Detailed Level of the CMS shall provide a graphical display of all detail in the schedule model for the Contract.  A CMS generated at the Detailed Level shall be able to be rolled up to, and shall provide visibility of, the Summary Level.

The CMS shall be delivered as a copy of the CMS database using the schedule modelling software package identified in accordance with clause 3.2.2 of the SOW.  The CMS database shall include all database elements used by the Contractor to develop, manage and update the CMS (eg, filter definitions, resources and notes).  Any non-database elements of the CMS shall be delivered in accordance with the CDRL (eg, using Microsoft Word®).

Specific Content

Data to be Included

The CMS shall graphically depict the Contract schedule baseline and progress for all tasks/activities and milestones contained in the CMS.

The CMS shall graphically present or otherwise identify:

tasks/activities and their estimated durations;

milestones, including the Milestones identified in the Contract;

the relationships and dependencies between tasks/activities and milestones to be accomplished by or for the Contractor in the performance of its obligations under the Contract;

earliest and latest start and finish dates for all tasks/activities and milestones;

critical and non-critical paths (based on float calculations), and may identify other significant paths through the schedule through the use of attributes;

floats available on all tasks/activities and milestones;

allocated resources for each task/activity; and

notes on the use of the CMS, including a glossary of terms and symbols used.

The CMS shall include a summary representation of dependencies, transition and maturity points from the lower level detail contained in all subordinate schedules required to manage the work under the Contract, including:

all other schedules required under the Contract (eg, the Systems Engineering schedule and the Integrated Logistic Support schedule);

Subcontractor schedules, to the extent consistent with the schedule detail for the Contractor’s own schedule;

Milestones, and all milestones identified in the Contractor’s plans (eg, the Approved Verification and Validation Plan (V&VP)) and delivery milestones in Attachment C (if not already identified as Milestones);

other major events, as agreed between the Contractor and the Commonwealth Representative;

Commonwealth Representative tasks/activities and tasks/activities performed by Associated Parties, where such tasks/activities interface with, and may affect, Contractor tasks/activities, to the extent necessary so that the Commonwealth can confirm that it can meet its schedule-related obligations under the Contract, including those being undertaken by Associated Parties; and

significant reviews, such as System Reviews.

The CMS shall comply with the following general criteria:

with the exception of the first and last task/activity or milestone, all tasks/activities and milestones shall have at least one predecessor and successor;

all tasks/activities and milestones shall have early, late and baseline dates assigned, unless otherwise agreed between the parties;

all tasks/activities and milestones shall have an appropriate calendar applied;

calendars shall be identified for a normal working week and a calendar week, as defined under the Contract;

all Commonwealth deliverables to the Contractor shall be included in the schedule and logically connected to the tasks/activities that are dependent upon those deliverables in accordance with the following provisions:

for Commonwealth deliverables that drive particular Contractor tasks/activities and associated schedule timeframes (eg, access to Government Furnished Facilities (GFF) and provision of Government Furnished Equipment (GFE)), the Commonwealth deliverables shall be individually identified in, and logically connected into, the CMS; and

for Commonwealth deliverables that are generally required, but do not drive particular Contractor tasks/activities (eg, Government Furnished Data (GFD) that needs to be provided to the Contractor at ED but not returned to the Commonwealth until the end of the Contract), the Commonwealth deliverables need not be individually identified in the CMS (eg, they may be grouped together under a single schedule line);

all deliverables from Associated Parties to the Contractor shall be included in the schedule and logically connected to the tasks/activities that are dependent upon those deliverables in accordance with the same logic used in subclauses e(i) and e(ii) above;

tasks/activities and milestones that are constrained (eg, by Target Start or Target Finish constraints) shall have the reason for the constraint explained within a notes field in the CMS database;

tasks/activities shall be coded to allow sorting/filtering by CWBS and organisational breakdown structure;

the CMS shall be able to demonstrate traceability, both upwards to the complete CWBS, SOW and CDRL (which, for clarity, may be provided through the CWBS), and downwards to subordinate schedules (if any);

level of effort tasks/activities shall be incorporated into the CMS in a way that ensures that these tasks/activities do not materially affect the ability of the CMS to properly schedule (eg, by masking the critical path and/or near-critical paths); and

other than level of effort tasks under subclause j above, the CMS shall not contain tasks/activities that do not materially contribute to the delivery of either end-products or enabling products (eg, other direct costs (ODCs) and travel); and

compliance with these criteria is only necessary for tasks/activities that are not yet complete; however, retrospective changes to the CMS are not to be made.

The precedence relationships and dependencies in the CMS shall be consistent with:

all schedule constraints identified in the Contract (eg, in the Milestone entry and exit criteria); and

the entry and exit criteria for both Mandated System Reviews and Internal System Reviews.

Each submission of the CMS shall provide visibility of progress against the current Approved schedule baseline, including:

time progress against all tasks/activities;

the actual start and completion dates for all tasks/activities and milestones; and

the current forecast completion dates for all tasks/activities and milestones.

Narrative Analysis

Each new submission of the full CMS, as required by the CDRL, shall provide a narrative analysis for the newly proposed CMS, which contains:

a baseline change log, which identifies all of the baseline changes from the current Approved CMS;

an explanation of the cause of each Contract Milestone’s rescheduled date that is later than the milestone's current baseline date in the current Approved CMS; and

the identification of the possible impacts on other milestones and tasks/activities for the Contract, and a description of any proposed work-around plans to minimise the impact.

Annex:

- List of Schedule Terminology

ANNEX A TO
DID-PM-DEF-CMS-2

LIST OF SCHEDULE TERMINOLOGY

Terms and Definitions

The following terms are applicable to the development and management of a schedule:

Calendar. The arrangement of normal working days, together with non-working days, such as holidays, as well as special work days (ie, overtime periods) used to determine dates on which project work will be completed.

Constraints. Limits applied to network start and finish dates (eg, “finish no later than”). (Note: Certain types of constraints should be used judiciously because they may impact or distort the network critical path.)

Control Account. A natural management control point where the integration of scope, budget and schedule occurs. It represents the work assigned to one responsible organisational individual for the purpose of planning, monitoring and taking corrective action for the performance of one element of the CWBS.

Critical Path. A sequence of discrete tasks/activities in the network that has the longest total duration through the contract or project. Discrete tasks/activities along the critical path have the least amount of float/slack. The critical path and near-critical paths are calculated by the scheduling software application.

Duration. The length of time estimated (or realised) to accomplish a task/activity.

Early Finish (EF). The earliest finish date a task/activity or milestone can end. A computer-calculated date.

Early Start (ES). The earliest start date a task/activity or milestone can begin the precedence relationships. A computer-calculated date.

Free Float/Slack. The amount of time a task/activity or milestone can slip before it delays any of its successor tasks/activities or milestones.

Lag. An interval of time that must occur between a predecessor and successor task/activity or milestone. Since negative time is not demonstrable, negative lag is not to be used.  (Note: Lag should not be used to manipulate float/slack or constrain schedule.)

Late Finish (LF). The latest date a task/activity or milestone can finish without delaying the contract or project target completion date.  A computer-calculated date.

Late Start (LS). The latest start date a task/activity or milestone can start without delaying the contract or project target completion date.  A computer-calculated date.

Hammock Task/Activity. A task/activity that spans between two points in a schedule.  It has no set duration of its own, and its duration is derived from the difference in time between the two ‘connection points’ in the schedule.  (It can be thought of as ‘hanging’ between these two points in the same way a normal hammock may hang between two trees.)

Milestone. A specific definable accomplishment in the contract network, recognizable at a particular point in time.  Milestones have zero duration and do not consume resources.  Contract Milestones are identified in Attachment C to the Contract.

Percent Complete (Schedule). The proportion of a task/activity that has been completed to time now.  This usually involves updating or statusing the task/activity utilising one of the below methods:

updating the remaining time to complete (remaining duration) and the scheduling software will then automatically update the schedule percent complete; or

manually entering the physical percent complete value, as determined by the user.  This is considered expert judgement based on the physical progress of the task/activity.  If EVM is being applied, this assessment of progress would be defined through the applicable earned value techniques.

Planning Package.  The logical aggregation of future work within a control account that cannot yet be planned in detail at the work package or task/activity level.  When authorised work scope within a control account cannot be planned in the near-term, a planning package is used to hold the scope, schedule, and budget until the work is planned in detail and the planning package is converted into work packages. The planning package is time-phased with the known schedule requirements and is detail planned into work package(s) before any work is performed on the scope contained in the planning package.

Relationship/Dependency. These identify how predecessor and successor tasks/activities and milestones are logically linked. Relationships, also called network logic, are modelled in four ways:

FS (Finish to Start). A predecessor task/activity or milestone that must finish before a succeeding task/activity or milestone can start. FS relationships shall be used whenever possible.

SS (Start to Start). A predecessor task/activity or milestone that must start before a succeeding task/activity or milestone can start.

FF (Finish to Finish). A predecessor task/activity or milestone that must finish before a succeeding task/activity or milestone can finish.

SF (Start to Finish). A predecessor task/activity or milestone that must start before a succeeding task/activity or milestone can finish.

Rolling Wave Planning.  An iterative planning technique in which the work to be accomplished in the near term is planned in detail using work packages, while work further in the future is planned at a higher level using planning packages.

Schedule Margin. A management method for accommodating schedule contingencies.  (Note: It is a designated buffer that is identified separately from other tasks/activities in the schedule and considered part of the baseline.)  Schedule margin is the difference between contractual milestone date(s) and the contractor’s planned date(s) of accomplishment.

Subproject. A task/activity that represents a group of subordinate tasks/activities, which may be either internal to the schedule (in which case, it is the same as a Summary Task/Activity) or external to the schedule (eg, a team’s detailed schedule that is summarised into the main contract schedule).

Summary Task/Activity. A task/activity, which rolls up a series of directly related tasks/activities within the schedule’s coding structure into one summary task/activity (sometimes called ‘Main Tasks/Activities’).  There may be several layers of summary tasks/activities which can be designed to align with the CWBS.  Summary tasks/activities do not have a set duration; the duration is calculated from the underlying tasks/activities in the schedule structure.

Task/Activity. An element of work with duration.

Task/Activity Codes and Data Dictionary. A list of field definitions and code structures.  This list shall be provided to the Commonwealth.

Task/Activity and Milestone Descriptions. These are descriptive titles that are concise, complete, and clearly identify the work effort being accomplished.  Abbreviations may be used to shorten the descriptive titles.

Total Float/Slack. The amount of time a task/activity or milestone can slip before it delays the contract or project finish date.

User Defined Fields. Specific fields in the CMS defined by the user for management purposes.

Work Package. A natural sub-division of a control account and constitutes the basic building blocks used in detailed planning, controlling and measuring Contract performance. It describes work to be accomplished by a specific performing organisation and serves as a vehicle for monitoring and reporting progress of work. Work packages have scope, budget and scheduled start and finish dates.