MSR cHecklisT

Identification: MSR-CHECKLIST-IBR-V5.4

TITLE:	INTEGRATED BASELINE REVIEW Checklist

DESCRIPTION and intended use

The Integrated Baseline Review (IBR) is an integral part of Earned Value Management (EVM), which provides for the review of the Contractor’s execution plans, focusing on the assignment, definition, scheduling and resourcing of work, thus establishing early visibility into the acceptability of the Contractor’s planning for the Contract.  The IBR also reviews the methods and metrics used to measure Contractor performance and progress.  The focus is upon reviewing the technical merits and resourcing of the plan, and to assess the risk associated with the baseline.

The main objective of the IBR is to enable the Commonwealth to Approve the Performance Measurement Baseline (PMB) through assessing the Contractor’s baseline plan in accordance with Steps 1 to 5 of AS 4817:2019 Earned value management in project and programme management and CASG Manual (PM) 006 Defence Supplement to the Australian Standard for Earned Value Management, AS 4817, which includes assessing whether:

the complete Contract scope of work is covered in the Contract Work Breakdown Structure (CWBS);

the complete Contract scope can be accomplished within baseline cost and schedule constraints and that resources have been appropriately distributed to the Contract tasks;

there is a logical sequence of effort in the Baseline Contract Master Schedule (CMS) and subordinate schedules that support the achievement of the Contract Delivery Schedule;

the risks in resource allocations and in the performance of the Contract scope have been identified and the cost and schedule implications of those risks have been incorporated, where appropriate, into the baseline plan;

the Contractor’s baseline has been accurately incorporated into the Contractor’s EVM System by examination of at least two Earned Value Performance Reports (EVPRs); and

the proposed performance measures / Earned Value Techniques (EVTs) to be used to measure and report progress are appropriate and will provide meaningful indicators of work completed.

The IBR also helps to improve Commonwealth understanding of the PMB, resulting in a better appreciation of the Contractor’s performance management process and the techniques used to measure performance.  This common understanding of the baseline plan should enable improved partnering throughout the Contract and reduce misunderstandings.

This Mandated System Review (MSR) Checklist sets out the Commonwealth’s requirements and minimum expectations for the conduct of an IBR.  The level of consideration needed to address each of the checklist elements is dependent up on the scale and risks for the Contract.  Further requirements on the conduct of an IBR are provided in CASG-2-Instruction (PM) 003, Integrated Baseline Review and EVM System Review, which includes a number of compliance and assurance activities associated with assessing the checklist items for an IBR, including:

Commonwealth review of relevant documentation (eg, control account plans, subordinate schedules (including Subcontractor schedules), basis of estimates, and work authorisation documents);

Commonwealth on-site review of the Contractor’s proposed plan and management systems, including interviews with Contractor staff; and

follow-up actions, as required, to satisfy the Commonwealth that the baseline is valid and executable.

Capitalised terms used in this MSR Checklist, where these terms are not included in the Glossary to the Contract, have the meaning given in:

CASG Manual (PM) 006 Defence Supplement to the Australian Standard for Earned Value Management, AS 4817 (hereinafter referred to as ‘Defence Supplement’); and

AS 4817:2019 Earned value management in project and programme management (hereinafter referred to as ‘AS4817’).

INTER-RELATIONSHIPS

The IBR shall be conducted in accordance with the Approved System Review Plan (SRP), and shall be consistent with the following data items, where these data items are required under the Contract:

Project Management Plan (PMP); and

Earned Value Management Plan (EVMP).

The IBR inter-relates with the following data items, where these data items are required under the Contract:

Contract Work Breakdown Structure (CWBS);

Baseline Contract Master Schedule (CMS);

Earned Value Performance Report (EVPR);

System Review Plan (SRP);

Mission System Technical Documentation Tree (MSTDT);

Measurement Plan, including the Information Needs and Measures Specification, which the Contract may require to be delivered separately from the Measurement Plan; and

Australian Industry Capability (AIC) Plan.

The IBR also inter-relates with any risk registers for the Contract, including the Risk Register.

Note:  The Status column in the following three tables indicates whether or not the associated Checklist items are able to be tailored by the Contractor in its SRP, based on the following definitions:

Mandatory items are not to be tailored;

Highly Desirable items should not be tailored, but may be tailored depending upon the specifics of the Contract and the Contractor’s internal processes; and

Optional items may be tailored, based upon the specifics of the Contract and the Contractor’s internal processes.

Notwithstanding the Status assigned to each Checklist item, the items are to be included in the SRP if they are applicable.

Review Entry Criteria

| Item | Entry Criteria | Status |
| --- | --- | --- |
| 1. | All data items and documentation required to be delivered before IBR have been delivered (including the IBR agenda, the EVM System documentation, updated Risk Register, documentation requested by the Commonwealth (eg, as per clause 3.4a), and at least two complete EVPRs), and the Commonwealth Representative considers these documents to be suitable for the purposes of conducting IBR. | Mandatory |
|  | The CWBS reflects the entire scope of work for the Contract and is defined to an appropriate level of detail. The delivered CWBS complies with the requirements of DID-PM-DEF-CWBS. | Mandatory |
|  | The Baseline CMS aligns to the CWBS and is defined to an appropriate level of detail. The delivered Baseline CMS complies with the benchmark criteria in DID-PM-DEF-CMS. | Mandatory |
|  | Subcontractor baselines, where applicable, have been incorporated into the PMB, and IBRs on those Subcontractors have been successfully completed by the Contractor. | Mandatory |
|  | Risks with the potential to impact upon the viability of the PMB have been identified and documented, including any assumptions that may need to be referenced in the future. | Mandatory |
|  | Action items from any previous System Reviews or prior risk-reduction activities (eg, an Offer Definition and Improvement Activities phase), which affect IBR, have been successfully addressed or action plans agreed with the Commonwealth Representative. | Mandatory |

Review Checklist

| Item | Checklist Item | Status |
| --- | --- | --- |
| General |  |  |
|  | Were all entry criteria satisfied before starting IBR? | Mandatory |
|  | Has the impact of Approved and pending CCPs been assessed? | Highly Desirable |
|  | Have all Commonwealth Representative review comments against data items been adequately addressed? | Mandatory |
| Decomposing the Project Scope |  |  |
|  | Is all of the work defined in the Contract (including through the Price and Payments Schedules, Delivery Schedule, SOW, CDRL and the implied work through the DIDs) fully incorporated into the CWBS? Do the CWBS and CWBS Dictionary provide direct cross-references to the applicable elements and clauses of the Contract? | Mandatory |
|  | Is the work broken down to a manageable level? (This may mean that some CWBS branches may need to be broken down to level four or five while others can be managed at level two.) | Mandatory |
|  | Is all of the work defined in the Contractor’s management plans (eg, PMP) fully incorporated into the CWBS? | Mandatory |
|  | Is all of the work defined in the Subcontracts, including the Contractor’s work associated with managing the Subcontracts, fully incorporated into the CWBS? Is this work clearly identified? | Mandatory |
|  | Is the CWBS structured around the major products to be delivered under the Contract (eg, Mission Systems) and is the breakdown of each Mission System in the CWBS consistent with the product breakdown structure for that Mission System? | Mandatory |
|  | Is the CWBS and associated CWBS Dictionary internally consistent (ie, no overlaps or gaps)? Are all CWBS elements mutually exclusive? Is any related work, which is excluded from a CWBS element, clearly identified? | Mandatory |
|  | Does the CWBS Dictionary clearly describe the full scope of work for each CWBS element? Is the responsible manager clearly identified? Does each Control Account Manager’s (CAM’s) understanding of the CWBS elements applicable to them align with the CWBS Dictionary? | Mandatory |
|  | Does each product in the CWBS have an associated specification, with a plan to develop and baseline the specification at an appropriate time? | Mandatory |
|  | Does the hierarchy of specifications and design documents defined in the MSTDT map to the CWBS? | Mandatory |
|  | Do key CWBS elements have defined entry and exit criteria, including, where applicable, acceptance requirements? Are the entry and exit criteria for Milestones and System Reviews, which are defined in the Contract (including, where applicable, the Approved SRP), traceable to the applicable CWBS elements? | Mandatory |
|  | Are the Contractor’s risk treatments, which involve work, identifiable in the CWBS? | Mandatory |
| Assign Responsibility |  |  |
|  | Has responsibility been assigned for each Control Account and Work Package (eg, through the Organisation Breakdown Structure (OBS) or the Responsibility Assignment Matrix (RAM)) to an appropriate CAM and Work Package manager, respectively? | Mandatory |
|  | Is the work assigned to one responsible organisation, including Subcontractors, in a manner that represents the way in which work is to be performed? | Mandatory |
|  | Is the RAM consistent with Control Account authorisations? | Mandatory |
|  | Even though the Control Account has been defined, does the Contractor have the human resources to resource the work? | Mandatory |
|  | For each component product within the Mission System product breakdown structure, does the CWBS facilitate clear and visible accountability for ensuring that the delivered component product meets its specification? | Mandatory |
|  | Has an appropriate division of responsibility been defined for: the overall management of Subcontracts; and the management of those elements of Subcontracts, which either interface with, or are subordinate to, other CWBS elements (eg, lower-level products within the Mission System product breakdown structure)? | Mandatory |
|  | How does the Subcontract management plan (or equivalent documented process) provide assurance that Subcontractor resourced plans are supportive of timely accomplishment of the required work scope? | Mandatory |
|  | Do work authorisation documents describe the scope of work that CAMs are authorised to perform, and provide a schedule and budget for the work, and coding against which the work is to be charged? Is the work scope, schedule, budget and coding consistent with source documents (eg, Contract Delivery Schedule, Baseline CMS, RAM, CWBS Dictionary, Control Account Plans, etc)? | Mandatory |
|  | Is the organisation assigned in the RAM, also the responsible organisation identified in the work authorisation documents? | Mandatory |
|  | Are the work authorisation documents approved and signed by the responsible functional managers designated in the RAM? | Mandatory |
|  | Do the CAMs and Work Package managers have an adequate understanding of EVM and its implementation for the Contract, including the proposed tools to be used? | Mandatory |
|  | Do the CAMs understand the scope of the work they are responsible for? | Mandatory |
|  | Do the CAMs have the necessary skills to be able to manage the Control Accounts effectively? | Mandatory |
|  | Where a CAM is responsible for multiple Control Accounts, they may report up through a single or multiple functional managers. In this case, how are conflicts of interests resolved between Control Accounts related to a single functional area or between multiple functional areas? | Mandatory |
|  | Does the CAM accept responsibility for achieving their assigned work scope, schedule, and resource targets? | Mandatory |
|  | Can the CAM demonstrate the basis of planning (resource and schedule estimates)? | Mandatory |
|  | Is the process for risk management clearly defined and understood? Do CAMs understand processes for escalating risks, communicating changes, and statusing their progress? | Mandatory |
|  | Is the process for escalating issues within teams and between teams defined and understood? | Mandatory |
| Schedule the Work |  |  |
|  | Is the Baseline CMS derived from, and traceable to, the CWBS? | Mandatory |
|  | Does the Baseline CMS comply with DID-PM-DEF-CMS? | Mandatory |
|  | Is the Baseline CMS structurally sound (eg, are all tasks suitably linked, have the appropriate precedence relationships, and minimise the use of forced constraints, such as ‘must start on’)? Does the Baseline CMS show the baseline, estimated start and finish dates, and float data, and will it enable progress data to be provided through the Statused CMS? | Mandatory |
|  | Does the Baseline CMS represent a logical sequence of activities to satisfy the Contract requirements? Is the logic consistent with the Contractor’s strategies, as set out in the applicable Contract management plans (eg, the integration and test strategy, Verification and Validation (V&V) strategy, Integrated Logistic Support (ILS) strategy, and Transition strategy)? | Mandatory |
|  | Does the Baseline CMS comply with any Contract constraints (eg, as set out in the SOW or the Delivery Schedule)? | Mandatory |
|  | Does each task in the Baseline CMS have a well-defined outcome or deliverable (with the exception of level-of-effort tasks)? | Mandatory |
|  | Is the Baseline CMS consistent with all subordinate schedules, including CAM schedules and Subcontract schedules? | Mandatory |
|  | Does the Baseline CMS identify all Commonwealth interactions and dependencies that impact upon the Contract timeframes (eg, delivery of Government Furnished Material (GFM) and Government Furnished Services (GFS), attendance at System Reviews and review of data items), including for both Work Packages and Planning Packages, as required by DID-PM-DEF-CMS? | Mandatory |
|  | Are the Commonwealth’s interactions and dependencies in the Baseline CMS (eg, for GFM and GFS) tied to the Contractor’s Baseline CMS activities that reflect the Contractor’s actual need / consumption points? | Mandatory |
|  | Are significant decision points, constraints, and interfaces identified as key milestones in the Baseline CMS? | Mandatory |
|  | Are Work Packages: adequately described and clearly defined, with scheduled start and end dates; and reasonable in duration or with sufficient value milestones so as to minimise subjective work-in-process assessments? | Mandatory |
|  | Are the Planning Packages readily identifiable? Have the Planning Packages been defined appropriately, such that they are neither too general nor too large in scope, value, and duration? | Mandatory |
|  | Does the schedule trace successfully vertically and horizontally (identifying inter-dependencies)? | Mandatory |
|  | Are the lower-tier schedules vertically traceable to the Baseline CMS? | Mandatory |
|  | Are the estimates for task times and resource requirements for both Work Packages and Planning Packages stable, reasonable and precedented? Are these task times and resource requirements based on sound estimating principles and practices (eg, historical, quantitative and/or performance estimates)? | Mandatory |
|  | Have the task times and resource requirements for the higher-risk tasks (eg, software-development activities) been validated using multiple methods (eg, historical data and software-estimating models and tools)? | Mandatory |
|  | Is the basis of estimate for all task times and resource requirements for both Work Packages and Planning Packages documented and agreed by those who are responsible for managing the work? | Mandatory |
|  | Are all of the dependencies between Control Accounts clearly defined in the Baseline CMS, and is the meaning / expectations of each dependency clearly understood by each CAM and reflected in their respective plans? | Mandatory |
|  | Have all external dependencies been identified in the Baseline CMS and assessed for feasibility? (External dependencies include interfaces, facilities, works and other services, etc.) | Mandatory |
|  | Does the Baseline CMS include sufficient contingency to absorb “normal” variance (eg, expected levels of rework) as well as some level of unanticipated events? | Mandatory |
|  | Has the Baseline CMS been constructed bottom up from quantitative estimates, not driven by predetermined dates? | Mandatory |
|  | Has the Baseline CMS been resource levelled to reflect realistic staff availability, including Contract ramp-up, staff leave/absences, public holidays, training, Contract ramp-down, etc? | Mandatory |
|  | Have the critical and near-critical path activities been identified? | Mandatory |
|  | Have the implications of parallel activities in the Baseline CMS been analysed to produce a clear understanding of the risks, including resource overlaps? | Mandatory |
|  | Has schedule risk analysis been undertaken to assist in evaluating whether the delivery plan, as described by the Baseline CMS, is achievable? | Mandatory |
|  | Is the Subcontracted effort incorporated into the schedule and is it easily identified? Are the Subcontractor’s schedules vertically and horizontally integrated with the Baseline CMS? | Mandatory |
|  | Does the delivery plan, as described by the Baseline CMS, reflect learning curve efficiencies? | Highly Desirable |
|  | Where available, have purchase orders, drawing releases, Subcontract schedules and material ordering schedules been examined to confirm consistency between the order and delivery dates and between material milestones and material progress measures / EVTs? | Mandatory |
|  | Is the Contractor’s staff/skills profile reasonable, achievable, and derived from the Baseline CMS (particularly for critical skills where there may be known shortages, such as systems engineers, software engineers and integrated logistic support staff)? | Mandatory |
|  | Has the dependence on Key Persons been addressed in the schedule? | Mandatory |
|  | Are the resources required to meet the schedule available (including personnel, facilities, subcontractor capacity, etc)? | Mandatory |
|  | Are the breakdown and the scheduling of activities in the CWBS and Baseline CMS consistent with the AIC Plan, and vice versa? | Highly Desirable |
| Develop Time-Phased Budget |  |  |
|  | Does the Contractor have a budgeting process and are procedures documented? Do these processes and procedures meet the intent of Step 4 of AS4817 and the Defence Supplement and are they being followed? | Mandatory |
|  | Are Control Accounts adequately described, budgeted and decomposed to perform the work? Does the Contractor use historical performance data when estimating budgets? | Mandatory |
|  | Are the Baseline CMS and PMB integrated? Is the scheduling system integrated with the budgeting and cost accumulation systems? | Mandatory |
|  | Are the schedules (ie, Baseline CMS and subordinate schedules, including Subcontractor schedules) and PMB identical in planning and consistent in their representation of progress? Is the time phasing of the budget consistent with the schedule for achieving the work? | Mandatory |
|  | Are CAMs able to substantiate their budgets in terms of the total amount (dollars or hours), mix of resources and time-phasing? | Mandatory |
|  | Are Work Package budgets: reasonably realistic; established in terms of dollars, man-hours, or other measurable units; and planned by element of cost (ie, labour, material, other direct costs)? | Mandatory |
|  | Do Work Packages have more than one element of cost and if so how is progress to be determined so that the progress of one element is not distorted by the progress of another element? | Mandatory |
|  | Are the budgets assigned to Planning Packages distributed appropriately to reflect the expected outcome of detailed planning? | Mandatory |
|  | Are there adequate procedures for converting a Planning Package into a Work Package, including for the establishment of progress measures / EVTs for new Work Packages? | Mandatory |
|  | Are budgets allocated once and summed appropriately through the EVMS (eg, budgets for Work Packages and Planning Packages sum up to the budgets for Control Accounts)? Do all budget values in the EVPR total to the Contract Price? | Mandatory |
|  | Are all budgeting documents consistent throughout the EVMS? Is the budget information in the work authorisation documents, the RAM, and the internal performance measurement reports reconcilable? Are the amounts on internal reports consistent with the EVPR being forwarded to the Commonwealth? | Mandatory |
|  | Are Control Accounts broken down into different cost elements (eg, labour, materials, and other direct costs)? | Mandatory |
|  | Is Management Reserve (MR) clearly identified as such? Is the amount of MR consistent with the Contractor’s assessment of risk? | Mandatory |
|  | Are appropriate arrangements in place for the management of MR, including authorising its use? | Mandatory |
|  | If MR or Undistributed Budget (UB) has been utilised, do the transfers reconcile with EVPR amounts? | Highly Desirable |
|  | For any aspects of the Contract where there is a high probability of rework occurring within scope (eg, document revisions and retesting), has appropriate provision for that work been included in the PMB? | Mandatory |
|  | Where rework is likely to be required, do the Contractor’s procedures ensure that zero-budget Work Packages will not be used and that budget will be assigned, the effort planned and performance measured? | Mandatory |
|  | Have the Work Packages been established so that, if different elements of cost (eg, labour and materials) have been included in a Work Package, a variance in the performance of one element will not make an assessment of earned value misleading or inaccurate? | Mandatory |
|  | Is the Level of Effort (LOE) content of Control Account budgets only applied where appropriate? | Mandatory |
|  | Is the percentage of LOE across the Contract budget less than 20%? This percentage should be calculated across Contractor labour (ie, with materials and other costs (eg, Subcontractors) removed). | Mandatory |
|  | Are the time-phased budgets (PVs) for the same Work Packages consistent with the start and finish dates in the Baseline CMS? | Mandatory |
|  | Are the Control Account or WBS Element start and finish dates on the Control Account Plans consistent with the schedule dates in the Baseline CMS? | Mandatory |
|  | Are the budgets for material time-phased to support schedule requirements? | Mandatory |
|  | Have overheads / indirect costs been appropriately apportioned to the Contract? | Mandatory |
|  | Is the effect of all known Contractor risks incorporated into the Estimate At Completion (EAC)? | Mandatory |
| Assign Objective Measures of Performance |  |  |
|  | Do the CAMs assign performance measures / EVTs in accordance with company processes and procedures? Do these processes and procedures meet the intent of Step 5 of AS4817 and the Defence Supplement and are they being followed? | Mandatory |
|  | Do the Control Accounts identify performance measures / EVTs at Work Package level (or lower) to enable effective measurement of progress? | Mandatory |
|  | Are the performance measures / EVTs objective, verifiable, and appropriate for the nature of the work being undertaken, including the length of each Work Package? | Mandatory |
|  | Will progress being reported using the performance measure / EVT correlate with technical achievement? Have performance measures / EVTs been selected such that Planned Value and Actual Cost are consistent? | Mandatory |
|  | Are the performance measures / EVTs consistent with the measures identified in the Information Needs and Measures Specification (where a Measurement Plan or a stand-alone Information Needs and Measures Specification are a requirement of the Contract)? | Mandatory |
|  | Where the performance measure / EVT is identified as ‘percent complete’, does the CAM have objective measures to identify the progress at a lower level? | Mandatory |
|  | Where the ‘apportioned effort’ technique is applied can the related discrete Work Package be readily identified? | Mandatory |
|  | Are the performance measures / EVTs to be used for measuring Subcontracted effort appropriate? | Mandatory |
|  | How does the Contractor safeguard against: the use of more than one performance measure / EVT per Work Package; and/or changing of performance measures / EVTs once the Work Packages have commenced? | Mandatory |

Review Exit Criteria

| Item | Exit Criteria | Status |
| --- | --- | --- |
|  | All checklist items have been addressed to the satisfaction of the Contractor and the Commonwealth Representative. | Mandatory |
|  | All major problem and risk areas have been identified and resolved and, for minor problems and risks, corrective action plans have been recorded and agreed by the Commonwealth Representative. | Mandatory |
|  | The PMB has been Approved. For clarity, this means: the CWBS has been Approved; the Baseline CMS has been Approved; the Contractor’s staff/skills profile has been Approved; the performance measures / EVTs have been Approved; and the Planned Value has been Approved. | Mandatory |
|  | Plans for the measurement and analysis program for the next phase have been agreed by the Commonwealth Representative, including the measures to be collected, associated collection methods, and analysis techniques. | Mandatory |
|  | All risks identified during the course of IBR have been documented and analysed. | Mandatory |
|  | The risks with proceeding to the next phase are acceptable to the Commonwealth Representative. | Mandatory |
|  | All major corrective action requests have been closed. | Mandatory |
|  | All minor corrective action requests have been documented and assigned with agreed closure dates. | Mandatory |
|  | Review minutes have been prepared, Approved, and distributed in accordance with the Contract. | Mandatory |