DATA ITEM DESCRIPTION

DID NUMBER:	DID-ENG-MGT-GEOPP-V5.4

TITLE:	GROWTH, Evolution and Obsolescence Program PLAN

DESCRIPTION AND INTENDED USE

The Growth, Evolution and Obsolescence Program Plan (GEOPP) documents the Contractor’s plans and expectations for the management of technology changes for the system during the acquisition phase (ie, design, development and production) and over its Life-of-Type (LOT).  The primary target of the GEOPP is the Mission System; however, it shall also apply to any critical, high value Support System Components.  Where the term ‘system’ is used in this DID, it encompasses both the Mission System and the critical, high-value Support System Components.

The Contractor uses the GEOPP to:

provide direction to the Contractor’s and each Approved Subcontractor’s teams undertaking the growth, evolution and Obsolescence program activities under the Contract;

identify the applicable Change Drivers (as that term is defined in clause 6.2.5) and describe their implications for the system over its LOT;

document the approach, plans, processes and tools for managing technology changes over the LOT of the system, including to demonstrate to the Commonwealth that:

the system design addresses the Change Drivers and enables the system to be updated to incorporate technology upgrades when required over the LOT; and

the system will not have Obsolescence problems at the time of delivery; and

provide a baseline against which progress of these activities are monitored.

The Commonwealth uses the GEOPP to:

gain an accurate insight into the approach, plans and procedures being employed by the Contractor in the execution of activities related to the management of technology changes;

facilitate Commonwealth input into the likely areas of operational change and the technology areas of interest to the Commonwealth, including priorities;

gain assurance that the Contractor's design, development and production programs will not deliver equipment that has Obsolescence problems at the time of delivery;

gain assurance that the Contractor’s solutions for the Mission System and Support System minimises Life Cycle Costs (LCC) when system growth and Obsolescence issues are taken into consideration; and

provide input to the Commonwealth’s own planning.

INTER-RELATIONSHIPS

The GEOPP is subordinate to the following data items, where these data items are required under the Contract:

Project Management Plan (PMP);

Systems Engineering Management Plan (SEMP); and

Integrated Support Plan (ISP).

The GEOPP inter-relates with the following data items, where these data items are required under the Contract:

the governing plans for each of the specialty engineering areas;

Life Cycle Cost Management Plan (LCCMP);

Life Cycle Cost Report and Model (LCCRM);

System Review Plan (SRP);

System Architecture Description (SAD); and

Contract Master Schedule (CMS).

APPLICABLE DOCUMENTS

The following documents form a part of this DID to the extent specified herein:

| Nil. |  |
| --- | --- |

PREPARATION INSTRUCTIONS

Generic Format and Content

The data item shall comply with the general format, content and preparation instructions contained in the CDRL clause entitled ‘General Requirements for Data Items’.

The data item shall include a traceability matrix that defines how each specific content requirement, as contained in this DID, is addressed by sections within the data item.

Specific Content

General

The GEOPP shall describe the objectives, scope, constraints, and assumptions associated with the growth, evolution and Obsolescence program.

The GEOPP shall describe the system(s) addressed through the GEOPP, including the design maturity and design characteristics relevant to the conduct of the growth, evolution and Obsolescence program.

Program Organisation

The GEOPP shall identify and describe in detail the responsibilities of the organisation(s) and individuals tasked with managing the growth, evolution and Obsolescence program, including those of Subcontractors.

The GEOPP shall identify the level of staffing to be allocated to the growth, evolution and Obsolescence program, including identifying any specialist resources required.

Program Strategy

The GEOPP shall describe the Contractor’s strategy for undertaking the growth, evolution and Obsolescence program, including:

explaining how the Contractor will ensure that the growth, evolution and Obsolescence program meets the objectives and outcomes identified in clause 3 of this DID and the growth, evolution and Obsolescence program provisions of the SOW;

describing how the growth, evolution and Obsolescence program will identify and provide the information required by this DID, including the methodology for:

identifying the initial set of Change Drivers (refer clause 6.2.5) and the subsequent changes to these Change Drivers as circumstances change, including in relation to operational and system imperatives;

identifying potential technology solutions over the period of the Contract, including assessing the maturity of these technology solutions and determining when they are likely to be sufficiently mature for incorporation into the Mission System;

incorporating inputs from the Commonwealth, and other activities under the Contract (eg, Supportability analyses, reliability growth and LCC analyses) and, if applicable, under the Contract (Support) (eg, Obsolescence monitoring); and

identifying likely Obsolescence problems over the period of the Contract, including determining the timeframes when these problems should be addressed (eg, in relation to Milestones relating to the design, development and implementation of the Mission System);

describing the Contractor’s plans for incorporating Approved Subcontractors into the growth, evolution and Obsolescence program;

describing the interrelationships and interactions between the growth, evolution and Obsolescence program, the broader systems engineering program for the Mission System, the speciality engineering programs, and the Integrated Logistics Support (ILS) program;

describing how the Contractor will involve the Commonwealth in the growth, evolution and Obsolescence program (eg, in relation to threat changes); and

identifying the Contractor’s expectations of the Commonwealth.

The GEOPP shall include an overall flow diagram of the Contractor’s activities and, where applicable, Subcontractors’ activities in relation to achieving the required growth, evolution and Obsolescence program outcomes.  This flow shall be sequentially arranged to include:

all significant growth, evolution and Obsolescence program milestones and work activities, including the flow and staging of the different streams of activity for the program, including Change Driver activities (eg, technology developments, Obsolescence monitoring and operational changes) and Mission System design activities;

the integration of the growth, evolution and Obsolescence program into the broader systems engineering and ILS programs;

the entity or group responsible for each growth, evolution and Obsolescence program activity; and

any additional information that clarifies the description of the growth, evolution and Obsolescence program.

The flow diagram shall reflect predicted dates for significant milestones, as set out in the Approved CMS.

Systems, Processes and Tools

The GEOPP shall describe the systems, processes and tools to be employed by the Contractor and Approved Subcontractors to satisfy the growth, evolution and Obsolescence requirements of the Contract, including:

describing the key activities to be performed, when and by whom, and describing the systems, processes and tools that facilitate and/or enable these activities to be performed;

describing the linkages to the configuration change processes under the Contract and, if applicable, the Contract (Support), including for Software changes, describing the criteria to be used to prioritise the changes and package those changes into Software Releases; and

describing the systems, processes and tools to capture data, monitor and report on the achievement of the growth, evolution and Obsolescence program, including in relation to:

the information required to be provided through the relevant Contract progress reporting mechanisms (eg, Contract Status Report (CSR) and CMS); and

the information needs and associated measures established under the measurement program (if such a program is required by the SOW) to monitor the growth, evolution and Obsolescence program and the achievement of the required outcomes.

Change Drivers

The GEOPP shall identify the change drivers relevant to the system (‘Change Drivers’), including those identified:

in the Operational Concept Document (OCD) and the Function and Performance Specification (FPS);

by the Commonwealth in addition to those identified in the OCD and FPS (eg, that may have arisen due to a changing threat environment or evolving operational needs and/or from its knowledge of the market); and

by the Contractor (eg, from its knowledge of the market, trade studies conducted as part of the design of the system, and/or Obsolescence studies conducted as part of the design and implementation of the Support System).

The Change Drivers identified in the GEOPP shall include those identified from an assessment over the forecast LOT of the system in relation to:

evolution of technology;

changes to threats, including cyber threats;

changes to user needs;

changes to external systems and interfaces including, if applicable, changes to host systems (ie, the materiel systems, platforms or information technology networks for which the system being analysed is a component);

Supportability considerations (eg, Obsolescence and reliability growth); or

system enhancements or upgrades, including those planned by the Contractor or component element suppliers.

Candidate Elements

The GEOPP shall identify candidate elements for change based on an assessment of the potential areas of the system that may change during the post-design phase (ie, post-DDR) or over the LOT of the system due to the Change Drivers identified in response to clause 6.2.3.

Choice of candidate elements should include a consideration of system hardware and Software, as well as elements that interface and integrate with humans.  An element may be at any level of the system hierarchy and is not necessarily a Hardware Configuration Item (HWCI) or Computer Software Configuration item (CSCI) (ie, elements may include subsystems, segments or groups of design components).

The primary candidate elements are expected to come from the Mission System; however, candidate elements should also be identified for any critical, high value Support System components.  Candidate elements are to include those elements under the control of Subcontractors.

The GEOPP shall include the rationale for either including or excluding elements of the system as candidate elements for change.  Although candidate elements may be assessed early in the design process, the list needs to be reassessed (in updates to the GEOPP) as the design matures and all parties develop greater knowledge of possible future changes.

Obsolescence Considerations

Where the Change Driver for a candidate element is identified as due to Obsolescence, the GEOPP shall describe and justify the Contractor’s recommended strategy for treating the Obsolescence risks, taking into consideration the costs, timeframes, likely ease of making changes, and Capability implications, and include the following potential strategies (which are not provided in any order of priority and more than one may be applicable for a particular candidate element or for products at different levels of the product hierarchy):

accept the risk and react to the Obsolescence problem when it arises;

undertake Obsolescence monitoring;

undertake a LOT buy of the affected product;

implement a modified Maintenance regime for the affected product to extend its remaining life;

substitute an alternative product that is form, fit and function compatible;

provide technology transparency – ensuring that the applicable Technical Data and Software rights are obtained for product interfaces, so that product substitution can be facilitated when Obsolescence problems occur;

incorporate flexible design concepts – ensuring that the design facilitates product substitution (refer clause 6.2.8.1); and

recognise planned system upgrades – ensuring that the Obsolescence risks are bounded because periodic system upgrades are planned over the LOT.

Design Aspects

The GEOPP shall identify design aspects for each candidate element that would allow those candidate elements to be either replaced or modified with new or updated technology.  Examples of relevant design aspects include the use of architectural features, such as:

standardised internal and external interfaces with the greatest potential design lifetime (ideally greater than the LOT);

an open, flexible infrastructure, capable of adaptation, extension and scaling to counter Obsolescence and to provide new functionality and capacity;

modularity of design;

use of standards and 'openness' of architecture; and

minimisation of software dependence upon the hardware platform.

Key interfaces are those most likely to be subject to change or with the greatest desired design life.  The GEOPP shall identify the key internal and external interfaces at which future change is likely to occur and discuss the design approach taken to ensure interface longevity.

The GEOPP shall identify likely impacts upon performance of the system that may be expected due to 'natural' evolution of technology and the consequence of that increased performance to the longevity of the overall design.

Acquisition Phase

For the identified candidate elements, the GEOPP shall identify the steps that will be taken by the Contractor, including the applicable scheduling and purchasing approach, to ensure that:

at the time of delivery, a balance has been achieved between the risks of immature technology and equipment Obsolescence (noting that a primary aim of the GEOPP is to demonstrate that the Contractor has incorporated appropriate steps into its design-and-development plans to ensure that it will not deliver equipment that has Obsolescence problems); and

the Contractor’s solutions for the Mission System and Support System will minimise LCC (as demonstrated in accordance with the Approved LCCMP) when any expected through-life upgrades and enhancements are taken into consideration.

The GEOPP shall identify the issues relating to system growth that will be addressed at each Mandated System Review and each Internal System Review.  The entry and exit criteria and checklist items for each review, which relate to system growth, should be included in the SRP.

The GEOPP shall identify the key decision points in the schedule where design or purchasing decisions, which relate to either system Obsolescence or system growth, need to occur and the visibility of these that will be provided to the Commonwealth.

The GEOPP shall describe the Contractor’s methodology for incorporating the growth, evolution and Obsolescence program into the LCC program (with appropriate cross-references to the LCCMP).

Support Phase

For the identified candidate elements, the GEOPP shall identify the expected need for growth and evolution due to the Change Drivers, which have applicability during the support phase, as well as the Contractor’s plans and timeframes for incorporating any resulting upgrades to the system.

The GEOPP shall identify and explain any implications for the Commonwealth of not maintaining the system delivered to the Commonwealth with the most current configuration of that system, or applicable subsystem, as it is upgraded by the original equipment manufacturer throughout the LOT.  To the extent known, the GEOPP shall also identify any implications should the Commonwealth choose not to proceed with any particular upgrade.

Technical Data and Software Rights

For each of the areas of potential system growth, evolution and Obsolescence over the LOT, including the key interfaces discussed in response to clause 6.2.8.2, the GEOPP shall identify any issues or limitations associated with Technical Data and Software rights, the implications of those issues and limitations, and how the Contractor proposes that these are to be addressed.

One set of strategies may be defined at a particular level of the product hierarchy (eg, Mission System or major subsystem), while different strategies may also be defined for subordinate products.