DATA ITEM DESCRIPTION

DID NUMBER:	DID-ENG-MGT-HSIPP-V5.4

TITLE:	Human SYSTEM INTEGRATION Program Plan

DESCRIPTION and intended use

The Human System Integration (HSI) Program Plan (HSIPP) describes the Contractor's HSI program, identifies its elements, and explains how the elements will be managed to achieve the requirements of the Contract.

The Contractor uses the HSIPP to:

define, manage and monitor the Contractor’s HSI and related activities under the Contract;

describe how the objectives of, and requirements for, the HSI program set out in the SOW will be achieved for the Mission System(s), Support System, and any Developmental Support System Components; and

ensure that those parties (including the Commonwealth and Subcontractors) performing HSI-related activities understand their respective responsibilities, the processes to be used, and the time-frames involved.

The Commonwealth uses the HSIPP to:

understand and evaluate the HSI-related design and management processes used by the Contractor;

gain assurance that the Contractor’s activities will satisfy the objectives of the HSI program set out in the SOW and deliver Supplies that meet the HSI process and product requirements and achieve the required performance outcomes from a usability perspective under the defined operating conditions;

help to identify issues of concern that could prevent the achievement of the required performance in relation to HSI for the Mission System(s), Support System, or Developmental Support System Components; and

provide input into the Commonwealth's own planning.

INTER-RELATIONSHIPS

The HSIPP is subordinate to the following data items, where these data items are required under the Contract:

Systems Engineering Management Plan (SEMP);

Integrated Support Plan (ISP);

Configuration Management Plan (CMP); and

Verification and Validation Plan (V&VP).

The HSIPP inter-relates with the following data items, where these data items are required under the Contract:

System Specification (SS) (for each different type of Mission System);

Support System Specification (SSSPEC);

System Architecture Description (SAD);

Human System Integration Assurance Report (HSIAR);

the safety-related data items (eg, System Safety Program Plan (SSPP), Safety Case Report (SCR), Hazard Analysis Report (HAR) and Hazard Log (HL));

Task Analysis Report (TAR);

Performance Needs Analysis Report (PNAR); and

Verification Cross Reference Matrix (VCRM).

Applicable Documents

The following documents form a part of this DID to the extent specified herein:

|  | Refer to the HSI-related standards identified in the HSI clause of the SOW and in the specifications attached at Annex A to the SOW. |
| --- | --- |

Preparation Instructions

Generic Format and Content

The data item shall comply with the general format, content and preparation instructions contained in the CDRL clause entitled ‘General Requirements for Data Items’.

When the Contract has specified delivery of another data item that contains aspects of the required information, the HSIPP should summarise these aspects and refer to the other data item.

The data item shall include a traceability matrix that defines how each specific content requirement, as contained in this DID, is addressed by sections within the data item.

Specific Content

Program Overview

The HSIPP shall provide an overview of the Contractor’s HSI program for the Contract, including:

defining the scope and purpose of the HSIPP, including its relationships to higher-level plans (eg, the plans identified at clause 4.1) and to relevant plans at the same level (eg, management plans for interfacing domains);

identifying and describing the nature and significance of the HSI concerns that will be managed through the HSIPP, including in relation to the Mission System(s), Support System and any Developmental Support System Components; and

describing any constraints, assumptions and risks associated with the program.

Organisation

The HSIPP shall describe the HSI organisation within the Contractor’s overall organisation, including:

details of the Contractor’s organisational element that is responsible for planning and executing the HSI program, including numbers and competencies;

how the necessary competencies will be identified, obtained and retained over the period of the Contract;

a description of the relationships to any other areas within the Contractor’s organisation that are either:

involved with or support the Contractor’s HSI program; or

will be affected by, or receive inputs from, the HSI program, including the organisational elements responsible for equipment and software design, Training, V&V, Integrated Logistic Support (ILS), and other specialty engineering programs (eg, system safety, system security and Integrated Reliability, Maintainability and Testability (IRMT) program); and

whether or not Subcontractors will be incorporated into the program and, if so, the details of the Subcontractors, including the nature and scope of the work to be undertaken.

HSI Strategy

The HSIPP shall include a summary graphic showing how the Contractor plans to conduct the HSI program for the Mission System(s), Support System and any Developmental Support System Components, including:

the flow of HSI activities, showing the steps and intermediate milestones (including Milestones) to satisfy the HSI objectives and requirements for the Contract, including the major HSI-related tests, evaluations, and demonstrations;

the integration of the HSI program with other key discipline areas, including system design, software development, V&V, system safety, IRMT and system security; and

any additional information that clarifies the strategy for the HSI program.

The HSIPP shall include an overview of each key activity and milestone in the summary graphic, including:

a brief description of the scope of work; and

entry and exit criteria, and dependencies on the Commonwealth and Associated Parties.

HSI Management Processes and Activities

The HSIPP shall provide an overview of the management processes and activities to be applied to the HSI Program, including:

describing the processes to be used to identify and characterise the HSI considerations;

describing the implementation and maintenance of a HSI RAIDOC (Risks, Assumptions, Issues, Dependencies, Opportunities and Constraints) Register (HSIRR) to capture, track, and communicate identified HSI considerations, with the HSIRR to be:

a separate entity from the HSIPP due to the dynamic nature of the content of the HSIRR; and

based on, or derived from, the HSIRR Template provided at Annex A to this DID;

describing the processes and tools for integrating the HSI considerations identified in the HSIRR into the Contractor’s HSI activities for the Contract;

identifying how HSI considerations will be communicated with the Commonwealth and integrated with the Contractor’s risk, issue and opportunity management processes;

describing the Human Factors (HF) analytical methods, tools and techniques that will be used at each stage of the Contract, including V&V activities;

describing how human-related trade-offs are to be analysed; and

identifying the expected updates to the HSIPP and the HSI-related reports and outputs to be provided to the Commonwealth.

Tailoring of Applicable Standards

Note: As set out in the SOW, the Commonwealth will work collaboratively with the Contractor to agree the tailoring of the specified HSI standard(s) prior to the initial submission of the HSIPP.

The HSIPP shall identify the agreed application of the HSI process standard(s) identified in the SOW (or equivalent standard(s) Approved by the Commonwealth Representative), including:

identifying the specific provisions from the standard(s) by section;

providing the rationale for the tailoring of that section; and

describing the effects of the tailoring on the HSI program.

The HSIPP shall identify any other standards, including relevant sections, to be used in relation to HSI activities, including providing an overview of the application of the standard(s), including tailoring, to satisfy the HSI requirements of the Contract.

HSI in Subcontractor Efforts

The HSIPP shall define how all HSI work conducted by Subcontractors shall be scoped, managed and monitored to ensure the Contract objectives are met.

The HSIPP shall define how the Subcontractor HSI documentation will be controlled and integrated into the overall documentation for the Contract.

Expectations for Commonwealth Involvement in the HSI Program

The HSIPP shall identify the expectations of the Contractor with respect to the Commonwealth, including access to stakeholders (including end-users, operators and maintainers), in order to ensure the HSI objectives are met.

HSI in System Analysis

The HSIPP shall identify those HSI efforts in system analysis, as described in the tailoring of the standards identified under clause 6.2.5, and the organisational element(s) responsible for the performance of the Mission System, Support System and Developmental Support System Components.

The HSIPP shall describe the participation of HSI in system mission analysis, determination of system functional requirements and capabilities, allocation of system functional requirements to personnel and/or technology (hardware and software), development of system functional flows, and performance of system effectiveness studies.

HSI in Equipment Design

The HSIPP shall describe the HSI effort in the detailed design activities for the Mission System, Support System and Developmental Support System Components to:

ensure compliance with the product-related HSI requirements in the specifications at Annex A to the SOW; and

provide assurance that operational and support personnel can achieve their required missions, safely and effectively, when the Mission System is operated in accordance with the operational concepts defined through the OCD and the HSI Working Group (HSIWG) meetings and supported by the implemented Support System.

The HSIPP shall describe the HSI participation in studies, tests, mock-up evaluations, dynamic simulation, specification preparation and System Reviews.

HSI in Equipment Procedure Development

The HSIPP shall describe the methods used by the Contractor to ensure that:

operator and maintainer functions and tasks are allocated, organised, and sequenced for efficiency, safety, and reliability; and

the results of this effort are reflected in operational, technical and training publications, and in training system design.

Where the methods described in response to clause 6.2.10.1 involve interactions with the ILS activities, the HSIPP shall describe:

the specific points where these interactions occur;

details of the information to be exchanged; and

how the HSI function will ensure that the ILS outcomes are suitable from an HSI perspective.

Derivation of Personnel and Training Requirements

The HSIPP shall describe the methods by which the Contractor shall ensure that operator and maintainer Personnel and Training requirements are based upon human performance requirements developed from system analysis data.

HSI in Verification and Validation

The HSIPP shall describe HSI V&V as an integrated effort within the Contractor’s overall V&V program.

The HSIPP shall contain specific information to show how and when the Contractor is applying the HSI test and evaluation guidance in the standards identified under clause 6.2.5.

The HSIPP shall identify design milestones at which HSI tests are to be performed to assess compatibility among human performance requirements, personnel aptitude and skill requirements, training requirements, and equipment design aspects of personnel equipment and Software interfaces.

The HSIPP shall identify major V&V objectives and describe the V&V methods to be applied for the HSI program.

HSI Working Groups

Where the SOW requires the Contractor to establish a HSI Working Group (HSIWG), the HSIPP shall include a plan for the HSIWG, including:

objectives and the terms of reference for the HSIWG;

the membership and points of contact for the HSIWG; and

arrangements for the conduct of HSIWG meetings, including:

structure and roles of the HSIWG members;

timing and frequency of meetings; and

proposed methods for conflict resolution.

Annex:

- HSIRR Template