DATA ITEM DESCRIPTION

DID NUMBER:	DID-PM-DEF-CMS-V5.4

TITLE:	Contract Master Schedule

DESCRIPTION and intended use

The Contract Master Schedule (CMS) is the schedule model that describes the Contractor’s planned sequence of tasks/activities, milestones and decision points to enable the objectives of the Contract to be met.  Additionally, the CMS defines the current schedule status, comparing the current schedule with the contracted schedule (ie, the Delivery Schedule).  The CMS also compares the current schedule status with any applicable baseline schedule.

The Contractor uses the CMS, including or supplemented by subordinate schedules, to:

plan the tasks/activities and sequencing of those tasks/activities to achieve the requirements of the Contract, including the tasks/activities required to be performed by the Commonwealth and/or Associated Parties that interact with the Contractor’s tasks/activities;

provide schedule direction and status to the management team responsible for conduct of the work; and

forecast outcomes and resourcing requirements.

The Commonwealth uses the CMS to:

achieve assurance that the Contractor can meet its contractual obligations, including in relation to those tasks/activities required to be performed by the Commonwealth and/or Associated Parties that interact with the Contractor’s tasks/activities;

gain visibility into the Contractor’s planning;

understand and evaluate the Contractor’s approach to meeting the requirements of the Contract;

assist with monitoring the progress of the Contractor in meeting the requirements of the Contract; and

as a source of input to planning performed by the Commonwealth Representative.

For the purposes of this DID, the term, ‘Overlapping Period’, means the period of time during which the Contract and the Contract (Support), if applicable, operate in parallel.

For the purposes of ensuring a common understanding of schedule-related terminology, including as used in this DID, Annex A to this DID contains a list of terms that are applicable to the development and management of a schedule.

INTER-RELATIONSHIPS

The CMS inter-relates with the following data items, where these data items are required under the Contract:

Project Management Plan (PMP);

Support Services Management Plan (SSMP) under the Contract (Support);

Earned Value Management Plan (EVMP);

System Review Plan (SRP);

Measurement Plan (MEASP);

Contract Work Breakdown Structure (CWBS);

CWBS for the Contract (Support) (CWBS (Support));

Support Services Master Schedule (SSMS) under the Contract (Support);

Earned Value Performance Report (EVPR); and

Contract Status Report (CSR).

APPLICABLE DOCUMENTS

The following documents form a part of this DID to the extent specified herein:

| Nil. |  |
| --- | --- |

Preparation Instructions

Generic Format and Content

The data item shall comply with the general format, content and preparation instructions contained in the CDRL clause entitled ‘General Requirements for Data Items’.

The CMS shall be the primary schedule for the Contract, and all other schedules shall be subordinate to the CMS.

The CMS shall be delivered as two distinct deliverables, both of which are derived from the same schedule model, namely:

the Baseline CMS, which includes the schedule model (ie, from the schedule modelling software package) that provides the baseline against which progress is measured and, as such, would underpin the Performance Measurement Baseline (PMB), as may be used to calculate earned value under an Earned Value Management System (EVMS); and

Note: The Baseline CMS includes more information than a baseline produced using OPP.  The Baseline CMS includes all information contained in the schedule model that underpins the PMB, including schedule logic, resourcing information, schedule performance measures, and schedule notes that help explain the baseline.

the Statused CMS, which includes the statused version of the schedule model that provides the status of the Contractor’s progress against the Baseline CMS, and

except where otherwise explicitly identified, all references to the CMS in this DID include both the Baseline CMS and the Statused CMS.

The Baseline CMS shall be developed such that it would be regarded as sound and reliable by a prudent and competent contractor in the Contractor’s position.

The Statused CMS shall be statused such that it would be regarded as sound and reliable by a prudent and competent contractor in the Contractor’s position.

The Baseline CMS shall be initially developed and subsequently updated on a rolling wave basis in accordance with the project control requirements of the Contract (eg, Approved EVMP).

The CMS shall be capable of being displayed in a variety of formats, including:

a Gantt chart;

a listing of all tasks/activities, together with their planned and actual start and completion dates;

a listing of milestones (including Milestones in the Contract), together with their original baseline, current baseline, forecast, and actual dates;

a breakdown of the Contract work into functional groupings such as project management, design, production, installation, integration, testing and trialing, Integrated Logistic Support (ILS), etc, as well as into CWBS elements; and

a spreadsheet view that details the task/activity coding and associated attributes specified in the schedule model.

The CMS shall be capable of being displayed at a number of levels, as follows:

Summary Level:  The Summary Level of the CMS shall provide a graphical display of Contract tasks/activities, key events, and milestones at Level 3 of the CWBS;

Intermediate Level:  The Intermediate Level of the CMS shall provide a graphical display of Contract tasks/activities, key events, and milestones at the control account level of the CWBS.  A CMS generated at the Intermediate Level shall be able to be rolled up to, and shall provide visibility of, the Summary Level; and

Detailed Level:  The Detailed Level of the CMS shall provide a graphical display of all detail in the schedule model for the Contract.  A CMS generated at the Detailed Level shall be able to be rolled up to, and shall provide visibility of, both the Intermediate Level and the Summary Level.  The Detailed Level of the CMS shall be a synthesis of lower level tasks/activities contained in planning packages and work package schedules.

The CMS shall be delivered as a copy of the CMS database using the schedule modelling software package identified in accordance with clause 3.2.2 of the SOW.  The CMS database shall include all database elements used by the Contractor to develop, manage and update the CMS (eg, filter definitions, resources and notes).  Any non-database elements of the Baseline CMS shall be delivered in accordance with the CDRL (eg, using Microsoft Word®).

Specific Content

Data to be Included

The CMS shall graphically depict the Contract schedule baseline and progress for all tasks/activities and milestones contained in the CMS.

The CMS shall identify:

tasks/activities and their estimated durations;

milestones, including the Milestones identified in the Contract;

the relationships and dependencies between tasks/activities and milestones to be accomplished by or for the Contractor in the performance of its obligations under the Contract;

earliest and latest start and finish dates for all tasks/activities and milestones;

critical and non-critical paths (based on float calculations), and may identify other significant paths through the schedule through the use of attributes;

floats available on all tasks/activities and milestones;

allocated resources for each task/activity; and

notes on the use of the CMS, including a glossary of terms and symbols used.

The CMS shall include a summary representation of dependencies, transition and maturity points from the lower level detail contained in all subordinate schedules required to manage the work under the Contract, including:

all other schedules required under the Contract (eg, the Systems Engineering schedule and the ILS schedule) and, during the Overlapping Period, the Contract (Support) (eg, Phase In schedule);

Subcontractor schedules, to the extent consistent with the schedule detail for the Contractor’s own schedule;

Milestones, and all milestones identified in the Contractor’s plans (eg, the Approved SRP) and delivery milestones in Attachment C (if not already identified as Milestones);

other major events, as agreed between the Contractor and the Commonwealth Representative;

Commonwealth Representative tasks/activities and tasks/activities performed by Associated Parties, where such tasks/activities interface with, and may affect, Contractor tasks/activities, to the extent necessary so that the Commonwealth can confirm that it can meet its schedule-related obligations under the Contract, including those being undertaken by Associated Parties;

during the Overlapping Period, Contract (Support) tasks/activities that interact with Contract tasks/activities, including those tasks/activities associated with:

transitioning from the Contract to the Contract (Support);

achieving the requirements of the Operative Date Milestone under the Contract (Support); and

achieving the requirements of any Concurrent Contract Milestones (if applicable) under the Contract and the Contract (Support); and

significant reviews, such as System Reviews.

The CMS shall comply with the following general criteria:

with the exception of the first and last task/activity or milestone, all tasks/activities and milestones shall have at least one predecessor and successor;

all tasks/activities and milestones shall have early, late and baseline dates assigned, unless otherwise agreed between the parties;

all tasks/activities and milestones shall have an appropriate calendar applied;

calendars shall be identified for a normal working week and a calendar week, as defined under the Contract;

all Commonwealth deliverables to the Contractor shall be included in the schedule and logically connected to the tasks/activities that are dependent upon those deliverables in accordance with the following provisions:

for Commonwealth deliverables that drive particular Contractor tasks/activities and associated schedule timeframes (eg, access to Government Furnished Facilities (GFF) and provision of Government Furnished Equipment (GFE)), the Commonwealth deliverables shall be individually identified in, and logically connected into, the CMS, including for both work packages and planning packages; and

for Commonwealth deliverables that are generally required, but do not drive particular Contractor tasks/activities (eg, Government Furnished Data (GFD) that needs to be provided to the Contractor at ED but not returned to the Commonwealth until the end of the Contract), the Commonwealth deliverables need not be individually identified in the CMS (eg, they may be grouped together under a single schedule line, either within a work package or as part of a planning package);

all deliverables from Associated Parties to the Contractor shall be included in the schedule and logically connected to the tasks/activities that are dependent upon those deliverables in accordance with the same logic used in subclauses e(i) and e(ii) above;

tasks/activities and milestones that are constrained (eg, by Target Start or Target Finish constraints) shall have the reason for the constraint explained within a notes field in the CMS database;

tasks/activities shall be coded to allow sorting/filtering by CWBS, organisational breakdown structure, control account, work package or planning package, and team;

the CMS shall be able to demonstrate traceability, both upwards to the complete CWBS, SOW and CDRL (which, for clarity, may be provided through the CWBS), and downwards to subordinate schedules;

level of effort tasks/activities shall be incorporated into the CMS in a way that ensures that these tasks/activities do not materially affect the ability of the CMS to properly schedule (eg, by masking the critical path and/or near-critical paths); and

other than level of effort tasks under subclause j above, the CMS shall not contain tasks/activities that do not materially contribute to the delivery of either end-products or enabling products (eg, other direct costs (ODCs) and travel); and

Compliance with these criteria is only necessary for tasks/activities that are not yet complete; however, retrospective changes to the Baseline CMS are not to be made.

The CMS shall comply with the following benchmark criteria:

Note to drafters: The following benchmark criteria may require adapting for the nature and scope of the particular Contract, and drafters should liaise with their respective project controls policy areas and centres of expertise to determine if any adaptations need to be made.

tasks/activities with total float of greater than 220 working days shall be limited to less than 10% of the total number of tasks/activities;

no more than 40% of tasks/activities and milestones shall have float of less than 5 working days;

tasks/activities with durations between 5 working days and 40 working days shall comprise more than 70% of total tasks/activities;

tasks/activities or planning packages with durations greater than 100 working days shall comprise no more than 10% of total tasks/activities;

the combination of relationships with lags greater than 90 working days shall comprise no more than 5% of total relationships;

all relationship lags and date constraints shall contain a schedule note describing their purpose or origin;

Finish to Start relationships shall comprise more than 80% of total relationships;

there shall be no Start to Finish relationships;

the number of summary tasks/activities (or subprojects) and hammock tasks/activities shall be less than 35% of the total number of tasks/activities, milestones, summary tasks/activities (or subprojects), and hammock tasks/activities;

summary tasks/activities shall have no logic, resources or constraints;

no more than 10% of tasks/activities shall be constrained as “No Earlier Than” or “No Later Than”;

for the Baseline CMS, there shall be no hard constraints or other constraints that prevent the calculation of float values; and

for the Baseline CMS, there shall be no tasks/activities or milestones with negative float.

In calculating the percentages associated with the benchmark criteria, the calculations are not to include summary tasks/activities (or subprojects), hammock tasks/activities, milestones or tasks/activities in the past, but are to include both work packages and planning packages.

The CMS shall include a Master Milestone Register, which records the significant milestones (including all Contract Milestones) that the Contractor has planned to establish managerial control, contractual control, qualification for payment under the Contract, and any other important events associated with progression of the Contract.  The Master Milestone Register shall, for each milestone, include a set of measurable conditions that will be used to assess the achievement of the milestone.  The Master Milestone Register may be provided as a stand-alone document or may be integrated into the CMS if the CMS tool provides this functionality (eg, through use of the Notes function).

When requested by the Customer Representative, the CMS shall include written confirmation from any Approved Subcontractor that the Approved Subcontractor’s schedule is accurately represented in the CMS and is achievable.

The precedence relationships and dependencies in the CMS shall be consistent with:

all schedule constraints identified in the Contract (eg, in the Milestone entry and exit criteria); and

the entry and exit criteria for both Mandated System Reviews and Internal System Reviews.

The CMS shall include the Contractor’s estimates in relation to schedule estimating uncertainty.

Baseline CMS

Update Cycle

The Baseline CMS shall be maintained in accordance with the Contractor’s EVMS implementation for the Contract (or subject to a documented process for formal change control where earned value management is not applied) and the Maintenance and Update requirements of the CDRL.  Furthermore, an update to the Baseline CMS shall be provided to the Commonwealth for Approval when changes to the Baseline CMS are proposed that:

affect Contract Milestone payments;

affect baseline dates for the Contract Milestones; or

affect the ability of the Commonwealth to meet its obligations under the Contract.

An update to the Baseline CMS shall also be provided to the Commonwealth when status updates to the Baseline CMS (to produce the Statused CMS) have been developed that result in the delivery plan, as described by the Baseline CMS, being considered by the Commonwealth to no longer be feasible (ie, the current baseline dates for the Contract Milestones that are yet to occur are assessed as no longer being achievable).

When the production of a Statused CMS results in the need for a new Baseline CMS (as formally advised by the Commonwealth), the required updates to the current Baseline CMS shall be either:

incorporated into the next delivery of the Baseline CMS in accordance with the Maintenance and Update requirements of the CDRL; or

if a corresponding change to the Contract is required, incorporated into the Baseline CMS through a Contract Change Proposal (CCP) in accordance with the Contract change provisions set out in the COC.

Additional Baseline CMS Content

Except where otherwise agreed, in writing, by the Commonwealth Representative (including through an Approved plan), each submission of the Baseline CMS shall include:

a description of the schedule risk analysis process employed to address both estimating uncertainty and schedule risks (ie, those risks that are assessed as having a potential impact upon scheduled dates);

details of the parameters used to model estimating uncertainty and schedule risks (eg, three-point estimates), including:

identifying the tasks/activities for which these parameters have been applied;

describing the rationale for the selection of the particular tasks/activities and the associated modelling parameters; and

describing how any changes in the identified schedule risks since the last delivery of the Baseline CMS have been incorporated;

details of the outcomes of applying the schedule risk analysis process (eg, the histogram graphs for key Milestones after running Monte Carlo simulations); and

providing any additional information or explanation to ensure the outcomes of the schedule risk analysis process are clearly understood by both parties.

Each new submission of the Baseline CMS shall provide a narrative analysis for the newly proposed Baseline CMS, which contains:

a baseline change log, which identifies all of the baseline changes from the current Approved Baseline CMS and cumulatively identifies all of the baseline changes since the first version of the Approved Baseline CMS;

an explanation of the cause of each Contract Milestone’s rescheduled date that is later than the milestone's current baseline date in the current Approved Baseline CMS;

the identification of the possible impacts on other milestones and tasks/activities for the Contract, and a description of any proposed work-around plans to minimise the impact; and

where any of the benchmark criteria in clause 6.2.1.5 are not achieved in the Baseline CMS, rationale as to why that is the case, and its impact on the validity of the schedule.

Approval Criteria

The Baseline CMS is subject to Commonwealth Approval in accordance with the CDRL.  To allow for more objective assessment of the Baseline CMS, Approval will be based upon the following criteria:

the delivery plan, as described by the Baseline CMS, shall be assessed as feasible by the Commonwealth (ie, the current baseline dates for the Contract Milestones that are yet to occur are assessed as being achievable);

the Baseline CMS shall accord with the applicable provisions of this DID; and

the Baseline CMS shall be considered to be of sufficient reliability when the benchmark criteria identified in clause 6.2.1.5 are met, or any deviations are adequately explained to the satisfaction of the Commonwealth Representative.

Statused CMS

Update Cycle

The Statused CMS shall be provided in accordance with the CDRL and this clause 6.2.3.

Additional Statused CMS Content

The Statused CMS shall provide the current status against the Baseline CMS, statused in accordance with the Contractor’s EVMS implementation for the Contract (or subject to a documented process for schedule statusing where earned value management is not applied) and identifying:

time progress against all tasks/activities;

the actual start and completion dates for all tasks/activities and milestones; and

the current forecast completion dates for all tasks/activities and milestones.

Review of Statused CMS

The Statused CMS is provided for Commonwealth Review in accordance with the CDRL.  In response to the Commonwealth’s review comments, either:

a new Baseline CMS shall be provided for Approval, in accordance with clauses 6.2.2.1.2 and 6.2.2.1.3 of this DID, when the delivery plan, as described by the Statused CMS, is assessed by the Commonwealth as no longer being feasible (ie, the current baseline dates for the Contract Milestones that are yet to occur are assessed as no longer being achievable); or

the next delivery of the Statused CMS shall address the Commonwealth’s comments.

Annex:

- List of Schedule Terminology

ANNEX A TO
DID-PM-DEF-CMS

LIST OF SCHEDULE TERMINOLOGY

Terms and Definitions

The following terms are applicable to the development and management of a schedule:

Calendar. The arrangement of normal working days, together with non-working days, such as holidays, as well as special work days (ie, overtime periods) used to determine dates on which project work will be completed.

Constraints. Limits applied to network start and finish dates (eg, “finish no later than”). (Note: Certain types of constraints should be used judiciously because they may impact or distort the network critical path.)

Control Account. A natural management control point where the integration of scope, budget and schedule occurs. It represents the work assigned to one responsible organisational individual for the purpose of planning, monitoring and taking corrective action for the performance of one element of the CWBS.

Critical Path. A sequence of discrete tasks/activities in the network that has the longest total duration through the contract or project. Discrete tasks/activities along the critical path have the least amount of float/slack. The critical path and near-critical paths are calculated by the scheduling software application.

Duration. The length of time estimated (or realised) to accomplish a task/activity.

Early Finish (EF). The earliest finish date a task/activity or milestone can end. A computer-calculated date.

Early Start (ES). The earliest start date a task/activity or milestone can begin the precedence relationships. A computer-calculated date.

Free Float/Slack. The amount of time a task/activity or milestone can slip before it delays any of its successor tasks/activities or milestones.

Lag. An interval of time that must occur between a predecessor and successor task/activity or milestone. Since negative time is not demonstrable, negative lag is not to be used.  (Note: Lag should not be used to manipulate float/slack or constrain schedule.)

Late Finish (LF). The latest date a task/activity or milestone can finish without delaying the contract or project target completion date.  A computer-calculated date.

Late Start (LS). The latest start date a task/activity or milestone can start without delaying the contract or project target completion date.  A computer-calculated date.

Hammock Task/Activity. A task/activity that spans between two points in a schedule.  It has no set duration of its own, and its duration is derived from the difference in time between the two ‘connection points’ in the schedule.  (It can be thought of as ‘hanging’ between these two points in the same way a normal hammock may hang between two trees.)

Milestone. A specific definable accomplishment in the contract network, recognizable at a particular point in time.  Milestones have zero duration and do not consume resources.  Contract Milestones are identified in Attachment C to the Contract.

Percent Complete (Schedule). The proportion of a task/activity that has been completed to time now.  This usually involves updating or statusing the task/activity utilising one of the below methods:

updating the remaining time to complete (remaining duration) and the scheduling software will then automatically update the schedule percent complete; or

manually entering the physical percent complete value, as determined by the user.  This is considered expert judgement based on the physical progress of the task/activity.  If EVM is being applied, this assessment of progress would be defined through the applicable earned value techniques.

Planning Package.  The logical aggregation of future work within a control account that cannot yet be planned in detail at the work package or task/activity level.  When authorised work scope within a control account cannot be planned in the near-term, a planning package is used to hold the scope, schedule, and budget until the work is planned in detail and the planning package is converted into work packages. The planning package is time-phased with the known schedule requirements and is detail planned into work package(s) before any work is performed on the scope contained in the planning package.

Relationship/Dependency. These identify how predecessor and successor tasks/activities and milestones are logically linked. Relationships, also called network logic, are modelled in four ways:

FS (Finish to Start). A predecessor task/activity or milestone that must finish before a succeeding task/activity or milestone can start. FS relationships shall be used whenever possible.

SS (Start to Start). A predecessor task/activity or milestone that must start before a succeeding task/activity or milestone can start.

FF (Finish to Finish). A predecessor task/activity or milestone that must finish before a succeeding task/activity or milestone can finish.

SF (Start to Finish). A predecessor task/activity or milestone that must start before a succeeding task/activity or milestone can finish.

Rolling Wave Planning.  An iterative planning technique in which the work to be accomplished in the near term is planned in detail using work packages, while work further in the future is planned at a higher level using planning packages.

Schedule Margin. A management method for accommodating schedule contingencies.  (Note: It is a designated buffer that is identified separately from other tasks/activities in the schedule and considered part of the baseline.)  Schedule margin is the difference between contractual milestone date(s) and the contractor’s planned date(s) of accomplishment.

Subproject. A task/activity that represents a group of subordinate tasks/activities, which may be either internal to the schedule (in which case, it is the same as a Summary Task/Activity) or external to the schedule (eg, a team’s detailed schedule that is summarised into the main contract schedule).

Summary Task/Activity. A task/activity, which rolls up a series of directly related tasks/activities within the schedule’s coding structure into one summary task/activity (sometimes called ‘Main Tasks/Activities’).  There may be several layers of summary tasks/activities which can be designed to align with the CWBS.  Summary tasks/activities do not have a set duration; the duration is calculated from the underlying tasks/activities in the schedule structure.

Task/Activity. An element of work with duration.

Task/Activity Codes and Data Dictionary. A list of field definitions and code structures.  This list shall be provided to the Commonwealth.

Task/Activity and Milestone Descriptions. These are descriptive titles that are concise, complete, and clearly identify the work effort being accomplished.  Abbreviations may be used to shorten the descriptive titles.

Total Float/Slack. The amount of time a task/activity or milestone can slip before it delays the contract or project finish date.

User Defined Fields. Specific fields in the CMS defined by the user for management purposes.

Work Package. A natural sub-division of a control account and constitutes the basic building blocks used in detailed planning, controlling and measuring Contract performance. It describes work to be accomplished by a specific performing organisation and serves as a vehicle for monitoring and reporting progress of work. Work packages have scope, budget and scheduled start and finish dates.